## Sheet1
Task# | Bldg Name | FIM # | Task Name | Schedule % Complete | Actual % Complete | Scheduled Start | Actual/Projected Start | Scheduled Finish | Actual Finish
0 |  |  | Clemson Green Tiger 1 | 46% |  | Thu 9/15/22 |  | Wed 3/26/25
1 |  |  | Project Initiation | 68% |  | Thu 9/15/22 |  | Mon 5/1/23
2 |  |  | Signed Contract & Notice to Proceed | 100% |  | Thu 9/15/22 |  | Mon 9/26/22
3 |  |  | Issue Contract | 100% |  | Thu 9/15/22 |  | Thu 9/15/22
4 |  |  | Issue NTP | 100% |  | Mon 9/26/22 |  | Mon 9/26/22
5 |  |  | Mobilization | 100% |  | Thu 9/22/22 |  | Fri 12/23/22
6 |  |  | Submit Bonds/Insurance/Etc | 100% |  | Thu 9/22/22 |  | Thu 9/22/22
7 |  |  | Customer Kick off Meeting | 100% |  | Tue 11/15/22 |  | Tue 11/15/22
8 |  |  | Establish Project Office & Temporary Facilities | 100% |  | Fri 12/9/22 |  | Fri 12/23/22
9 |  |  | Preconstruction Planning | 57% |  | Thu 9/15/22 |  | Tue 11/1/22
10 |  |  | Organizational & Communication Plan | 100% |  | Mon 9/19/22 |  | Wed 9/21/22
11 |  |  | Diversity Plan | 0% |  | Thu 9/15/22 |  | Fri 9/16/22
12 |  |  | Schedule - SOV - Resource Plan | 100% |  | Mon 9/26/22 |  | Fri 10/7/22
13 |  |  | Quality Plan | 100% |  | Mon 10/10/22 |  | Fri 10/14/22
14 |  |  | Safety Plan | 100% |  | Tue 10/18/22 |  | Tue 10/25/22
15 |  |  | M&V Plan | 0% |  | Thu 9/15/22 |  | Wed 9/28/22
16 |  |  | Project Execution Plan | 0% |  | Tue 10/25/22 |  | Tue 11/1/22
17 |  |  | Award Subcontracts, P.O.'s & PSA's | 80% |  | Mon 9/26/22 |  | Mon 5/1/23
18 |  |  | Design Engineer | 100% |  | Mon 1/30/23 |  | Mon 1/30/23
19 |  |  | Water Conservation Sub | 100% |  | Thu 1/26/23 |  | Thu 1/26/23
20 |  |  | Lighting Sub | 100% |  | Mon 9/26/22 |  | Mon 9/26/22
21 |  |  | Building Automation Sub | 100% |  | Mon 9/26/22 |  | Mon 9/26/22
22 |  |  | Mechanical / Electrical / General Con Sub | 0% |  | Mon 5/1/23 |  | Mon 5/1/23
23 |  |  | Design & Submittals | 25% |  | Tue 12/13/22 |  | Wed 12/13/23
24 | Varies |  | Design Engineer (MEP) | 0% |  | Tue 3/7/23 |  | Thu 9/21/23
25 | Varies | 9 | FIM 9.0 Lab Controls Engineering | 0% |  | Tue 3/7/23 |  | Sat 6/10/23
26 | 35 | 9 | 35 Kinard Lab | 0% |  | Mon 5/1/23 |  | Mon 5/22/23
27 | 35 | 9 | Submit Design for Approval | 0% |  | Mon 5/1/23 |  | Mon 5/1/23
28 | 35 | 9 | CU | 0% |  | Tue 5/2/23 |  | Mon 5/15/23
29 | 35 | 9 | OSE | 0% |  | Tue 5/16/23 |  | Mon 5/22/23
30 | 35 | 9 | Customer Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
31 | 232A | 9 | 232A Rhodes Hall Annex | 100% |  | Mon 5/1/23 |  | Sat 6/10/23
32 | 232A | 9 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
33 | 232A | 9 | CU | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
34 | 232A | 9 | OSE | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
35 | 232A | 9 | Customer Approval | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
36 | 1277 | 9 | 1277 Life Sciences Building | 0% |  | Mon 5/1/23 |  | Mon 5/22/23
37 | 1277 | 9 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
38 | 1277 | 9 | CU | 0% |  | Tue 5/2/23 |  | Mon 5/15/23
39 | 1277 | 9 | OSE | 0% |  | Tue 5/16/23 |  | Mon 5/22/23
40 | 1277 | 9 | Customer Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
41 | 1259 | 9 | 1259 Biosystems Research Complex (BRC) | 0% |  | Tue 3/7/23 |  | Mon 3/27/23
42 | 1259 | 9 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
43 | 1259 | 9 | CU | 0% |  | Wed 3/8/23 |  | Tue 3/21/23
44 | 1259 | 9 | OSE | 0% |  | Wed 3/22/23 |  | Mon 3/27/23
45 | 1259 | 9 | Customer Approval | 0% |  | Mon 3/27/23 |  | Mon 3/27/23
46 | 1264 | 9 | 1264 Advanced Materials Research Lab | 0% |  | Mon 5/1/23 |  | Fri 5/19/23
47 | 1264 | 9 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
48 | 1264 | 9 | CU | 0% |  | Mon 5/1/23 |  | Fri 5/12/23
49 | 1264 | 9 | OSE | 0% |  | Mon 5/15/23 |  | Fri 5/19/23
50 | 1264 | 9 | Customer Approval | 0% |  | Fri 5/19/23 |  | Fri 5/19/23
51 | 272 | 9 | 272 Jordan Hall | 0% |  | Tue 3/7/23 |  | Mon 3/27/23
52 | 272 | 9 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
53 | 272 | 9 | CU | 0% |  | Wed 3/8/23 |  | Tue 3/21/23
54 | 272 | 9 | OSE | 0% |  | Wed 3/22/23 |  | Mon 3/27/23
55 | 272 | 9 | Customer Approval | 0% |  | Mon 3/27/23 |  | Mon 3/27/23
56 | 388 | 9 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Mon 5/1/23 |  | Mon 5/22/23
57 | 388 | 9 | Submit Design for Approval | 0% |  | Mon 5/1/23 |  | Mon 5/1/23
58 | 388 | 9 | CU | 0% |  | Tue 5/2/23 |  | Mon 5/15/23
59 | 388 | 9 | OSE | 0% |  | Tue 5/16/23 |  | Mon 5/22/23
60 | 388 | 9 | Customer Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
61 | Varies | 9.1, 10.0, 11.0, 12.0 | FIMs 9.1 / 10.0 / 11.0 / 12.0 Engineering | 0% |  | Mon 5/1/23 |  | Thu 9/21/23
62 | 388 | 9.1, 10.0 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Mon 5/1/23 |  | Fri 5/19/23
63 | 388 | 9.1, 10.0 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
64 | 388 | 9.1, 10.0 | CU | 0% |  | Mon 5/1/23 |  | Fri 5/12/23
65 | 388 | 9.1, 10.0 | OSE | 0% |  | Mon 5/15/23 |  | Fri 5/19/23
66 | 388 | 9.1, 10.0 | Customer Approval | 0% |  | Fri 5/19/23 |  | Fri 5/19/23
67 | 1264 | 9.1, 11.0, 12.0 | 1264 Advanced Materials Research Lab | 0% |  | Mon 5/1/23 |  | Fri 5/19/23
68 | 1264 | 9.1, 11.0, 12.0 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
69 | 1264 | 9.1, 11.0, 12.0 | CU | 0% |  | Mon 5/1/23 |  | Fri 5/12/23
70 | 1264 | 9.1, 11.0, 12.0 | OSE | 0% |  | Mon 5/15/23 |  | Fri 5/19/23
71 | 1264 | 9.1, 11.0, 12.0 | Customer Approval | 0% |  | Fri 5/19/23 |  | Fri 5/19/23
72 | 38 | 10 | 38 Mcadams Hall | 0% |  | Tue 8/1/23 |  | Fri 8/18/23
73 | 38 | 10 | Submit Design for Approval | 0% |  | Tue 8/1/23 |  | Tue 8/1/23
74 | 38 | 10 | CU | 0% |  | Wed 8/2/23 |  | Sun 8/13/23
75 | 38 | 10 | OSE | 0% |  | Mon 8/14/23 |  | Fri 8/18/23
76 | 38 | 10 | Customer Approval | 0% |  | Fri 8/18/23 |  | Fri 8/18/23
77 | 367 | 10 | 367 Hunter Hall | 0% |  | Sat 7/1/23 |  | Thu 7/20/23
78 | 367 | 10 | Submit Design for Approval | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
79 | 367 | 10 | CU | 0% |  | Mon 7/3/23 |  | Fri 7/14/23
80 | 367 | 10 | OSE | 0% |  | Sat 7/15/23 |  | Thu 7/20/23
81 | 367 | 10 | Customer Approval | 0% |  | Thu 7/20/23 |  | Thu 7/20/23
82 | 1059 | 10.0, 11.0, 12.0 | 1059 Ravenel Research Center | 0% |  | Mon 5/1/23 |  | Mon 5/22/23
83 | 1059 | 10.0, 11.0, 12.0 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
84 | 1059 | 10.0, 11.0, 12.0 | CU | 0% |  | Tue 5/2/23 |  | Mon 5/15/23
85 | 1059 | 10.0, 11.0, 12.0 | OSE | 0% |  | Tue 5/16/23 |  | Mon 5/22/23
86 | 1059 | 10.0, 11.0, 12.0 | Customer Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
87 | 1168 | 10 | 1168 Lebanon Road, 502 | 0% |  | Mon 5/1/23 |  | Mon 5/22/23
88 | 1168 | 10 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Mon 5/1/23
89 | 1168 | 10 | CU | 0% |  | Tue 5/2/23 |  | Mon 5/15/23
90 | 1168 | 10 | OSE | 0% |  | Tue 5/16/23 |  | Mon 5/22/23
91 | 1168 | 10 | Customer Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
92 | 1178 | 10 | 1178 Westinghouse Road, 509 | 0% |  | Fri 9/1/23 |  | Thu 9/21/23
93 | 1178 | 10 | Submit Design for Approval | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
94 | 1178 | 10 | CU | 0% |  | Mon 9/4/23 |  | Thu 9/14/23
95 | 1178 | 10 | OSE | 0% |  | Fri 9/15/23 |  | Thu 9/21/23
96 | 1178 | 10 | Customer Approval | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
97 | Varies |  | Controls Engineering | 43% |  | Tue 3/7/23 |  | Wed 12/13/23
98 | Varies | 5.1 | FIM 5.1 Retro Cx Engineering | 0% |  | Thu 6/1/23 |  | Wed 12/13/23
99 | 3 | 5.1 | 3 Godfrey Hall Cx Engineering | 100% |  | Thu 6/1/23 |  | Fri 6/16/23
100 | 3 | 5.1 | Submit Design for Approval | 100% |  | Thu 6/1/23 |  | Thu 6/1/23
101 | 3 | 5.1 | CU | 100% |  | Thu 6/15/23 |  | Thu 6/15/23
102 | 3 | 5.1 | Review & Approval | 100% |  | Fri 6/16/23 |  | Fri 6/16/23
103 | 6 | 5.1 | 6 Dillard Building Cx Engineering | 100% |  | Thu 6/1/23 |  | Fri 6/16/23
104 | 6 | 5.1 | Submit Design for Approval | 100% |  | Thu 6/1/23 |  | Thu 6/1/23
105 | 6 | 5.1 | CU | 100% |  | Thu 6/15/23 |  | Thu 6/15/23
106 | 6 | 5.1 | Review & Approval | 100% |  | Fri 6/16/23 |  | Fri 6/16/23
107 | 28 | 5.1 | 28 Lee Hall Cx Engineering | 100% |  | Thu 6/1/23 |  | Fri 6/16/23
108 | 28 | 5.1 | Submit Design for Approval | 100% |  | Thu 6/1/23 |  | Thu 6/1/23
109 | 28 | 5.1 | CU | 100% |  | Thu 6/15/23 |  | Thu 6/15/23
110 | 28 | 5.1 | Review & Approval | 100% |  | Fri 6/16/23 |  | Fri 6/16/23
111 | 35 | 5.1 | 35 Kinard Lab Cx Engineering | 0% |  | Tue 8/1/23 |  | Sun 8/13/23
112 | 35 | 5.1 | Submit Design for Approval | 0% |  | Tue 8/1/23 |  | Tue 8/1/23
113 | 35 | 5.1 | CU | 0% |  | Wed 8/2/23 |  | Sun 8/13/23
114 | 35 | 5.1 | Review & Approval | 0% |  | Sun 8/13/23 |  | Sun 8/13/23
115 | 38 | 5.1 | 38 Mcadams Hall Cx Engineering | 100% |  | Thu 6/1/23 |  | Fri 6/16/23
116 | 38 | 5.1 | Submit Design for Approval | 100% |  | Thu 6/1/23 |  | Thu 6/1/23
117 | 38 | 5.1 | CU | 100% |  | Thu 6/15/23 |  | Thu 6/15/23
118 | 38 | 5.1 | Review & Approval | 100% |  | Fri 6/16/23 |  | Fri 6/16/23
119 | 40 | 5.1 | 40 Poole Argiculutral Center Cx Engineering | 0% |  | Tue 8/1/23 |  | Sun 8/13/23
120 | 40 | 5.1 | Submit Design for Approval | 0% |  | Tue 8/1/23 |  | Tue 8/1/23
121 | 40 | 5.1 | CU | 0% |  | Wed 8/2/23 |  | Sun 8/13/23
122 | 40 | 5.1 | Review & Approval | 0% |  | Sun 8/13/23 |  | Sun 8/13/23
123 | 112 | 5.1 | 112 Harris A Smith Building Cx Engineering | 0% |  | Tue 8/1/23 |  | Sun 8/13/23
124 | 112 | 5.1 | Submit Design for Approval | 0% |  | Tue 8/1/23 |  | Tue 8/1/23
125 | 112 | 5.1 | CU | 0% |  | Wed 8/2/23 |  | Sun 8/13/23
126 | 112 | 5.1 | Review & Approval | 0% |  | Sun 8/13/23 |  | Sun 8/13/23
127 | 212 | 5.1 | 212 Cooper Library Cx Engineering | 0% |  | Sun 10/1/23 |  | Fri 10/13/23
128 | 212 | 5.1 | Submit Design for Approval | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
129 | 212 | 5.1 | CU | 0% |  | Mon 10/2/23 |  | Fri 10/13/23
130 | 212 | 5.1 | Review & Approval | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
131 | 232A | 5.1 | 232A Rhodes Hall Annex Cx Engineering | 0% |  | Sun 10/1/23 |  | Fri 10/13/23
132 | 232A | 5.1 | Submit Design for Approval | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
133 | 232A | 5.1 | CU | 0% |  | Mon 10/2/23 |  | Fri 10/13/23
134 | 232A | 5.1 | Review & Approval | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
135 | 265 | 5.1 | 265 Barre Hall Cx Engineering | 0% |  | Sun 10/1/23 |  | Fri 10/13/23
136 | 265 | 5.1 | Submit Design for Approval | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
137 | 265 | 5.1 | CU | 0% |  | Mon 10/2/23 |  | Fri 10/13/23
138 | 265 | 5.1 | Review & Approval | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
139 | 1059 | 5.1 | 1059 Ravenel Research Center Cx Engineering | 0% |  | Fri 12/1/23 |  | Wed 12/13/23
140 | 1059 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
141 | 1059 | 5.1 | CU | 0% |  | Sat 12/2/23 |  | Wed 12/13/23
142 | 1059 | 5.1 | Review & Approval | 0% |  | Wed 12/13/23 |  | Wed 12/13/23
143 | 1222 | 5.1 | 1222 Clemson Environmental Tech Lab CETL Cx Engineering | 0% |  | Fri 12/1/23 |  | Wed 12/13/23
144 | 1222 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
145 | 1222 | 5.1 | CU | 0% |  | Sat 12/2/23 |  | Wed 12/13/23
146 | 1222 | 5.1 | Review & Approval | 0% |  | Wed 12/13/23 |  | Wed 12/13/23
147 | 1227 | 5.1 | 1227 Hendrix Student Center Cx Engineering | 0% |  | Fri 12/1/23 |  | Wed 12/13/23
148 | 1227 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
149 | 1227 | 5.1 | CU | 0% |  | Sat 12/2/23 |  | Wed 12/13/23
150 | 1227 | 5.1 | Review & Approval | 0% |  | Wed 12/13/23 |  | Wed 12/13/23
151 | 1259 | 5.1 | 1259 Biosystems Research Complex (BRC) Cx Engineering | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
152 | 1259 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
153 | 1259 | 5.1 | CU | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
154 | 1259 | 5.1 | Review & Approval | 0% |  | Tue 12/12/23 |  | Tue 12/12/23
155 | 1264 | 5.1 | 1264 Advanced Materials Research Lab Cx Engineering | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
156 | 1264 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
157 | 1264 | 5.1 | CU | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
158 | 1264 | 5.1 | Review & Approval | 0% |  | Tue 12/12/23 |  | Tue 12/12/23
159 | 1277 | 5.1 | 1277 Life Sciences Building Cx Engineering | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
160 | 1277 | 5.1 | Submit Design for Approval | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
161 | 1277 | 5.1 | CU | 0% |  | Fri 12/1/23 |  | Tue 12/12/23
162 | 1277 | 5.1 | Review & Approval | 0% |  | Tue 12/12/23 |  | Tue 12/12/23
163 |  | 8 | FIM 8.0 Control Improvements Engineering | 100% |  | Tue 3/7/23 |  | Tue 6/27/23
164 | 4 | 8 | 4 Holtzendorff Hall Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
165 | 4 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
166 | 4 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
167 | 4 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
168 | 6 | 8 | 6 Dillard Building Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
169 | 6 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
170 | 6 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
171 | 6 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
172 | 10 | 8 | 10 Fike Recreation Center Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
173 | 10 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
174 | 10 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
175 | 10 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
176 | 30 | 8 | 30 Brackett Hall Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
177 | 30 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
178 | 30 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
179 | 30 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
180 | 31 | 8 | 31 Sikes Hall Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
181 | 31 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
182 | 31 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
183 | 31 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
184 | 35 | 8 | 35 Kinard Lab Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
185 | 35 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
186 | 35 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
187 | 35 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
188 | 39 | 8 | 39 Newman Hall Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
189 | 39 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
190 | 39 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
191 | 39 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
192 | 212 | 8 | 212 Cooper Library Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
193 | 212 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
194 | 212 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
195 | 212 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
196 | 216 | 8 | 216 Cook Lab Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
197 | 216 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
198 | 216 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
199 | 216 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
200 | 232A | 8 | 232A Rhodes Hall Annex Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
201 | 232A | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
202 | 232A | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
203 | 232A | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
204 | 318 | 8 | 318 Administrative Services Building (ASB) Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
205 | 318 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
206 | 318 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
207 | 318 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
208 | 406 | 8 | 406 Linvil Rich Environmental Research Lab Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
209 | 406 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
210 | 406 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
211 | 406 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
212 | 409 | 8 | 409 Wind Test Load Facility Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
213 | 409 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
214 | 409 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
215 | 409 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
216 | 420 | 8 | 420 Gas Turbine Lab #2 Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
217 | 420 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
218 | 420 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
219 | 420 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
220 | 446 | 8 | 446 Child Development Center Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
221 | 446 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
222 | 446 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
223 | 446 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
224 | 1059 | 8 | 1059 Ravenel Research Center Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
225 | 1059 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
226 | 1059 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
227 | 1059 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
228 | 1227 | 8 | 1227 Hendrix Student Center Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
229 | 1227 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
230 | 1227 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
231 | 1227 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
232 | 1241 | 8 | 1241 Wind Engineering Structures Lab Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
233 | 1241 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
234 | 1241 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
235 | 1241 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
236 | 1258 | 8 | 1258 Asphalt Rubber Technology Services (ARTS) Controls Engineering | 100% |  | Tue 3/7/23 |  | Tue 3/21/23
237 | 1258 | 8 | Submit Design for Approval | 100% |  | Tue 3/7/23 |  | Tue 3/7/23
238 | 1258 | 8 | CU | 100% |  | Wed 3/8/23 |  | Tue 3/21/23
239 | 1258 | 8 | Review & Approval | 100% |  | Tue 3/21/23 |  | Tue 3/21/23
240 | 1263 | 8 | 1263 Clemson Textiles Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
241 | 1263 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
242 | 1263 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
243 | 1263 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
244 | 1271 | 8 | 1271 Emerging Technology Center (ETC) Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
245 | 1271 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
246 | 1271 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
247 | 1271 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
248 | 6220 | 8 | 6220 University Facilities Complex Controls Engineering | 100% |  | Mon 5/1/23 |  | Tue 6/27/23
249 | 6220 | 8 | Submit Design for Approval | 100% |  | Mon 5/1/23 |  | Tue 5/9/23
250 | 6220 | 8 | CU | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
251 | 6220 | 8 | Review & Approval | 100% |  | Tue 6/27/23 |  | Tue 6/27/23
252 |  | 9 | FIM 9.0 Lab Controls Engineering | 42% |  | Tue 3/7/23 |  | Wed 6/28/23
253 | 35 | 9 | 35 Kinard Lab | 0% |  | Mon 5/1/23 |  | Mon 5/29/23
254 | 35 | 9 | Submit For Approval | 0% |  | Mon 5/1/23 |  | Mon 5/1/23
255 | 35 | 9 | RMF | 0% |  | Tue 5/2/23 |  | Mon 5/8/23
256 | 35 | 9 | CU | 0% |  | Tue 5/9/23 |  | Mon 5/22/23
257 | 35 | 9 | OSE | 0% |  | Tue 5/23/23 |  | Mon 5/29/23
258 | 35 | 9 | Review & Approval | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
259 | 232A | 9 | 232A Rhodes Hall Annex | 100% |  | Sat 4/1/23 |  | Sat 6/10/23
260 | 232A | 9 | Submit For Approval | 100% |  | Sat 4/1/23 |  | Mon 5/1/23
261 | 232A | 9 | RMF | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
262 | 232A | 9 | CU | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
263 | 232A | 9 | OSE | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
264 | 232A | 9 | Review & Approval | 100% |  | Sat 6/10/23 |  | Sat 6/10/23
265 | 1277 | 9 | 1277 Life Sciences Building | 52% |  | Sat 4/1/23 |  | Mon 5/29/23
266 | 1277 | 9 | Submit For Approval | 100% |  | Sat 4/1/23 |  | Mon 5/1/23
267 | 1277 | 9 | RMF | 0% |  | Tue 5/2/23 |  | Mon 5/8/23
268 | 1277 | 9 | CU | 0% |  | Tue 5/9/23 |  | Mon 5/22/23
269 | 1277 | 9 | OSE | 0% |  | Tue 5/23/23 |  | Mon 5/29/23
270 | 1277 | 9 | Review & Approval | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
271 | 1259 | 9 | 1259 Biosystems Research Complex (BRC) | 0% |  | Tue 3/7/23 |  | Sat 4/1/23
272 | 1259 | 9 | Submit For Approval | 0% |  | Tue 3/7/23 |  | Tue 3/7/23
273 | 1259 | 9 | RMF | 0% |  | Wed 3/8/23 |  | Tue 3/14/23
274 | 1259 | 9 | CU | 0% |  | Wed 3/15/23 |  | Mon 3/27/23
275 | 1259 | 9 | OSE | 0% |  | Tue 3/28/23 |  | Sat 4/1/23
276 | 1259 | 9 | Review & Approval | 0% |  | Sat 4/1/23 |  | Sat 4/1/23
277 | 1264 | 9 | 1264 Advanced Materials Research Lab | 52% |  | Sat 4/1/23 |  | Mon 5/29/23
278 | 1264 | 9 | Submit For Approval | 100% |  | Sat 4/1/23 |  | Mon 5/1/23
279 | 1264 | 9 | RMF | 0% |  | Tue 5/2/23 |  | Mon 5/8/23
280 | 1264 | 9 | CU | 0% |  | Tue 5/9/23 |  | Mon 5/22/23
281 | 1264 | 9 | OSE | 0% |  | Tue 5/23/23 |  | Mon 5/29/23
282 | 1264 | 9 | Review & Approval | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
283 | 272 | 9 | 272 Jordan Hall | 0% |  | Thu 6/1/23 |  | Wed 6/28/23
284 | 272 | 9 | Submit For Approval | 0% |  | Thu 6/1/23 |  | Thu 6/1/23
285 | 272 | 9 | RMF | 0% |  | Thu 6/1/23 |  | Wed 6/7/23
286 | 272 | 9 | CU | 0% |  | Thu 6/8/23 |  | Wed 6/21/23
287 | 272 | 9 | OSE | 0% |  | Thu 6/22/23 |  | Wed 6/28/23
288 | 272 | 9 | Review & Approval | 0% |  | Wed 6/28/23 |  | Wed 6/28/23
289 | 388 | 9 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 52% |  | Sat 4/1/23 |  | Mon 5/29/23
290 | 388 | 9 | Submit For Approval | 100% |  | Sat 4/1/23 |  | Mon 5/1/23
291 | 388 | 9 | RMF | 0% |  | Tue 5/2/23 |  | Mon 5/8/23
292 | 388 | 9 | CU | 0% |  | Tue 5/9/23 |  | Mon 5/22/23
293 | 388 | 9 | OSE | 0% |  | Tue 5/23/23 |  | Mon 5/29/23
294 | 388 | 9 | Review & Approval | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
295 |  | 9.1, 10.0, 11.0, 12.0 | FIMs 9.1 / 10.0 / 11.0 / 12.0 Controls Engineering | 0% |  | Fri 5/19/23 |  | Thu 9/21/23
296 | 388 | 9.1, 10.0 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Fri 5/19/23 |  | Fri 6/9/23
297 | 388 | 9.1, 10.0 | Submit For Approval | 0% |  | Fri 5/19/23 |  | Fri 5/19/23
298 | 388 | 9.1, 10.0 | CU | 0% |  | Mon 5/22/23 |  | Fri 6/2/23
299 | 388 | 9.1, 10.0 | OSE | 0% |  | Mon 6/5/23 |  | Fri 6/9/23
300 | 388 | 9.1, 10.0 | Review & Approval | 0% |  | Fri 6/9/23 |  | Fri 6/9/23
301 | 1264 | 9.1, 11.0, 12.0 | 1264 Advanced Materials Research Lab | 0% |  | Fri 6/30/23 |  | Tue 7/18/23
302 | 1264 | 9.1, 11.0, 12.0 | Submit For Approval | 0% |  | Fri 6/30/23 |  | Fri 6/30/23
303 | 1264 | 9.1, 11.0, 12.0 | CU | 0% |  | Fri 6/30/23 |  | Wed 7/12/23
304 | 1264 | 9.1, 11.0, 12.0 | OSE | 0% |  | Thu 7/13/23 |  | Tue 7/18/23
305 | 1264 | 9.1, 11.0, 12.0 | Review & Approval | 0% |  | Tue 7/18/23 |  | Tue 7/18/23
306 | 38 | 10 | 38 Mcadams Hall | 0% |  | Mon 6/26/23 |  | Fri 7/14/23
307 | 38 | 10 | Submit For Approval | 0% |  | Mon 6/26/23 |  | Mon 6/26/23
308 | 38 | 10 | CU | 0% |  | Tue 6/27/23 |  | Fri 7/7/23
309 | 38 | 10 | OSE | 0% |  | Mon 7/10/23 |  | Fri 7/14/23
310 | 38 | 10 | Review & Approval | 0% |  | Fri 7/14/23 |  | Fri 7/14/23
311 | 367 | 10 | 367 Hunter Hall | 0% |  | Thu 7/6/23 |  | Wed 7/26/23
312 | 367 | 10 | Submit For Approval | 0% |  | Thu 7/6/23 |  | Thu 7/6/23
313 | 367 | 10 | CU | 0% |  | Fri 7/7/23 |  | Wed 7/19/23
314 | 367 | 10 | OSE | 0% |  | Thu 7/20/23 |  | Wed 7/26/23
315 | 367 | 10 | Review & Approval | 0% |  | Wed 7/26/23 |  | Wed 7/26/23
316 | 1059 | 10.0, 11.0, 12.0 | 1059 Ravenel Research Center | 0% |  | Sat 7/15/23 |  | Wed 8/9/23
317 | 1059 | 10.0, 11.0, 12.0 | Submit For Approval | 0% |  | Sat 7/15/23 |  | Sat 7/15/23
318 | 1059 | 10.0, 11.0, 12.0 | RMF | 0% |  | Sat 7/15/23 |  | Thu 7/20/23
319 | 1059 | 10.0, 11.0, 12.0 | CU | 0% |  | Fri 7/21/23 |  | Wed 8/2/23
320 | 1059 | 10.0, 11.0, 12.0 | OSE | 0% |  | Thu 8/3/23 |  | Wed 8/9/23
321 | 1059 | 10.0, 11.0, 12.0 | Review & Approval | 0% |  | Wed 8/9/23 |  | Wed 8/9/23
322 | 1168 | 10 | 1168 Lebanon Road, 502 | 0% |  | Sat 7/15/23 |  | Wed 8/2/23
323 | 1168 | 10 | Submit For Approval | 0% |  | Sat 7/15/23 |  | Sat 7/15/23
324 | 1168 | 10 | CU | 0% |  | Sat 7/15/23 |  | Thu 7/27/23
325 | 1168 | 10 | OSE | 0% |  | Fri 7/28/23 |  | Wed 8/2/23
326 | 1168 | 10 | Review & Approval | 0% |  | Wed 8/2/23 |  | Wed 8/2/23
327 | 1178 | 10 | 1178 Westinghouse Road, 509 | 0% |  | Fri 9/1/23 |  | Thu 9/21/23
328 | 1178 | 10 | Submit For Approval | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
329 | 1178 | 10 | CU | 0% |  | Mon 9/4/23 |  | Thu 9/14/23
330 | 1178 | 10 | OSE | 0% |  | Fri 9/15/23 |  | Thu 9/21/23
331 | 1178 | 10 | Review & Approval | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
332 |  |  | Equipment Submittals | 12% |  | Tue 12/13/22 |  | Thu 10/19/23
333 |  | 1.1, 1.2 | FIM 1.1, 1.2 Lighting Eq Submittals | 100% |  | Tue 12/13/22 |  | Wed 1/4/23
334 |  | 1.1, 1.2 | Interior / Exterior Lighting Submittals - All Buildings | 100% |  | Tue 12/13/22 |  | Wed 1/4/23
335 |  | 1.1, 1.2 | Submit Equipment Submittal | 100% | 100% | Tue 12/13/22 | 2023-04-04 | Tue 12/13/22 | 2023-04-04
336 |  | 1.1, 1.2 | Submit Design for Approval | 100% | 100% | Wed 12/14/22 | 2023-04-04 | Wed 12/14/22 | 2023-04-04
337 |  | 1.1, 1.2 | CU | 100% | 100% | Thu 12/15/22 | 2023-04-04 | Wed 12/28/22 | 2023-04-04
338 |  | 1.1, 1.2 | OSE | 100% | 100% | Thu 12/29/22 | 2023-04-04 | Wed 1/4/23 | 2023-04-04
339 |  | 1.1, 1.2 | Submittal Approval and Release | 100% | 100% | Wed 1/4/23 | 2023-04-04 | Wed 1/4/23 | 2023-04-04
340 |  | 2.1 | FIM 2.1 Water Conservation Eq Submittals | 100% |  | Wed 3/15/23 |  | Mon 4/3/23
341 |  | 2.1 | Water Conservation - All Buildings | 100% |  | Wed 3/15/23 |  | Mon 4/3/23
342 |  | 2.1 | Submit Equipment Submittal | 100% | 100% | Wed 3/15/23 | 2023-05-08 | Wed 3/15/23 | 2023-05-08
343 |  | 2.1 | Submit Design for Approval | 100% | 100% | Wed 3/15/23 | 2023-05-08 | Wed 3/15/23 | 2023-05-08
344 |  | 2.1 | CU | 100% | 100% | Thu 3/16/23 | 2023-05-08 | Mon 4/3/23 | 2023-05-08
345 |  | 2.1 | Submittal Approval and Release | 100% | 100% | Mon 4/3/23 | 2023-05-08 | Mon 4/3/23 | 2023-05-08
346 |  | 3.1 | FIM 3.1 Steam Trap Eq Submittals | 0% |  | Sat 7/1/23 |  | Fri 7/14/23
347 |  | 3.1 | Steam Trap Submittals - All Buildings | 0% |  | Sat 7/1/23 |  | Fri 7/14/23
348 |  | 3.1 | Submit Equipment Submittal | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
349 |  | 3.1 | Submit Design for Approval | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
350 |  | 3.1 | CU | 0% |  | Mon 7/3/23 |  | Fri 7/14/23
351 |  | 3.1 | Submittal Approval and Release | 0% |  | Fri 7/14/23 |  | Fri 7/14/23
352 |  | 3.2 | FIM 3.2 Mechanical Insulation Matl Submittals | 9% |  | Fri 3/17/23 |  | Sat 7/1/23
353 |  | 3.2 | Mechanical Insulation Submittals - All Buildings | 9% |  | Fri 3/17/23 |  | Sat 7/1/23
354 |  | 3.2 | Submit Equipment Submittal | 100% |  | Sat 7/1/23 |  | Sat 7/1/23
355 |  | 3.2 | Submit Design for Approval | 100% |  | Fri 3/17/23 |  | Fri 3/17/23
356 |  | 3.2 | CU | 0% |  | Mon 3/20/23 |  | Thu 3/30/23
357 |  | 3.2 | Submittal Approval and Release | 0% |  | Thu 3/30/23 |  | Thu 3/30/23
358 |  | 3.3 | FIM 3.3 Condensate Receive Repair Eq Submittals | 0% |  | Sat 7/1/23 |  | Fri 7/14/23
359 |  | 3.3 | Consensate Receiver Repair - All Buildings | 0% |  | Sat 7/1/23 |  | Fri 7/14/23
360 |  | 3.3 | Submit Equipment Submittal | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
361 |  | 3.3 | Submit Design for Approval | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
362 |  | 3.3 | CU | 0% |  | Mon 7/3/23 |  | Fri 7/14/23
363 |  | 3.3 | Submittal Approval and Release | 0% |  | Fri 7/14/23 |  | Fri 7/14/23
364 |  | 4.1 | FIM 4.1 HVAC Seal Matl Submittals | 100% |  | Wed 2/8/23 |  | Wed 2/22/23
365 |  | 4.1 | HVAC Seals - All Buildings | 100% |  | Wed 2/8/23 |  | Wed 2/22/23
366 |  | 4.1 | Submit Equipment Submittal | 100% | 100% | Wed 2/8/23 | 2023-02-21 | Wed 2/8/23 | 2023-02-21
367 |  | 4.1 | Submit Design for Approval | 100% | 100% | Wed 2/8/23 | 2023-02-21 | Wed 2/8/23 | 2023-02-21
368 |  | 4.1 | CU | 100% | 100% | Thu 2/9/23 | 2023-02-21 | Wed 2/22/23 | 2023-02-21
369 |  | 4.1 | Submittal Approval and Release | 100% | 100% | Wed 2/22/23 | 2023-02-21 | Wed 2/22/23 | 2023-02-21
370 |  | 6.1 | FIM 6.1 Building Envelope Matl Submittals | 100% |  | Mon 3/20/23 |  | Fri 6/23/23
371 |  | 6.1 | Building Envelope - All Buildings | 100% |  | Mon 3/20/23 |  | Fri 6/23/23
372 |  | 6.1 | Submit Equipment Submittal | 100% | 100% | Mon 3/20/23 | 2023-03-27 | Mon 3/20/23 | 2023-03-27
373 |  | 6.1 | Submit Design for Approval | 100% | 100% | Mon 3/20/23 | 2023-03-27 | Mon 3/20/23 | 2023-03-27
374 |  | 6.1 | CU | 100% | 100% | Fri 6/23/23 | 2023-03-27 | Fri 6/23/23 | 2023-03-27
375 |  | 6.1 | Submittal Approval and Release | 100% | 100% | Fri 6/23/23 | 2023-03-27 | Fri 6/23/23 | 2023-03-27
376 |  | 8.1 | FIM 8.1 Kitchen Hood Eq Submittals | 0% |  | Thu 6/29/23 |  | Tue 7/25/23
377 | 223 | 8.1 | 223 Schilletter Dining Hall Equipment Submittals | 0% |  | Thu 6/29/23 |  | Tue 7/25/23
378 | 223 | 8.1 | Submit Equipment Submittal | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
379 | 223 | 8.1 | Submit Design for Approval | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
380 | 223 | 8.1 | RMF | 0% |  | Fri 6/30/23 |  | Wed 7/5/23
381 | 223 | 8.1 | CU | 0% |  | Thu 7/6/23 |  | Tue 7/18/23
382 | 223 | 8.1 | OSE | 0% |  | Wed 7/19/23 |  | Tue 7/25/23
383 | 223 | 8.1 | Submittal Approval and Release | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
384 | 1284 | 8.1 | 1284 Gressette Hall Equipment Submittals | 0% |  | Thu 6/29/23 |  | Tue 7/25/23
385 | 1284 | 8.1 | Submit Equipment Submittal | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
386 | 1284 | 8.1 | Submit Design for Approval | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
387 | 1284 | 8.1 | RMF | 0% |  | Fri 6/30/23 |  | Wed 7/5/23
388 | 1284 | 8.1 | CU | 0% |  | Thu 7/6/23 |  | Tue 7/18/23
389 | 1284 | 8.1 | OSE | 0% |  | Wed 7/19/23 |  | Tue 7/25/23
390 | 1284 | 8.1 | Submittal Approval and Release | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
391 | 1307 | 8.1 | 1307 Mcalister Hall Equipment Submittals | 0% |  | Thu 6/29/23 |  | Tue 7/25/23
392 | 1307 | 8.1 | Submit Equipment Submittal | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
393 | 1307 | 8.1 | Submit Design for Approval | 0% |  | Thu 6/29/23 |  | Thu 6/29/23
394 | 1307 | 8.1 | RMF | 0% |  | Fri 6/30/23 |  | Wed 7/5/23
395 | 1307 | 8.1 | CU | 0% |  | Thu 7/6/23 |  | Tue 7/18/23
396 | 1307 | 8.1 | OSE | 0% |  | Wed 7/19/23 |  | Tue 7/25/23
397 | 1307 | 8.1 | Submittal Approval and Release | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
398 |  | 9 | FIM 9.0 Lab Conrtols Eq Submittals | 4% |  | Sat 4/1/23 |  | Mon 8/21/23
399 | 35 | 9 | 35 Kinard Lab Equipment Submittals | 0% |  | Mon 5/29/23 |  | Tue 6/27/23
400 | 35 | 9 | Submit Equipment Submittal | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
401 | 35 | 9 | Submit Design for Approval | 0% |  | Tue 5/30/23 |  | Tue 5/30/23
402 | 35 | 9 | RMF | 0% |  | Wed 5/31/23 |  | Tue 6/6/23
403 | 35 | 9 | CU | 0% |  | Wed 6/7/23 |  | Tue 6/20/23
404 | 35 | 9 | OSE | 0% |  | Wed 6/21/23 |  | Tue 6/27/23
405 | 35 | 9 | Submittal Approval and Release | 0% |  | Tue 6/27/23 |  | Tue 6/27/23
406 | 232A | 9 | 232A Rhodes Hall Annex Equipment Submittals | 99% |  | Tue 5/30/23 |  | Tue 5/30/23
407 | 232A | 9 | Submit Equipment Submittal | 100% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
408 | 232A | 9 | Submit Design for Approval | 100% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
409 | 232A | 9 | RMF | 100% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
410 | 232A | 9 | CU | 100% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
411 | 232A | 9 | OSE | 100% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
412 | 232A | 9 | Submittal Approval and Release | 0% | 100% | Tue 5/30/23 | 2023-06-06 | Tue 5/30/23 | 2023-06-06
413 | 1277 | 9 | 1277 Life Sciences Building Equipment Submittals | 5% |  | Tue 5/30/23 |  | Tue 6/27/23
414 | 1277 | 9 | Submit Equipment Submittal | 100% | 100% | Tue 5/30/23 | 2023-06-22 | Tue 5/30/23 | 2023-06-22
415 | 1277 | 9 | Submit Design for Approval | 100% | 100% | Tue 5/30/23 | 2023-06-22 | Tue 5/30/23 | 2023-06-22
416 | 1277 | 9 | RMF | 0% | 100% | Wed 5/31/23 | 2023-06-22 | Tue 6/6/23 | 2023-06-22
417 | 1277 | 9 | CU | 0% | 100% | Wed 6/7/23 | 2023-06-22 | Tue 6/20/23 | 2023-06-22
418 | 1277 | 9 | OSE | 0% | 100% | Wed 6/21/23 | 2023-06-22 | Tue 6/27/23 | 2023-06-22
419 | 1277 | 9 | Submittal Approval and Release | 0% | 100% | Tue 6/27/23 | 2023-06-22 | Tue 6/27/23 | 2023-06-22
420 | 1259 | 9 | 1259 Biosystems Research Complex (BRC) Equipment Submittals | 0% |  | Sat 4/1/23 |  | Mon 5/1/23
421 | 1259 | 9 | Submit Equipment Submittal | 0% |  | Sat 4/1/23 |  | Sat 4/1/23
422 | 1259 | 9 | Submit Design for Approval | 0% |  | Mon 4/3/23 |  | Mon 4/3/23
423 | 1259 | 9 | RMF | 0% |  | Tue 4/4/23 |  | Mon 4/10/23
424 | 1259 | 9 | CU | 0% |  | Tue 4/11/23 |  | Mon 4/24/23
425 | 1259 | 9 | OSE | 0% |  | Tue 4/25/23 |  | Mon 5/1/23
426 | 1259 | 9 | Submittal Approval and Release | 0% |  | Mon 5/1/23 |  | Mon 5/1/23
427 | 1264 | 9 | 1264 Advanced Materials Research Lab Equipment Submittals | 0% |  | Sun 7/30/23 |  | Mon 8/21/23
428 | 1264 | 9 | Submit Equipment Submittal | 0% | 100% | Sun 7/30/23 | 2023-05-02 | Sun 7/30/23 | 2023-05-02
429 | 1264 | 9 | Submit Design for Approval | 0% | 100% | Sun 7/30/23 | 2023-05-02 | Sun 7/30/23 | 2023-05-02
430 | 1264 | 9 | RMF | 0% | 100% | Mon 7/31/23 | 2023-05-02 | Fri 8/4/23 | 2023-05-02
431 | 1264 | 9 | CU | 0% | 100% | Mon 8/7/23 | 2023-05-02 | Wed 8/16/23 | 2023-05-02
432 | 1264 | 9 | OSE | 0% | 100% | Thu 8/17/23 | 2023-05-02 | Mon 8/21/23 | 2023-05-02
433 | 1264 | 9 | Submittal Approval and Release | 0% | 100% | Mon 8/21/23 | 2023-05-02 | Mon 8/21/23 | 2023-05-02
434 | 272 | 9 | 272 Jordan Hall Equipment Submittals | 0% |  | Sun 7/30/23 |  | Mon 8/21/23
435 | 272 | 9 | Submit Equipment Submittal | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
436 | 272 | 9 | Submit Design for Approval | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
437 | 272 | 9 | RMF | 0% |  | Mon 7/31/23 |  | Fri 8/4/23
438 | 272 | 9 | CU | 0% |  | Mon 8/7/23 |  | Wed 8/16/23
439 | 272 | 9 | OSE | 0% |  | Thu 8/17/23 |  | Mon 8/21/23
440 | 272 | 9 | Submittal Approval and Release | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
441 | 388 | 9 | 388 Fluor Daniel (Engineering Innovation Center) EIB Equipment Submittals | 0% |  | Mon 5/29/23 |  | Tue 6/27/23
442 | 388 | 9 | Submit Equipment Submittal | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
443 | 388 | 9 | Submit Design for Approval | 0% |  | Tue 5/30/23 |  | Tue 5/30/23
444 | 388 | 9 | RMF | 0% |  | Wed 5/31/23 |  | Tue 6/6/23
445 | 388 | 9 | CU | 0% |  | Wed 6/7/23 |  | Tue 6/20/23
446 | 388 | 9 | OSE | 0% |  | Wed 6/21/23 |  | Tue 6/27/23
447 | 388 | 9 | Submittal Approval and Release | 0% |  | Tue 6/27/23 |  | Tue 6/27/23
448 |  | 9.1 | FIM 9.1 Heat Coil Recovery Eq Submittals | 0% |  | Sun 7/30/23 |  | Mon 8/21/23
449 | 388 | 9.1 | 388 Fluor Daniel (Engineering Innovation Center) EIB Equipment Submittals | 0% |  | Sun 7/30/23 |  | Mon 8/21/23
450 | 388 | 9.1 | Submit Equipment Submittal | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
451 | 388 | 9.1 | Submit Design for Approval | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
452 | 388 | 9.1 | RMF | 0% |  | Mon 7/31/23 |  | Fri 8/4/23
453 | 388 | 9.1 | CU | 0% |  | Mon 8/7/23 |  | Wed 8/16/23
454 | 388 | 9.1 | OSE | 0% |  | Thu 8/17/23 |  | Mon 8/21/23
455 | 388 | 9.1 | Submittal Approval and Release | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
456 | 1264 | 9.1 | 1264 Advanced Materials Research Lab Equipment Submittals | 0% |  | Sun 7/30/23 |  | Mon 8/21/23
457 | 1264 | 9.1 | Submit Equipment Submittal | 0% | 100% | Sun 7/30/23 | 2023-09-18 | Sun 7/30/23 | 2023-09-18
458 | 1264 | 9.1 | Submit Design for Approval | 0% | 100% | Sun 7/30/23 | 2023-09-18 | Sun 7/30/23 | 2023-09-18
459 | 1264 | 9.1 | RMF | 0% | 100% | Mon 7/31/23 | 2023-09-18 | Fri 8/4/23 | 2023-09-18
460 | 1264 | 9.1 | CU | 0% | 100% | Mon 8/7/23 | 2023-09-18 | Wed 8/16/23 | 2023-09-18
461 | 1264 | 9.1 | OSE | 0% | 100% | Thu 8/17/23 | 2023-09-18 | Mon 8/21/23 | 2023-09-18
462 | 1264 | 9.1 | Submittal Approval and Release | 0% | 100% | Mon 8/21/23 | 2023-09-18 | Mon 8/21/23 | 2023-09-18
463 |  | 10 | FIM 10.0 HVAC Upgrades Eq Submittals | 2% |  | Fri 5/19/23 |  | Thu 10/19/23
464 | 38 | 10 | 38 Mcadams Hall Equipment Submittals | 0% |  | Fri 8/18/23 |  | Mon 9/11/23
465 | 38 | 10 | Submit Equipment Submittal | 0% | 100% | Fri 8/18/23 | 2023-07-14 | Fri 8/18/23 | 2023-07-14
466 | 38 | 10 | Submit Design for Approval | 0% | 100% | Sat 8/19/23 | 2023-07-14 | Sat 8/19/23 | 2023-07-14
467 | 38 | 10 | RMF | 0% | 100% | Sun 8/20/23 | 2023-07-14 | Thu 8/24/23 | 2023-07-14
468 | 38 | 10 | CU | 0% | 100% | Fri 8/25/23 | 2023-07-14 | Tue 9/5/23 | 2023-07-14
469 | 38 | 10 | OSE | 0% | 100% | Wed 9/6/23 | 2023-07-14 | Mon 9/11/23 | 2023-07-14
470 | 38 | 10 | Submittal Approval and Release | 0% | 100% | Mon 9/11/23 | 2023-07-14 | Mon 9/11/23 | 2023-07-14
471 | 367 | 10 | 367 Hunter Hall Equipment Submittals | 0% |  | Thu 7/20/23 |  | Tue 8/15/23
472 | 367 | 10 | Submit Equipment Submittal | 0% | 100% | Thu 7/20/23 | 2023-09-07 | Thu 7/20/23 | 2023-09-07
473 | 367 | 10 | Submit Design for Approval | 0% | 100% | Fri 7/21/23 | 2023-09-07 | Fri 7/21/23 | 2023-09-07
474 | 367 | 10 | RMF | 0% | 100% | Mon 7/24/23 | 2023-09-07 | Fri 7/28/23 | 2023-09-07
475 | 367 | 10 | CU | 0% | 100% | Sun 7/30/23 | 2023-09-07 | Thu 8/10/23 | 2023-09-07
476 | 367 | 10 | OSE | 0% | 100% | Fri 8/11/23 | 2023-09-07 | Tue 8/15/23 | 2023-09-07
477 | 367 | 10 | Submittal Approval and Release | 0% | 100% | Tue 8/15/23 | 2023-09-07 | Tue 8/15/23 | 2023-09-07
478 | 388 | 10 | 388 Fluor Daniel (Engineering Innovation Center) EIB Equipment Submittals | 0% |  | Fri 5/19/23 |  | Mon 6/19/23
479 | 388 | 10 | Submit Equipment Submittal | 0% | 100% | Fri 5/19/23 | 2023-06-16 | Fri 5/19/23 | 2023-06-16
480 | 388 | 10 | Submit Design for Approval | 0% | 100% | Mon 5/22/23 | 2023-06-16 | Mon 5/22/23 | 2023-06-16
481 | 388 | 10 | RMF | 0% | 100% | Tue 5/23/23 | 2023-06-16 | Mon 5/29/23 | 2023-06-16
482 | 388 | 10 | CU | 0% | 100% | Tue 5/30/23 | 2023-06-16 | Mon 6/12/23 | 2023-06-16
483 | 388 | 10 | OSE | 0% | 100% | Tue 6/13/23 | 2023-06-16 | Mon 6/19/23 | 2023-06-16
484 | 388 | 10 | Submittal Approval and Release | 0% | 100% | Mon 6/19/23 | 2023-06-16 | Mon 6/19/23 | 2023-06-16
485 | 1059 | 10 | 1059 Ravenel Research Center Equipment Submittals | 12% |  | Tue 5/30/23 |  | Tue 6/20/23
486 | 1059 | 10 | Submit Equipment Submittal | 100% | 100% | Tue 5/30/23 | 2023-05-24 | Tue 5/30/23 | 2023-05-24
487 | 1059 | 10 | Submit Design for Approval | 100% | 100% | Tue 5/30/23 | 2023-05-24 | Tue 5/30/23 | 2023-05-24
488 | 1059 | 10 | RMF | 100% | 100% | Tue 5/30/23 | 2023-05-24 | Tue 5/30/23 | 2023-05-24
489 | 1059 | 10 | CU | 0% | 100% | Wed 5/31/23 | 2023-05-24 | Tue 6/13/23 | 2023-05-24
490 | 1059 | 10 | OSE | 0% | 100% | Wed 6/14/23 | 2023-05-24 | Tue 6/20/23 | 2023-05-24
491 | 1059 | 10 | Submittal Approval and Release | 0% | 100% | Tue 6/20/23 | 2023-05-24 | Tue 6/20/23 | 2023-05-24
492 | 1168 | 10 | 1168 Lebanon Road, 502 Equipment Submittals | 0% |  | Mon 5/22/23 |  | Tue 6/20/23
493 | 1168 | 10 | Submit Equipment Submittal | 0% | 100% | Mon 5/22/23 | 2023-05-05 | Mon 5/22/23 | 2023-05-05
494 | 1168 | 10 | Submit Design for Approval | 0% | 100% | Tue 5/23/23 | 2023-05-05 | Tue 5/23/23 | 2023-05-05
495 | 1168 | 10 | RMF | 0% | 100% | Wed 5/24/23 | 2023-05-05 | Tue 5/30/23 | 2023-05-05
496 | 1168 | 10 | CU | 0% | 100% | Wed 5/31/23 | 2023-05-05 | Tue 6/13/23 | 2023-05-05
497 | 1168 | 10 | OSE | 0% | 100% | Wed 6/14/23 | 2023-05-05 | Tue 6/20/23 | 2023-05-05
498 | 1168 | 10 | Submittal Approval and Release | 0% | 100% | Tue 6/20/23 | 2023-05-05 | Tue 6/20/23 | 2023-05-05
499 | 1178 | 10 | 1178 Westinghouse Road, 509 Equipment Submittals | 0% |  | Thu 9/21/23 |  | Thu 10/19/23
500 | 1178 | 10 | Submit Equipment Submittal | 0% | 100% | Thu 9/21/23 | 2023-09-07 | Thu 9/21/23 | 2023-09-07
501 | 1178 | 10 | Submit Design for Approval | 0% | 100% | Fri 9/22/23 | 2023-09-07 | Fri 9/22/23 | 2023-09-07
502 | 1178 | 10 | RMF | 0% | 100% | Mon 9/25/23 | 2023-09-07 | Fri 9/29/23 | 2023-09-07
503 | 1178 | 10 | CU | 0% | 100% | Sun 10/1/23 | 2023-09-07 | Thu 10/12/23 | 2023-09-07
504 | 1178 | 10 | OSE | 0% | 100% | Fri 10/13/23 | 2023-09-07 | Thu 10/19/23 | 2023-09-07
505 | 1178 | 10 | Submittal Approval and Release | 0% | 100% | Thu 10/19/23 | 2023-09-07 | Thu 10/19/23 | 2023-09-07
506 |  | 11 | FIM 11.0 Chiller Plant Eq Submittals | 44% |  | Mon 3/27/23 |  | Tue 6/20/23
507 | 1059 | 11 | 1059 Ravenel Research Center Equipment Submittals | 12% |  | Mon 4/24/23 |  | Tue 6/20/23
508 | 1059 | 11 | Submit Equipment Submittal | 100% |  | Mon 4/24/23 |  | Mon 4/24/23
509 | 1059 | 11 | Submit Design for Approval | 100% |  | Mon 4/24/23 |  | Mon 4/24/23
510 | 1059 | 11 | RMF | 100% |  | Tue 5/30/23 |  | Tue 5/30/23
511 | 1059 | 11 | CU | 0% |  | Wed 5/31/23 |  | Tue 6/13/23
512 | 1059 | 11 | OSE | 0% |  | Wed 6/14/23 |  | Tue 6/20/23
513 | 1059 | 11 | Submittal Approval and Release | 0% |  | Tue 6/20/23 |  | Tue 6/20/23
514 | 1264 | 11 | 1264 Advanced Materials Research Lab Equipment Submittals | 100% |  | Mon 3/27/23 |  | Thu 4/6/23
515 | 1264 | 11 | Submit Equipment Submittal | 100% |  | Mon 3/27/23 |  | Mon 3/27/23
516 | 1264 | 11 | Submit Design for Approval | 100% |  | Mon 3/27/23 |  | Mon 3/27/23
517 | 1264 | 11 | RMF | 100% |  | Tue 3/28/23 |  | Wed 3/29/23
518 | 1264 | 11 | CU | 100% |  | Thu 3/30/23 |  | Thu 4/6/23
519 | 1264 | 11 | OSE | 100% |  | Thu 4/6/23 |  | Thu 4/6/23
520 | 1264 | 11 | Submittal Approval and Release | 100% |  | Thu 4/6/23 |  | Thu 4/6/23
521 |  | 12 | FIM 12.0 Heating Plant Eq Submittals | 0% |  | Fri 5/19/23 |  | Mon 6/26/23
522 | 1059 | 12 | 1059 Ravenel Research Center Equipment Submittals | 0% |  | Mon 5/22/23 |  | Tue 6/20/23
523 | 1059 | 12 | Submit Equipment Submittal | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
524 | 1059 | 12 | Submit Design for Approval | 0% |  | Tue 5/23/23 |  | Tue 5/23/23
525 | 1059 | 12 | RMF | 0% |  | Wed 5/24/23 |  | Tue 5/30/23
526 | 1059 | 12 | CU | 0% |  | Wed 5/31/23 |  | Tue 6/13/23
527 | 1059 | 12 | OSE | 0% |  | Wed 6/14/23 |  | Tue 6/20/23
528 | 1059 | 12 | Submittal Approval and Release | 0% |  | Tue 6/20/23 |  | Tue 6/20/23
529 | 1264 | 12 | 1264 Advanced Materials Research Lab Equipment Submittals | 0% |  | Fri 5/19/23 |  | Mon 6/26/23
530 | 1264 | 12 | Submit Equipment Submittal | 0% |  | Fri 5/19/23 |  | Fri 5/19/23
531 | 1264 | 12 | Submit Design for Approval | 0% |  | Mon 5/22/23 |  | Mon 5/22/23
532 | 1264 | 12 | RMF | 0% |  | Tue 5/23/23 |  | Mon 6/5/23
533 | 1264 | 12 | CU | 0% |  | Tue 6/6/23 |  | Mon 6/19/23
534 | 1264 | 12 | OSE | 0% |  | Tue 6/20/23 |  | Mon 6/26/23
535 | 1264 | 12 | Submittal Approval and Release | 0% |  | Mon 6/26/23 |  | Mon 6/26/23
536 |  |  | Material Procurement | 0% |  | Wed 2/1/23 |  | Thu 3/7/24
537 |  |  | Long Lead Purchase Items | 0% |  | Wed 2/1/23 |  | Thu 3/7/24
538 |  | 9 | FIM 9.0 Lab Controls Material | 0% |  | Wed 2/1/23 |  | Tue 8/29/23
539 | 35 | 9 | 35 Kinard Lab | 100% |  | Wed 2/1/23 |  | Wed 3/15/23
540 | 35 | 9 | Order Equipment | 100% |  | Wed 2/1/23 |  | Wed 2/1/23
541 | 35 | 9 | Site Receipt | 100% |  | Wed 3/15/23 |  | Wed 3/15/23
542 | 232A | 9 | 232A Rhodes Hall Annex | 100% |  | Wed 2/1/23 |  | Wed 3/15/23
543 | 232A | 9 | Order Equipment | 100% | 100% | Wed 2/1/23 | 2023-06-08 | Wed 2/1/23 | 2023-06-08
544 | 232A | 9 | Site Receipt | 100% | 100% | Wed 3/15/23 | 2023-06-20 | Wed 3/15/23 | 2023-06-20
545 | 1277 | 9 | 1277 Life Sciences Building | 100% |  | Wed 2/1/23 |  | Wed 3/15/23
546 | 1277 | 9 | Order Equipment | 100% | 100% | Wed 2/1/23 | 2023-06-24 | Wed 2/1/23 | 2023-06-24
547 | 1277 | 9 | Site Receipt | 100% | 100% | Wed 3/15/23 | 2023-07-06 | Wed 3/15/23 | 2023-07-06
548 | 1259 | 9 | 1259 Biosystems Research Complex (BRC) | 100% |  | Wed 2/1/23 |  | Wed 3/15/23
549 | 1259 | 9 | Order Equipment | 100% |  | Wed 2/1/23 |  | Wed 2/1/23
550 | 1259 | 9 | Site Receipt | 100% |  | Wed 3/15/23 |  | Wed 3/15/23
551 | 1264 | 9 | 1264 Advanced Materials Research Lab | 0% |  | Fri 7/28/23 |  | Tue 8/29/23
552 | 1264 | 9 | Order Equipment | 0% | 100% | Fri 7/28/23 | 2023-05-04 | Fri 7/28/23 | 2023-05-04
553 | 1264 | 9 | Site Receipt | 0% | 100% | Tue 8/29/23 | 2023-05-17 | Tue 8/29/23 | 2023-05-17
554 | 272 | 9 | 272 Jordan Hall | 0% |  | Fri 7/28/23 |  | Tue 8/29/23
555 | 272 | 9 | Order Equipment | 0% |  | Fri 7/28/23 |  | Fri 7/28/23
556 | 272 | 9 | Site Receipt | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
557 | 388 | 9 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Tue 6/27/23 |  | Thu 8/3/23
558 | 388 | 9 | Order Equipment | 0% |  | Tue 6/27/23 |  | Tue 6/27/23
559 | 388 | 9 | Site Receipt | 0% |  | Thu 8/3/23 |  | Thu 8/3/23
560 |  | 9.1 | FIM 9.1 Heat Coil Recovery Material | 0% |  | Mon 8/21/23 |  | Wed 9/27/23
561 | 388 | 9.1 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Mon 8/21/23 |  | Wed 9/27/23
562 | 388 | 9.1 | Order Equipment | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
563 | 388 | 9.1 | Site Receipt | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
564 | 1264 | 9.1 | 1264 Advanced Materials Research Lab | 0% |  | Mon 8/21/23 |  | Wed 9/27/23
565 | 1264 | 9.1 | Order Equipment | 0% | 100% | Mon 8/21/23 | 2023-09-20 | Mon 8/21/23 | 2023-09-20
566 | 1264 | 9.1 | Site Receipt | 0% | 100% | Wed 9/27/23 | 2023-10-02 | Wed 9/27/23 | 2023-10-02
567 |  | 10 | FIM 10.0 HVAC Upgrades Material | 0% |  | Mon 6/19/23 |  | Thu 1/25/24
568 | 38 | 10 | 38 Mcadams Hall | 0% |  | Mon 9/11/23 |  | Fri 10/20/23
569 | 38 | 10 | Order Equipment | 0% | 100% | Mon 9/11/23 | 2023-07-16 | Mon 9/11/23 | 2023-07-16
570 | 38 | 10 | Site Receipt | 0% | 100% | Fri 10/20/23 | 2023-07-28 | Fri 10/20/23 | 2023-07-28
571 | 367 | 10 | 367 Hunter Hall | 0% |  | Tue 8/15/23 |  | Tue 9/19/23
572 | 367 | 10 | Order Equipment | 0% | 100% | Tue 8/15/23 | 2023-09-09 | Tue 8/15/23 | 2023-09-09
573 | 367 | 10 | Site Receipt | 0% | 100% | Tue 9/19/23 | 2023-09-21 | Tue 9/19/23 | 2023-09-21
574 | 388 | 10 | 388 Fluor Daniel (Engineering Innovation Center) EIB | 0% |  | Mon 6/19/23 |  | Thu 7/27/23
575 | 388 | 10 | Order Equipment | 0% | 100% | Mon 6/19/23 | 2023-06-18 | Mon 6/19/23 | 2023-06-18
576 | 388 | 10 | Site Receipt | 0% | 100% | Thu 7/27/23 | 2023-06-30 | Thu 7/27/23 | 2023-06-30
577 | 1059 | 10 | 1059 Ravenel Research Center | 0% |  | Tue 6/20/23 |  | Fri 7/28/23
578 | 1059 | 10 | Order Equipment | 0% | 100% | Tue 6/20/23 | 2023-05-26 | Tue 6/20/23 | 2023-05-26
579 | 1059 | 10 | Site Receipt | 0% | 100% | Fri 7/28/23 | 2023-06-09 | Fri 7/28/23 | 2023-06-09
580 | 1168 | 10 | 1168 Lebanon Road, 502 | 0% |  | Tue 6/20/23 |  | Thu 1/25/24
581 | 1168 | 10 | Order Equipment | 0% | 100% | Tue 6/20/23 | 2023-05-07 | Tue 6/20/23 | 2023-05-07
582 | 1168 | 10 | Site Receipt | 0% | 100% | Thu 1/25/24 | 2023-05-19 | Thu 1/25/24 | 2023-05-19
583 | 1178 | 10 | 1178 Westinghouse Road, 509 | 0% |  | Thu 10/19/23 |  | Thu 11/30/23
584 | 1178 | 10 | Order Equipment | 0% | 100% | Thu 10/19/23 | 2023-09-09 | Thu 10/19/23 | 2023-09-09
585 | 1178 | 10 | Site Receipt | 0% | 100% | Thu 11/30/23 | 2023-09-21 | Thu 11/30/23 | 2023-09-21
586 |  | 11 | FIM 11.0 Chiller Plant Material | 0% |  | Sat 4/8/23 |  | Thu 3/7/24
587 | 1059 | 11 | 1059 Ravenel Research Center | 0% |  | Tue 6/20/23 |  | Thu 3/7/24
588 | 1059 | 11 | Order Equipment | 0% |  | Tue 6/20/23 |  | Tue 6/20/23
589 | 1059 | 11 | Site Receipt | 0% |  | Thu 3/7/24 |  | Thu 3/7/24
590 | 1264 | 11 | 1264 Advanced Materials Research Lab | 0% |  | Sat 4/8/23 |  | Fri 10/13/23
591 | 1264 | 11 | Order Equipment | 100% |  | Sat 4/8/23 |  | Sat 4/8/23
592 | 1264 | 11 | Site Receipt | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
593 |  | 12 | FIM 12.0 Heating Plant Material | 0% |  | Sat 4/8/23 |  | Wed 8/30/23
594 | 1059 | 12 | 1059 Ravenel Research Center | 0% |  | Tue 6/20/23 |  | Wed 8/30/23
595 | 1059 | 12 | Order Equipment | 0% |  | Tue 6/20/23 |  | Tue 6/20/23
596 | 1059 | 12 | Site Receipt | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
597 | 1264 | 12 | 1264 Advanced Materials Research Lab | 0% |  | Sat 4/8/23 |  | Fri 6/30/23
598 | 1264 | 12 | Order Equipment | 100% |  | Sat 4/8/23 |  | Sat 4/8/23
599 | 1264 | 12 | Site Receipt | 0% |  | Fri 6/30/23 |  | Fri 6/30/23
600 |  |  | Installation | 51% |  | Wed 1/4/23 |  | Mon 11/11/24
601 | KIM |  | Key Interface Milestones - FIM Release | 0% |  | Wed 1/4/23 |  | Mon 6/3/24
602 | KIM | 1.1 | FIM 1.1 Interior Lighting & Controls Release | 100% |  | Wed 1/4/23 |  | Wed 1/4/23
603 | KIM | 1.2 | FIM 1.2 Exterior Lighting & Controls Release | 100% |  | Mon 4/17/23 |  | Mon 4/17/23
604 | KIM | 2.1 | FIM 2.1 Water Conservation Release | 0% | 100% | Fri 9/1/23 | 2023-08-01 | Fri 9/1/23 | 2023-08-01
605 | KIM | 3.1 | FIM 3.1 Steam Trap Replacement Release | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
606 | KIM | 3.2 | FIM 3.2 Mechanical Insulation Release | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
607 | KIM | 3.3 | FIM 3.3 Condensate Receiver Repair Release | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
608 | KIM | 4.1 | FIM 4.1 Seal HVAC Ductwork Release | 100% |  | Sun 3/19/23 |  | Sun 3/19/23
609 | KIM | 5.1 | FIM 5.1 Retro Cx Release | 0% | 100% | Tue 12/12/23 | 2023-04-19 | Tue 12/12/23 | 2023-04-19
610 | KIM | 6.1 | FIM 6.1 Building Envelope Release | 0% | 100% | Mon 7/17/23 | 2023-06-26 | Mon 7/17/23 | 2023-06-26
611 | KIM | 8 | FIM 8.0 Control Improvements Release | 100% |  | Mon 4/17/23 |  | Mon 4/17/23
612 | KIM | 8.1 | FIM 8.1 Kitchen Hood Controls or Upgrade Release | 0% |  | Mon 4/1/24 |  | Mon 4/1/24
613 | KIM | 8.2 | FIM 8.2 Control Optimization - MDMP / MRR Release | 0% |  | Mon 6/3/24 |  | Mon 6/3/24
614 | KIM | 9 | FIM 9.0 Lab Controls Release | 0% | 100% | Mon 7/17/23 | 2023-06-12 | Mon 7/17/23 | 2023-06-12
615 | KIM | 9.1 | FIM 9.1 Heat Recovery Coils Release | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
616 | KIM | 10 | FIM 10.0 HVAC Upgrades Release | 0% |  | Tue 6/20/23 |  | Tue 6/20/23
617 | KIM | 11 | FIM 11.0 Chiller Plant Improvements Release | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
618 | KIM | 12 | FIM 12.0 Heating Plant Improvements Release | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
619 | 1258 |  | Building 1258 ARTS Hugo Drive 202 Installation | 97% |  | Wed 2/8/23 |  | Fri 9/8/23
620 | 1258 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Fri 8/25/23 |  | Fri 9/8/23
621 | 1258 | 6.1 | Building 1258 Building Envelope Installation | 99% |  | Fri 8/25/23 |  | Sat 9/2/23
622 | 1258 | 6.1 | Building 1258 Building Envelope Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
623 | 1258 | 8 | FIM 8.0 Controls Improvement | 95% |  | Mon 4/17/23 |  | Fri 8/11/23
624 | 1258 | 8 | Building 1258 Controls Improvement Installation | 95% | 100% | Mon 4/17/23 | 2023-04-17 | Fri 8/4/23 | 2023-10-06
625 | 1258 | 8 | Building 1258 Controls Improvement Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
626 | 1258 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Wed 2/8/23 |  | Fri 4/21/23
627 | 1258 | 1.1 | Building 1258 Interior Lighting and Controls Installation | 100% |  | Wed 2/8/23 |  | Mon 3/13/23
628 | 1258 | 1.1 | Building 1258 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
629 | 1258 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Fri 2/17/23 |  | Tue 6/13/23
630 | 1258 | 1.2 | Building 1258 Exterior Lighting and Controls Installation | 100% |  | Fri 2/17/23 |  | Tue 6/6/23
631 | 1258 | 1.2 | Building 1258 Exterior Lighting and Controls Acceptance | 0% |  | Tue 6/13/23 |  | Tue 6/13/23
632 | 34 |  | Building 34 Campbell Museum Installation | 66% |  | Thu 3/2/23 |  | Fri 6/14/24
633 | 34 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Fri 8/11/23 |  | Wed 8/16/23
634 | 34 | 6.1 | Building 34 Building Envelope Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
635 | 34 | 6.1 | Building 34 Building Envelope Acceptance | 0% |  | Wed 8/16/23 |  | Wed 8/16/23
636 | 34 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Thu 3/2/23 |  | Fri 4/21/23
637 | 34 | 1.1 | Building 34 Interior Lighting and Controls Installation | 100% |  | Thu 3/2/23 |  | Mon 3/13/23
638 | 34 | 1.1 | Building 34 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
639 | 34 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 4/18/23 |  | Tue 4/25/23
640 | 34 | 1.2 | Building 34 Exterior Lighting and Controls Installation | 100% |  | Tue 4/18/23 |  | Tue 4/18/23
641 | 34 | 1.2 | Building 34 Exterior Lighting and Controls Acceptance | 0% |  | Tue 4/25/23 |  | Tue 4/25/23
642 | 34 | 8.2 | FIM 8.2 Control Optimization - MDMP/MRR | 0% |  | Mon 6/3/24 |  | Fri 6/14/24
643 | 34 | 8.2 | Building 34 Control Optimization - MDMP/MRR Installation | 0% |  | Mon 6/3/24 |  | Fri 6/7/24
644 | 34 | 8.2 | Building 34 Control Optimization - MDMP/MRR Acceptance | 0% |  | Fri 6/14/24 |  | Fri 6/14/24
645 | 27 |  | Building 27 Olin Hall Installation | 87% |  | Thu 3/2/23 |  | Tue 9/12/23
646 | 27 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Tue 9/5/23 |  | Mon 9/11/23
647 | 27 | 6.1 | Building 27 Building Envelope Installation | 99% |  | Tue 9/5/23 |  | Tue 9/5/23
648 | 27 | 6.1 | Building 27 Building Envelope Acceptance | 0% |  | Mon 9/11/23 |  | Mon 9/11/23
649 | 27 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Thu 3/2/23 |  | Fri 4/21/23
650 | 27 | 1.1 | Building 27 Interior Lighting and Controls Installation | 100% |  | Thu 3/2/23 |  | Mon 3/13/23
651 | 27 | 1.1 | Building 27 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
652 | 27 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 5/2/23 |  | Mon 6/19/23
653 | 27 | 1.2 | Building 27 Exterior Lighting and Controls Installation | 100% |  | Tue 5/2/23 |  | Mon 6/12/23
654 | 27 | 1.2 | Building 27 Exterior Lighting and Controls Acceptance | 0% |  | Mon 6/19/23 |  | Mon 6/19/23
655 | 27 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
656 | 27 | 2.1 | Building 27 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
657 | 27 | 2.1 | Building 27 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
658 | 27 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 9/1/23 |  | Tue 9/12/23
659 | 27 | 3.2 | Building 27 Mechanical Insulation Installation | 0% |  | Fri 9/1/23 |  | Wed 9/6/23
660 | 27 | 3.2 | Building 27 Mechanical Insulation Acceptance | 0% |  | Tue 9/12/23 |  | Tue 9/12/23
661 | 27 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 9/1/23 |  | Mon 9/11/23
662 | 27 | 3.1 | Building 27 Steam Trap Replacement Installation | 0% |  | Fri 9/1/23 |  | Tue 9/5/23
663 | 27 | 3.1 | Building 27 Steam Trap Replacement Acceptance | 0% |  | Mon 9/11/23 |  | Mon 9/11/23
664 | 27 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Wed 4/5/23 |  | Tue 4/25/23
665 | 27 | 4.1 | Building 27 Seal HVAC Ductwork Installation | 95% |  | Wed 4/5/23 |  | Tue 4/18/23
666 | 27 | 4.1 | Building 27 Seal HVAC Ductwork Acceptance | 0% |  | Tue 4/25/23 |  | Tue 4/25/23
667 | 5 |  | Building 5 Mell Hall Installation | 98% |  | Wed 3/8/23 |  | Thu 9/14/23
668 | 5 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 7/5/23 |  | Wed 7/12/23
669 | 5 | 6.1 | Building 5 Building Envelope Installation | 95% |  | Wed 7/5/23 |  | Wed 7/5/23
670 | 5 | 6.1 | Building 5 Building Envelope Acceptance | 0% |  | Wed 7/12/23 |  | Wed 7/12/23
671 | 5 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 3/8/23 |  | Tue 7/25/23
672 | 5 | 1.1 | Building 5 Interior Lighting and Controls Installation | 100% |  | Wed 3/8/23 |  | Tue 7/18/23
673 | 5 | 1.1 | Building 5 Interior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
674 | 5 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 4/17/23 |  | Tue 7/25/23
675 | 5 | 1.2 | Building 5 Exterior Lighting and Controls Installation | 100% |  | Mon 4/17/23 |  | Tue 7/18/23
676 | 5 | 1.2 | Building 5 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
677 | 5 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/1/23 |  | Tue 8/8/23
678 | 5 | 2.1 | Building 5 Water Conservation Installation | 95% |  | Tue 8/1/23 |  | Tue 8/1/23
679 | 5 | 2.1 | Building 5 Water Conservation Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
680 | 5 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 9/7/23 |  | Wed 9/13/23
681 | 5 | 3.2 | Building 5 Mechanical Insulation Installation | 0% |  | Thu 9/7/23 |  | Thu 9/7/23
682 | 5 | 3.2 | Building 5 Mechanical Insulation Acceptance | 0% |  | Wed 9/13/23 |  | Wed 9/13/23
683 | 5 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 9/6/23 |  | Thu 9/14/23
684 | 5 | 3.1 | Building 5 Steam Trap Replacement Installation | 0% |  | Wed 9/6/23 |  | Fri 9/8/23
685 | 5 | 3.1 | Building 5 Steam Trap Replacement Acceptance | 0% |  | Thu 9/14/23 |  | Thu 9/14/23
686 | 46 |  | Building 46 Trustee House Installation | 99% |  | Thu 3/16/23 |  | Mon 8/21/23
687 | 46 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Fri 8/11/23 |  | Wed 8/16/23
688 | 46 | 6.1 | Building 46 Building Envelope Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
689 | 46 | 6.1 | Building 46 Building Envelope Acceptance | 0% |  | Wed 8/16/23 |  | Wed 8/16/23
690 | 46 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Thu 3/16/23 |  | Thu 3/23/23
691 | 46 | 1.1 | Building 46 Interior Lighting and Controls Installation | 100% |  | Thu 3/16/23 |  | Thu 3/16/23
692 | 46 | 1.1 | Building 46 Interior Lighting and Controls Acceptance | 0% |  | Thu 3/23/23 |  | Thu 3/23/23
693 | 46 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 4/17/23 |  | Mon 6/19/23
694 | 46 | 1.2 | Building 46 Exterior Lighting and Controls Installation | 100% |  | Mon 4/17/23 |  | Mon 6/12/23
695 | 46 | 1.2 | Building 46 Exterior Lighting and Controls Acceptance | 0% |  | Mon 6/19/23 |  | Mon 6/19/23
696 | 46 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
697 | 46 | 2.1 | Building 46 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
698 | 46 | 2.1 | Building 46 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
699 | 216 |  | Building 216 Cook Lab Installation | 88% |  | Mon 3/20/23 |  | Thu 10/19/23
700 | 216 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Wed 10/11/23 |  | Thu 10/19/23
701 | 216 | 6.1 | Building 216 Building Envelope Installation | 0% | 99% | Wed 10/11/23 | 2023-10-13 | Thu 10/12/23 | 2023-10-13
702 | 216 | 6.1 | Building 216 Building Envelope Acceptance | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
703 | 216 | 8 | FIM 8.0 Controls Improvement | 95% |  | Mon 5/22/23 |  | Tue 8/29/23
704 | 216 | 8 | Building 216 Controls Improvement Installation | 95% |  | Mon 5/22/23 |  | Thu 8/24/23
705 | 216 | 8 | Building 216 Controls Improvement Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
706 | 216 | 1.1 | FIM 1.1 Interior Lighting and Controls | 95% |  | Mon 3/20/23 |  | Sat 3/25/23
707 | 216 | 1.1 | Building 216 Interior Lighting and Controls Installation | 95% |  | Mon 3/20/23 |  | Mon 3/20/23
708 | 216 | 1.1 | Building 216 Interior Lighting and Controls Acceptance | 0% |  | Sat 3/25/23 |  | Sat 3/25/23
709 | 216 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Sun 8/20/23 |  | Fri 8/25/23
710 | 216 | 2.1 | Building 216 Water Conservation Installation | 95% |  | Sun 8/20/23 |  | Sun 8/20/23
711 | 216 | 2.1 | Building 216 Water Conservation Acceptance | 0% |  | Fri 8/25/23 |  | Fri 8/25/23
712 | 216 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 9/8/23 |  | Thu 9/14/23
713 | 216 | 3.2 | Building 216 Mechanical Insulation Installation | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
714 | 216 | 3.2 | Building 216 Mechanical Insulation Acceptance | 0% |  | Thu 9/14/23 |  | Thu 9/14/23
715 | 216 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Sun 9/10/23 |  | Tue 9/19/23
716 | 216 | 3.1 | Building 216 Steam Trap Replacement Installation | 0% |  | Sun 9/10/23 |  | Tue 9/12/23
717 | 216 | 3.1 | Building 216 Steam Trap Replacement Acceptance | 0% |  | Tue 9/19/23 |  | Tue 9/19/23
718 | 319 |  | Building 319 Daniel Annex Installation | 98% |  | Tue 6/27/23 |  | Thu 10/19/23
719 | 319 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 10/12/23 |  | Thu 10/19/23
720 | 319 | 6.1 | Building 319 Building Envelope Installation | 0% | 99% | Thu 10/12/23 | 2023-10-16 | Thu 10/12/23 | 2023-10-16
721 | 319 | 6.1 | Building 319 Building Envelope Acceptance | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
722 | 319 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Tue 6/27/23 |  | Fri 7/28/23
723 | 319 | 1.1 | Building 319 Interior Lighting and Controls Installation | 100% |  | Tue 6/27/23 |  | Fri 7/21/23
724 | 319 | 1.1 | Building 319 Interior Lighting and Controls Acceptance | 0% |  | Fri 7/28/23 |  | Fri 7/28/23
725 | 319 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 6/27/23 |  | Fri 7/28/23
726 | 319 | 1.2 | Building 319 Exterior Lighting and Controls Installation | 100% |  | Tue 6/27/23 |  | Fri 7/21/23
727 | 319 | 1.2 | Building 319 Exterior Lighting and Controls Acceptance | 0% |  | Fri 7/28/23 |  | Fri 7/28/23
728 | 319 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
729 | 319 | 2.1 | Building 319 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
730 | 319 | 2.1 | Building 319 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
731 | 221 |  | Building 221 Strode Tower Installation | 97% |  | Mon 3/20/23 |  | Fri 9/22/23
732 | 221 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/14/23 |  | Wed 8/23/23
733 | 221 | 6.1 | Building 221 Building Envelope Installation | 95% |  | Mon 8/14/23 |  | Fri 8/18/23
734 | 221 | 6.1 | Building 221 Building Envelope Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
735 | 221 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 3/22/23 |  | Thu 8/3/23
736 | 221 | 1.1 | Building 221 Interior Lighting and Controls Installation | 100% |  | Wed 3/22/23 |  | Fri 7/28/23
737 | 221 | 1.1 | Building 221 Interior Lighting and Controls Acceptance | 0% |  | Thu 8/3/23 |  | Thu 8/3/23
738 | 221 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 3/22/23 |  | Thu 8/3/23
739 | 221 | 1.2 | Building 221 Exterior Lighting and Controls Installation | 100% |  | Wed 3/22/23 |  | Fri 7/28/23
740 | 221 | 1.2 | Building 221 Exterior Lighting and Controls Acceptance | 0% |  | Thu 8/3/23 |  | Thu 8/3/23
741 | 221 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
742 | 221 | 2.1 | Building 221 Water Conservation Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
743 | 221 | 2.1 | Building 221 Water Conservation Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
744 | 221 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 9/13/23 |  | Fri 9/22/23
745 | 221 | 3.1 | Building 221 Steam Trap Replacement Installation | 0% |  | Wed 9/13/23 |  | Fri 9/15/23
746 | 221 | 3.1 | Building 221 Steam Trap Replacement Acceptance | 0% |  | Fri 9/22/23 |  | Fri 9/22/23
747 | 221 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 3/20/23 |  | Wed 6/28/23
748 | 221 | 4.1 | Building 221 Seal HVAC Ductwork Installation | 95% |  | Mon 3/20/23 |  | Wed 6/21/23
749 | 221 | 4.1 | Building 221 Seal HVAC Ductwork Acceptance | 0% |  | Wed 6/28/23 |  | Wed 6/28/23
750 | 1241 |  | Building 1241 Wind Engineering Structures Lab Installation | 98% |  | Tue 2/7/23 |  | Tue 8/29/23
751 | 1241 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/24/23 |  | Tue 8/29/23
752 | 1241 | 6.1 | Building 1241 Building Envelope Installation | 0% |  | Thu 8/24/23 |  | Thu 8/24/23
753 | 1241 | 6.1 | Building 1241 Building Envelope Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
754 | 1241 | 8 | FIM 8.0 Controls Improvement | 95% |  | Wed 8/2/23 |  | Fri 8/11/23
755 | 1241 | 8 | Building 1241 Controls Improvement Installation | 95% | 99% | Wed 8/2/23 | 2023-08-02 | Fri 8/4/23 | 2023-10-06
756 | 1241 | 8 | Building 1241 Controls Improvement Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
757 | 1241 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Tue 2/7/23 |  | Fri 4/21/23
758 | 1241 | 1.1 | Building 1241 Interior Lighting and Controls Installation | 100% |  | Tue 2/7/23 |  | Mon 3/13/23
759 | 1241 | 1.1 | Building 1241 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
760 | 1241 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Thu 5/18/23 |  | Tue 6/13/23
761 | 1241 | 1.2 | Building 1241 Exterior Lighting and Controls Installation | 100% |  | Thu 5/18/23 |  | Tue 6/6/23
762 | 1241 | 1.2 | Building 1241 Exterior Lighting and Controls Acceptance | 0% |  | Tue 6/13/23 |  | Tue 6/13/23
763 | 1241 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/23/23 |  | Mon 8/28/23
764 | 1241 | 2.1 | Building 1241 Water Conservation Installation | 95% |  | Wed 8/23/23 |  | Wed 8/23/23
765 | 1241 | 2.1 | Building 1241 Water Conservation Acceptance | 0% |  | Mon 8/28/23 |  | Mon 8/28/23
766 | 409 |  | Building 409 Wind Test Load Facility Installation | 98% |  | Tue 2/7/23 |  | Sun 8/27/23
767 | 409 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
768 | 409 | 6.1 | Building 409 Building Envelope Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
769 | 409 | 6.1 | Building 409 Building Envelope Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
770 | 409 | 8 | FIM 8.0 Controls Improvement | 95% |  | Wed 8/2/23 |  | Sun 8/27/23
771 | 409 | 8 | Building 409 Controls Improvement Installation | 95% | 99% | Wed 8/2/23 | 2023-08-02 | Tue 8/22/23 | 2023-10-06
772 | 409 | 8 | Building 409 Controls Improvement Acceptance | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
773 | 409 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Tue 2/7/23 |  | Fri 4/21/23
774 | 409 | 1.1 | Building 409 Interior Lighting and Controls Installation | 100% |  | Tue 2/7/23 |  | Mon 3/13/23
775 | 409 | 1.1 | Building 409 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
776 | 409 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Thu 5/18/23 |  | Tue 6/13/23
777 | 409 | 1.2 | Building 409 Exterior Lighting and Controls Installation | 100% |  | Thu 5/18/23 |  | Tue 6/6/23
778 | 409 | 1.2 | Building 409 Exterior Lighting and Controls Acceptance | 0% |  | Tue 6/13/23 |  | Tue 6/13/23
779 | 409 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
780 | 409 | 2.1 | Building 409 Water Conservation Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
781 | 409 | 2.1 | Building 409 Water Conservation Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
782 | 420 |  | Building 420 Gas Turbine Lab #2 Installation | 95% |  | Mon 2/6/23 |  | Wed 9/20/23
783 | 420 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 8/28/23 |  | Tue 9/5/23
784 | 420 | 6.1 | Building 420 Building Envelope Installation | 0% |  | Mon 8/28/23 |  | Tue 8/29/23
785 | 420 | 6.1 | Building 420 Building Envelope Acceptance | 0% |  | Tue 9/5/23 |  | Tue 9/5/23
786 | 420 | 8 | FIM 8.0 Controls Improvement | 99% |  | Fri 8/4/23 |  | Wed 9/20/23
787 | 420 | 8 | Building 420 Controls Improvement Installation | 99% | 99% | Fri 8/4/23 | 2023-08-02 | Wed 9/13/23 | 2023-10-06
788 | 420 | 8 | Building 420 Controls Improvement Acceptance | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
789 | 420 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Mon 2/6/23 |  | Fri 4/21/23
790 | 420 | 1.1 | Building 420 Interior Lighting and Controls Installation | 100% |  | Mon 2/6/23 |  | Mon 3/13/23
791 | 420 | 1.1 | Building 420 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
792 | 420 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Wed 6/7/23 |  | Wed 6/14/23
793 | 420 | 1.2 | Building 420 Exterior Lighting and Controls Installation | 0% |  | Wed 6/7/23 |  | Wed 6/7/23
794 | 420 | 1.2 | Building 420 Exterior Lighting and Controls Acceptance | 0% |  | Wed 6/14/23 |  | Wed 6/14/23
795 | 420 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/23/23 |  | Mon 8/28/23
796 | 420 | 2.1 | Building 420 Water Conservation Installation | 95% |  | Wed 8/23/23 |  | Wed 8/23/23
797 | 420 | 2.1 | Building 420 Water Conservation Acceptance | 0% |  | Mon 8/28/23 |  | Mon 8/28/23
798 | 1142 |  | Building 1142 Strom Thurmond Institute Installation | 11% |  | Sat 3/25/23 |  | Fri 6/21/24
799 | 1142 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Tue 8/22/23 |  | Sun 8/27/23
800 | 1142 | 6.1 | Building 1142 Building Envelope Installation | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
801 | 1142 | 6.1 | Building 1142 Building Envelope Acceptance | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
802 | 1142 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Sat 3/25/23 |  | Fri 3/31/23
803 | 1142 | 1.1 | Building 1142 Interior Lighting and Controls Installation | 100% |  | Sat 3/25/23 |  | Sat 3/25/23
804 | 1142 | 1.1 | Building 1142 Interior Lighting and Controls Acceptance | 0% |  | Fri 3/31/23 |  | Fri 3/31/23
805 | 1142 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 6/8/23 |  | Thu 6/15/23
806 | 1142 | 1.2 | Building 1142 Exterior Lighting and Controls Installation | 0% |  | Thu 6/8/23 |  | Thu 6/8/23
807 | 1142 | 1.2 | Building 1142 Exterior Lighting and Controls Acceptance | 0% |  | Thu 6/15/23 |  | Thu 6/15/23
808 | 1142 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 6/10/24 |  | Fri 6/21/24
809 | 1142 | 8.2 | Building 1142 Control Optimization MDMP/MRR Installation | 0% |  | Mon 6/10/24 |  | Fri 6/14/24
810 | 1142 | 8.2 | Building 1142 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 6/21/24 |  | Fri 6/21/24
811 | 1142 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/17/23 |  | Tue 8/22/23
812 | 1142 | 2.1 | Building 1142 Water Conservation Installation | 95% |  | Thu 8/17/23 |  | Thu 8/17/23
813 | 1142 | 2.1 | Building 1142 Water Conservation Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
814 | 1142 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Sun 9/10/23 |  | Fri 9/15/23
815 | 1142 | 3.2 | Building 1142 Mechanical Insulation Installation | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
816 | 1142 | 3.2 | Building 1142 Mechanical Insulation Acceptance | 0% |  | Fri 9/15/23 |  | Fri 9/15/23
817 | 1142 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 9/18/23 |  | Wed 9/27/23
818 | 1142 | 3.1 | Building 1142 Steam Trap Replacement Installation | 0% |  | Mon 9/18/23 |  | Wed 9/20/23
819 | 1142 | 3.1 | Building 1142 Steam Trap Replacement Acceptance | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
820 | 1142 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Mon 10/2/23 |  | Thu 10/12/23
821 | 1142 | 4.1 | Building 1142 Seal HVAC Ductwork Installation | 0% | 99% | Mon 10/2/23 | 2023-10-02 | Thu 10/5/23 | 2023-10-05
822 | 1142 | 4.1 | Building 1142 Seal HVAC Ductwork Acceptance | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
823 | 30 |  | Building 30 Brackett Hall Installation | 89% |  | Wed 4/12/23 |  | Wed 11/15/23
824 | 30 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Wed 11/1/23 |  | Wed 11/15/23
825 | 30 | 6.1 | Building 30 Building Envelope Installation | 0% | 99% | Wed 11/1/23 | 2023-10-12 | Wed 11/8/23 | 2023-10-12
826 | 30 | 6.1 | Building 30 Building Envelope Acceptance | 0% |  | Wed 11/15/23 |  | Wed 11/15/23
827 | 30 | 8 | FIM 8.0 Controls Improvement | 99% |  | Mon 5/8/23 |  | Tue 5/23/23
828 | 30 | 8 | Building 30 Controls Improvement Installation | 100% |  | Mon 5/8/23 |  | Tue 5/16/23
829 | 30 | 8 | Building 30 Controls Improvement Acceptance | 0% |  | Tue 5/23/23 |  | Tue 5/23/23
830 | 30 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 4/12/23 |  | Mon 6/19/23
831 | 30 | 1.1 | Building 30 Interior Lighting and Controls Installation | 100% |  | Wed 4/12/23 |  | Mon 6/12/23
832 | 30 | 1.1 | Building 30 Interior Lighting and Controls Acceptance | 0% |  | Mon 6/19/23 |  | Mon 6/19/23
833 | 30 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 4/12/23 |  | Mon 6/19/23
834 | 30 | 1.2 | Building 30 Exterior Lighting and Controls Installation | 100% |  | Wed 4/12/23 |  | Mon 6/12/23
835 | 30 | 1.2 | Building 30 Exterior Lighting and Controls Acceptance | 0% |  | Mon 6/19/23 |  | Mon 6/19/23
836 | 30 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
837 | 30 | 2.1 | Building 30 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
838 | 30 | 2.1 | Building 30 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
839 | 30 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 9/11/23 |  | Mon 9/18/23
840 | 30 | 3.2 | Building 30 Mechanical Insulation Installation | 0% |  | Mon 9/11/23 |  | Mon 9/11/23
841 | 30 | 3.2 | Building 30 Mechanical Insulation Acceptance | 0% |  | Mon 9/18/23 |  | Mon 9/18/23
842 | 30 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 9/21/23 |  | Sun 10/1/23
843 | 30 | 3.1 | Building 30 Steam Trap Replacement Installation | 0% |  | Thu 9/21/23 |  | Mon 9/25/23
844 | 30 | 3.1 | Building 30 Steam Trap Replacement Acceptance | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
845 | 30 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 5/8/23 |  | Wed 5/24/23
846 | 30 | 4.1 | Building 30 Seal HVAC Ductwork Installation | 95% |  | Mon 5/8/23 |  | Wed 5/17/23
847 | 30 | 4.1 | Building 30 Seal HVAC Ductwork Acceptance | 0% |  | Wed 5/24/23 |  | Wed 5/24/23
848 | 30 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Fri 9/1/23 |  | Sun 9/10/23
849 | 30 | 3.3 | Building 30 Condensate Receiver Repair Installation | 0% |  | Fri 9/1/23 |  | Mon 9/4/23
850 | 30 | 3.3 | Building 30 Condensate Receiver Repair Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
851 | 367 |  | Building 367 Hunter Hall Installation | 42% |  | Thu 5/18/23 |  | Fri 3/29/24
852 | 367 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Wed 3/13/24 |  | Mon 3/25/24
853 | 367 | 6.1 | Building 367 Building Envelope Installation | 0% | 99% | Wed 3/13/24 | 2023-10-16 | Mon 3/18/24 | 2023-10-16
854 | 367 | 6.1 | Building 367 Building Envelope Acceptance | 0% |  | Mon 3/25/24 |  | Mon 3/25/24
855 | 367 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Fri 6/9/23 |  | Fri 6/16/23
856 | 367 | 1.1 | Building 367 Interior Lighting and Controls Installation | 100% | 100% | Fri 6/9/23 | 2023-06-12 | Fri 6/9/23 | 2023-10-17
857 | 367 | 1.1 | Building 367 Interior Lighting and Controls Acceptance | 0% |  | Fri 6/16/23 |  | Fri 6/16/23
858 | 367 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% | 100% | Fri 6/9/23 |  | Fri 6/16/23
859 | 367 | 1.2 | Building 367 Exterior Lighting and Controls Installation | 100% |  | Fri 6/9/23 | 2023-06-12 | Fri 6/9/23 | 2023-10-17
860 | 367 | 1.2 | Building 367 Exterior Lighting and Controls Acceptance | 0% |  | Fri 6/16/23 |  | Fri 6/16/23
861 | 367 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
862 | 367 | 2.1 | Building 367 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
863 | 367 | 2.1 | Building 367 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
864 | 367 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 9/12/23 |  | Tue 9/19/23
865 | 367 | 3.2 | Building 367 Mechanical Insulation Installation | 0% |  | Tue 9/12/23 |  | Tue 9/12/23
866 | 367 | 3.2 | Building 367 Mechanical Insulation Acceptance | 0% |  | Tue 9/19/23 |  | Tue 9/19/23
867 | 367 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 9/26/23 |  | Wed 10/4/23
868 | 367 | 3.1 | Building 367 Steam Trap Replacement Installation | 0% |  | Tue 9/26/23 |  | Thu 9/28/23
869 | 367 | 3.1 | Building 367 Steam Trap Replacement Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
870 | 367 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Thu 5/18/23 |  | Wed 7/26/23
871 | 367 | 4.1 | Building 367 Seal HVAC Ductwork Installation | 95% |  | Thu 5/18/23 |  | Wed 7/19/23
872 | 367 | 4.1 | Building 367 Seal HVAC Ductwork Acceptance | 0% |  | Wed 7/26/23 |  | Wed 7/26/23
873 | 367 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Mon 1/8/24 |  | Fri 3/29/24
874 | 367 | 10 | Building 367 HVAC Upgrades Installation | 0% |  | Mon 1/8/24 |  | Fri 3/22/24
875 | 367 | 10 | Building 367 HVAC Upgrades Acceptance | 0% |  | Fri 3/29/24 |  | Fri 3/29/24
876 | 25 |  | Building 25 Freeman Hall Installation | 51% |  | Mon 3/27/23 |  | Fri 6/28/24
877 | 25 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 8/9/23 |  | Mon 8/14/23
878 | 25 | 6.1 | Building 25 Building Envelope Installation | 95% |  | Wed 8/9/23 |  | Wed 8/9/23
879 | 25 | 6.1 | Building 25 Building Envelope Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
880 | 25 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Tue 4/4/23 |  | Tue 4/11/23
881 | 25 | 1.1 | Building 25 Interior Lighting and Controls Installation | 100% |  | Tue 4/4/23 |  | Tue 4/4/23
882 | 25 | 1.1 | Building 25 Interior Lighting and Controls Acceptance | 0% |  | Tue 4/11/23 |  | Tue 4/11/23
883 | 25 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 5/22/23 |  | Mon 5/29/23
884 | 25 | 1.2 | Building 25 Exterior Lighting and Controls Installation | 100% |  | Mon 5/22/23 |  | Mon 5/22/23
885 | 25 | 1.2 | Building 25 Exterior Lighting and Controls Acceptance | 0% |  | Mon 5/29/23 |  | Mon 5/29/23
886 | 25 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 6/17/24 |  | Fri 6/28/24
887 | 25 | 8.2 | Building 25 Control Optimization MDMP/MRR Installation | 0% |  | Mon 6/17/24 |  | Fri 6/21/24
888 | 25 | 8.2 | Building 25 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 6/28/24 |  | Fri 6/28/24
889 | 25 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 9/13/23 |  | Wed 9/20/23
890 | 25 | 3.2 | Building 25 Mechanical Insulation Installation | 0% |  | Wed 9/13/23 |  | Wed 9/13/23
891 | 25 | 3.2 | Building 25 Mechanical Insulation Acceptance | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
892 | 25 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 9/29/23 |  | Mon 10/9/23
893 | 25 | 3.1 | Building 25 Steam Trap Replacement Installation | 0% |  | Fri 9/29/23 |  | Mon 10/2/23
894 | 25 | 3.1 | Building 25 Steam Trap Replacement Acceptance | 0% |  | Mon 10/9/23 |  | Mon 10/9/23
895 | 25 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 3/27/23 |  | Mon 4/10/23
896 | 25 | 4.1 | Building 25 Seal HVAC Ductwork Installation | 95% |  | Mon 3/27/23 |  | Mon 4/3/23
897 | 25 | 4.1 | Building 25 Seal HVAC Ductwork Acceptance | 0% |  | Mon 4/10/23 |  | Mon 4/10/23
898 | 29 |  | Building 29 Hardin Hall Installation | 81% |  | Mon 5/8/23 |  | Mon 10/30/23
899 | 29 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 10/16/23 |  | Mon 10/30/23
900 | 29 | 6.1 | Building 29 Building Envelope Installation | 0% | 99% | Mon 10/16/23 | 2023-10-16 | Mon 10/23/23 | 2023-10-16
901 | 29 | 6.1 | Building 29 Building Envelope Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
902 | 29 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 5/8/23 |  | Fri 6/16/23
903 | 29 | 1.1 | Building 29 Interior Lighting and Controls Installation | 100% |  | Mon 5/8/23 |  | Fri 6/9/23
904 | 29 | 1.1 | Building 29 Interior Lighting and Controls Acceptance | 0% |  | Fri 6/16/23 |  | Fri 6/16/23
905 | 29 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 5/22/23 |  | Mon 6/19/23
906 | 29 | 1.2 | Building 29 Exterior Lighting and Controls Installation | 100% |  | Mon 5/22/23 |  | Mon 6/12/23
907 | 29 | 1.2 | Building 29 Exterior Lighting and Controls Acceptance | 0% |  | Mon 6/19/23 |  | Mon 6/19/23
908 | 29 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
909 | 29 | 2.1 | Building 29 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
910 | 29 | 2.1 | Building 29 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
911 | 29 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 9/14/23 |  | Thu 9/21/23
912 | 29 | 3.2 | Building 29 Mechanical Insulation Installation | 0% |  | Thu 9/14/23 |  | Thu 9/14/23
913 | 29 | 3.2 | Building 29 Mechanical Insulation Acceptance | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
914 | 29 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 10/3/23 |  | Thu 10/12/23
915 | 29 | 3.1 | Building 29 Steam Trap Replacement Installation | 0% |  | Tue 10/3/23 |  | Thu 10/5/23
916 | 29 | 3.1 | Building 29 Steam Trap Replacement Acceptance | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
917 | 29 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 99% |  | Wed 6/14/23 |  | Thu 6/22/23
918 | 29 | 4.1 | Building 29 Seal HVAC Ductwork Installation | 100% |  | Wed 6/14/23 |  | Thu 6/15/23
919 | 29 | 4.1 | Building 29 Seal HVAC Ductwork Acceptance | 0% |  | Thu 6/22/23 |  | Thu 6/22/23
920 | 26 |  | Building 26 Riggs Hall Installation | 82% |  | Mon 5/15/23 |  | Fri 7/5/24
921 | 26 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Tue 9/5/23 |  | Thu 9/21/23
922 | 26 | 6.1 | Building 26 Building Envelope Installation | 0% | 99% | Tue 9/5/23 | 2023-10-05 | Thu 9/14/23 | 2023-10-13
923 | 26 | 6.1 | Building 26 Building Envelope Acceptance | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
924 | 26 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 5/15/23 |  | Thu 7/27/23
925 | 26 | 1.1 | Building 26 Interior Lighting and Controls Installation | 100% |  | Mon 5/15/23 |  | Thu 7/20/23
926 | 26 | 1.1 | Building 26 Interior Lighting and Controls Acceptance | 0% |  | Thu 7/27/23 |  | Thu 7/27/23
927 | 26 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Fri 5/19/23 |  | Thu 7/27/23
928 | 26 | 1.2 | Building 26 Exterior Lighting and Controls Installation | 100% |  | Fri 5/19/23 |  | Thu 7/20/23
929 | 26 | 1.2 | Building 26 Exterior Lighting and Controls Acceptance | 0% |  | Thu 7/27/23 |  | Thu 7/27/23
930 | 26 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 6/24/24 |  | Fri 7/5/24
931 | 26 | 8.2 | Building 26 Control Optimization MDMP/MRR Installation | 0% |  | Mon 6/24/24 |  | Fri 6/28/24
932 | 26 | 8.2 | Building 26 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 7/5/24 |  | Fri 7/5/24
933 | 26 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
934 | 26 | 2.1 | Building 26 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
935 | 26 | 2.1 | Building 26 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
936 | 26 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 9/15/23 |  | Fri 9/22/23
937 | 26 | 3.2 | Building 26 Mechanical Insulation Installation | 0% |  | Fri 9/15/23 |  | Fri 9/15/23
938 | 26 | 3.2 | Building 26 Mechanical Insulation Acceptance | 0% |  | Fri 9/22/23 |  | Fri 9/22/23
939 | 26 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 10/6/23 |  | Tue 10/17/23
940 | 26 | 3.1 | Building 26 Steam Trap Replacement Installation | 0% |  | Fri 10/6/23 |  | Tue 10/10/23
941 | 26 | 3.1 | Building 26 Steam Trap Replacement Acceptance | 0% |  | Tue 10/17/23 |  | Tue 10/17/23
942 | 1 |  | Building 1 Tillman Hall Installation | 85% |  | Mon 4/24/23 |  | Fri 7/12/24
943 | 1 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Sun 7/30/23 |  | Mon 8/7/23
944 | 1 | 6.1 | Building 1 Building Envelope Installation | 95% |  | Sun 7/30/23 |  | Mon 7/31/23
945 | 1 | 6.1 | Building 1 Building Envelope Acceptance | 0% |  | Mon 8/7/23 |  | Mon 8/7/23
946 | 1 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 4/24/23 |  | Wed 6/21/23
947 | 1 | 1.1 | Building 1 Interior Lighting and Controls Installation | 100% |  | Mon 4/24/23 |  | Wed 6/14/23
948 | 1 | 1.1 | Building 1 Interior Lighting and Controls Acceptance | 0% |  | Wed 6/21/23 |  | Wed 6/21/23
949 | 1 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 5/16/23 |  | Wed 6/21/23
950 | 1 | 1.2 | Building 1 Exterior Lighting and Controls Installation | 100% |  | Tue 5/16/23 |  | Wed 6/14/23
951 | 1 | 1.2 | Building 1 Exterior Lighting and Controls Acceptance | 0% |  | Wed 6/21/23 |  | Wed 6/21/23
952 | 1 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 7/1/24 |  | Fri 7/12/24
953 | 1 | 8.2 | Building 1 Control Optimization MDMP/MRR Installation | 0% |  | Mon 7/1/24 |  | Fri 7/5/24
954 | 1 | 8.2 | Building 1 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 7/12/24 |  | Fri 7/12/24
955 | 1 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/11/23 |  | Mon 8/21/23
956 | 1 | 2.1 | Building 1 Water Conservation Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
957 | 1 | 2.1 | Building 1 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
958 | 1 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 9/18/23 |  | Mon 9/25/23
959 | 1 | 3.2 | Building 1 Mechanical Insulation Installation | 0% |  | Mon 9/18/23 |  | Mon 9/18/23
960 | 1 | 3.2 | Building 1 Mechanical Insulation Acceptance | 0% |  | Mon 9/25/23 |  | Mon 9/25/23
961 | 1 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 10/11/23 |  | Fri 10/20/23
962 | 1 | 3.1 | Building 1 Steam Trap Replacement Installation | 0% |  | Wed 10/11/23 |  | Fri 10/13/23
963 | 1 | 3.1 | Building 1 Steam Trap Replacement Acceptance | 0% |  | Fri 10/20/23 |  | Fri 10/20/23
964 | 1 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 7/10/23 |  | Wed 7/19/23
965 | 1 | 4.1 | Building 1 Seal HVAC Ductwork Installation | 95% |  | Mon 7/10/23 |  | Thu 7/13/23
966 | 1 | 4.1 | Building 1 Seal HVAC Ductwork Acceptance | 0% |  | Wed 7/19/23 |  | Wed 7/19/23
967 | 1 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Tue 9/5/23 |  | Tue 9/12/23
968 | 1 | 3.3 | Building 1 Condensate Receiver Repair Installation | 0% |  | Tue 9/5/23 |  | Wed 9/6/23
969 | 1 | 3.3 | Building 1 Condensate Receiver Repair Acceptance | 0% |  | Tue 9/12/23 |  | Tue 9/12/23
970 | 348 |  | Building 348 Fire Station Installation | 96% |  | Thu 2/9/23 |  | Tue 8/22/23
971 | 348 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/17/23 |  | Tue 8/22/23
972 | 348 | 6.1 | Building 348 Building Envelope Installation | 0% |  | Thu 8/17/23 |  | Thu 8/17/23
973 | 348 | 6.1 | Building 348 Building Envelope Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
974 | 348 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Thu 2/9/23 |  | Fri 4/21/23
975 | 348 | 1.1 | Building 348 Interior Lighting and Controls Installation | 100% |  | Thu 2/9/23 |  | Mon 3/13/23
976 | 348 | 1.1 | Building 348 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
977 | 348 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
978 | 348 | 2.1 | Building 348 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
979 | 348 | 2.1 | Building 348 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
980 | 112 |  | Building 112 Harris A Smith Installation | 85% |  | Wed 5/31/23 |  | Wed 10/25/23
981 | 112 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Thu 9/28/23 |  | Mon 10/9/23
982 | 112 | 6.1 | Building 112 Building Envelope Installation | 99% | 99% | Thu 9/28/23 | 2023-10-16 | Mon 10/2/23 | 2023-10-16
983 | 112 | 6.1 | Building 112 Building Envelope Acceptance | 0% |  | Mon 10/9/23 |  | Mon 10/9/23
984 | 112 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 5/31/23 |  | Wed 8/2/23
985 | 112 | 1.1 | Building 112 Interior Lighting and Controls Installation | 100% |  | Wed 5/31/23 |  | Thu 7/27/23
986 | 112 | 1.1 | Building 112 Interior Lighting and Controls Acceptance | 0% |  | Wed 8/2/23 |  | Wed 8/2/23
987 | 112 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 5/31/23 |  | Wed 8/2/23
988 | 112 | 1.2 | Building 112 Exterior Lighting and Controls Installation | 100% |  | Wed 5/31/23 |  | Thu 7/27/23
989 | 112 | 1.2 | Building 112 Exterior Lighting and Controls Acceptance | 0% |  | Wed 8/2/23 |  | Wed 8/2/23
990 | 112 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/18/23 |  | Wed 8/23/23
991 | 112 | 2.1 | Building 112 Water Conservation Installation | 95% |  | Fri 8/18/23 |  | Fri 8/18/23
992 | 112 | 2.1 | Building 112 Water Conservation Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
993 | 112 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 9/19/23 |  | Tue 9/26/23
994 | 112 | 3.2 | Building 112 Mechanical Insulation Installation | 0% |  | Tue 9/19/23 |  | Tue 9/19/23
995 | 112 | 3.2 | Building 112 Mechanical Insulation Acceptance | 0% |  | Tue 9/26/23 |  | Tue 9/26/23
996 | 112 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 10/16/23 |  | Wed 10/25/23
997 | 112 | 3.1 | Building 112 Steam Trap Replacement Installation | 0% |  | Mon 10/16/23 |  | Wed 10/18/23
998 | 112 | 3.1 | Building 112 Steam Trap Replacement Acceptance | 0% |  | Wed 10/25/23 |  | Wed 10/25/23
999 | 112 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Thu 7/20/23 |  | Thu 7/27/23
1000 | 112 | 4.1 | Building 112 Seal HVAC Ductwork Installation | 95% |  | Thu 7/20/23 |  | Thu 7/20/23
1001 | 112 | 4.1 | Building 112 Seal HVAC Ductwork Acceptance | 0% |  | Thu 7/27/23 |  | Thu 7/27/23
1002 | 112 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Mon 8/14/23 |  | Wed 8/30/23
1003 | 112 | 5.1 | Building 112 Retro Cx Installation | 0% |  | Mon 8/14/23 |  | Fri 8/25/23
1004 | 112 | 5.1 | Building 112 Retro Cx Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1005 | 4170 |  | Building 4170 Douthit Hills A Installation | 95% |  | Tue 6/27/23 |  | Wed 8/30/23
1006 | 4170 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Tue 6/27/23 |  | Mon 7/3/23
1007 | 4170 | 6.1 | Building 4170 Building Envelope Installation | 95% |  | Tue 6/27/23 |  | Tue 6/27/23
1008 | 4170 | 6.1 | Building 4170 Building Envelope Acceptance | 0% |  | Mon 7/3/23 |  | Mon 7/3/23
1009 | 4170 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1010 | 4170 | 2.1 | Building 4170 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1011 | 4170 | 2.1 | Building 4170 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1012 | 4171 |  | Building 4171 Douthit Hills B Installation | 95% |  | Tue 6/27/23 |  | Wed 8/30/23
1013 | 4171 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Tue 6/27/23 |  | Mon 7/3/23
1014 | 4171 | 6.1 | Building 4171 Building Envelope Installation | 95% |  | Tue 6/27/23 |  | Tue 6/27/23
1015 | 4171 | 6.1 | Building 4171 Building Envelope Acceptance | 0% |  | Mon 7/3/23 |  | Mon 7/3/23
1016 | 4171 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1017 | 4171 | 2.1 | Building 4171 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1018 | 4171 | 2.1 | Building 4171 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1019 | 4172 |  | Building 4172 Douthit Hills C Installation | 95% |  | Tue 6/27/23 |  | Wed 8/30/23
1020 | 4172 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Tue 6/27/23 |  | Mon 7/3/23
1021 | 4172 | 6.1 | Building 4172 Building Envelope Installation | 95% |  | Tue 6/27/23 |  | Tue 6/27/23
1022 | 4172 | 6.1 | Building 4172 Building Envelope Acceptance | 0% |  | Mon 7/3/23 |  | Mon 7/3/23
1023 | 4172 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1024 | 4172 | 2.1 | Building 4172 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1025 | 4172 | 2.1 | Building 4172 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1026 | 4173 |  | Building 4173 Douthit Hills D Installation | 95% |  | Wed 6/28/23 |  | Wed 8/30/23
1027 | 4173 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 6/28/23 |  | Tue 7/4/23
1028 | 4173 | 6.1 | Building 4173 Building Envelope Installation | 95% |  | Wed 6/28/23 |  | Wed 6/28/23
1029 | 4173 | 6.1 | Building 4173 Building Envelope Acceptance | 0% |  | Tue 7/4/23 |  | Tue 7/4/23
1030 | 4173 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1031 | 4173 | 2.1 | Building 4173 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1032 | 4173 | 2.1 | Building 4173 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1033 | 4175 |  | Building 4175 Douthit Hills E Installation | 98% |  | Mon 6/26/23 |  | Wed 8/30/23
1034 | 4175 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 6/26/23 |  | Sat 7/1/23
1035 | 4175 | 6.1 | Building 4175 Building Envelope Installation | 100% |  | Mon 6/26/23 |  | Mon 6/26/23
1036 | 4175 | 6.1 | Building 4175 Building Envelope Acceptance | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
1037 | 4175 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1038 | 4175 | 2.1 | Building 4175 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1039 | 4175 | 2.1 | Building 4175 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1040 | 4176 |  | Building 4176 Douthit Hills F Installation | 95% |  | Wed 6/28/23 |  | Wed 8/30/23
1041 | 4176 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 6/28/23 |  | Tue 7/4/23
1042 | 4176 | 6.1 | Building 4176 Building Envelope Installation | 95% |  | Wed 6/28/23 |  | Wed 6/28/23
1043 | 4176 | 6.1 | Building 4176 Building Envelope Acceptance | 0% |  | Tue 7/4/23 |  | Tue 7/4/23
1044 | 4176 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1045 | 4176 | 2.1 | Building 4176 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1046 | 4176 | 2.1 | Building 4176 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1047 | 4177 |  | Building 4177 Douthit Hills G Installation | 95% |  | Mon 6/26/23 |  | Wed 8/30/23
1048 | 4177 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 6/26/23 |  | Sat 7/1/23
1049 | 4177 | 6.1 | Building 4177 Building Envelope Installation | 95% |  | Mon 6/26/23 |  | Mon 6/26/23
1050 | 4177 | 6.1 | Building 4177 Building Envelope Acceptance | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
1051 | 4177 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1052 | 4177 | 2.1 | Building 4177 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1053 | 4177 | 2.1 | Building 4177 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1054 | 4174 |  | Building 4174 Douthit Hills HUB Installation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1055 | 4174 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1056 | 4174 | 2.1 | Building 4174 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1057 | 4174 | 2.1 | Building 4174 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1058 | 1278 |  | Building 1278 Academic Success Center Installation | 75% |  | Mon 6/5/23 |  | Mon 10/30/23
1059 | 1278 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 8/28/23 |  | Sun 9/10/23
1060 | 1278 | 6.1 | Building 1278 Building Envelope Installation | 99% |  | Mon 8/28/23 |  | Mon 9/4/23
1061 | 1278 | 6.1 | Building 1278 Building Envelope Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
1062 | 1278 | 1.1 | FIM 1.1 Interior Lighting and Controls | 95% |  | Mon 6/5/23 |  | Thu 6/15/23
1063 | 1278 | 1.1 | Building 1278 Interior Lighting and Controls Installation | 95% |  | Mon 6/5/23 |  | Thu 6/8/23
1064 | 1278 | 1.1 | Building 1278 Interior Lighting and Controls Acceptance | 0% |  | Thu 6/15/23 |  | Thu 6/15/23
1065 | 1278 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 95% |  | Mon 6/5/23 |  | Thu 6/15/23
1066 | 1278 | 1.2 | Building 1278 Exterior Lighting and Controls Installation | 95% |  | Mon 6/5/23 |  | Thu 6/8/23
1067 | 1278 | 1.2 | Building 1278 Exterior Lighting and Controls Acceptance | 0% |  | Thu 6/15/23 |  | Thu 6/15/23
1068 | 1278 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 9/20/23 |  | Wed 9/27/23
1069 | 1278 | 3.2 | Building 1278 Mechanical Insulation Installation | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
1070 | 1278 | 3.2 | Building 1278 Mechanical Insulation Acceptance | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
1071 | 1278 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 10/19/23 |  | Mon 10/30/23
1072 | 1278 | 3.1 | Building 1278 Steam Trap Replacement Installation | 0% |  | Thu 10/19/23 |  | Mon 10/23/23
1073 | 1278 | 3.1 | Building 1278 Steam Trap Replacement Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
1074 | 2551 |  | Building 2551 Lightsey Bridge Apartment Building 1 Installation | 95% |  | Thu 8/24/23 |  | Thu 7/18/24
1075 | 2551 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 6/26/24 |  | Thu 7/18/24
1076 | 2551 | 6.1 | Building 2551 Building Envelope Installation | 95% |  | Wed 6/26/24 |  | Thu 7/11/24
1077 | 2551 | 6.1 | Building 2551 Building Envelope Acceptance | 0% |  | Thu 7/18/24 |  | Thu 7/18/24
1078 | 2551 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1079 | 2551 | 2.1 | Building 2551 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1080 | 2551 | 2.1 | Building 2551 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1081 | 2560 |  | Building 2560 Lightsey Bridge Apartment Building 10 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1082 | 2560 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1083 | 2560 | 2.1 | Building 2560 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1084 | 2560 | 2.1 | Building 2560 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1085 | 2552 |  | Building 2552 Lightsey Bridge Apartment Building 2 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1086 | 2552 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1087 | 2552 | 2.1 | Building 2552 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1088 | 2552 | 2.1 | Building 2552 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1089 | 2553 |  | Building 2553 Lightsey Bridge Apartment Building 3 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1090 | 2553 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1091 | 2553 | 2.1 | Building 2553 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1092 | 2553 | 2.1 | Building 2553 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1093 | 2554 |  | Building 2554 Lightsey Bridge Apartment Building 4 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1094 | 2554 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1095 | 2554 | 2.1 | Building 2554 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1096 | 2554 | 2.1 | Building 2554 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1097 | 2555 |  | Building 2555 Lightsey Bridge Apartment Building 5 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1098 | 2555 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1099 | 2555 | 2.1 | Building 2555 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1100 | 2555 | 2.1 | Building 2555 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1101 | 2556 |  | Building 2556 Lightsey Bridge Apartment Building 6 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1102 | 2556 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1103 | 2556 | 2.1 | Building 2556 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1104 | 2556 | 2.1 | Building 2556 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1105 | 2557 |  | Building 2557 Lightsey Bridge Apartment Building 7 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1106 | 2557 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1107 | 2557 | 2.1 | Building 2557 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1108 | 2557 | 2.1 | Building 2557 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1109 | 2558 |  | Building 2558 Lightsey Bridge Apartment Building 8 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1110 | 2558 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1111 | 2558 | 2.1 | Building 2558 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1112 | 2558 | 2.1 | Building 2558 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1113 | 2559 |  | Building 2559 Lightsey Bridge Apartment Building 9 Installation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1114 | 2559 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1115 | 2559 | 2.1 | Building 2559 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1116 | 2559 | 2.1 | Building 2559 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1117 | 4 |  | Building 4 Holtzendorff Hall Installation | 94% |  | Wed 5/17/23 |  | Fri 7/19/24
1118 | 4 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Fri 8/25/23 |  | Thu 10/19/23
1119 | 4 | 6.1 | Building 4 Building Envelope Installation | 99% |  | Fri 8/25/23 |  | Thu 8/31/23
1120 | 4 | 6.1 | Building 4 Building Envelope Acceptance | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
1121 | 4 | 8 | FIM 8.0 Controls Improvement | 99% |  | Wed 5/17/23 |  | Mon 9/18/23
1122 | 4 | 8 | Building 4 Controls Improvement Installation | 100% |  | Wed 5/17/23 |  | Mon 9/11/23
1123 | 4 | 8 | Building 4 Controls Improvement Acceptance | 0% |  | Mon 9/18/23 |  | Mon 9/18/23
1124 | 4 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Thu 6/8/23 |  | Wed 6/28/23
1125 | 4 | 1.1 | Building 4 Interior Lighting and Controls Installation | 100% |  | Thu 6/8/23 |  | Wed 6/21/23
1126 | 4 | 1.1 | Building 4 Interior Lighting and Controls Acceptance | 0% |  | Wed 6/28/23 |  | Wed 6/28/23
1127 | 4 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 6/13/23 |  | Sat 7/1/23
1128 | 4 | 1.2 | Building 4 Exterior Lighting and Controls Installation | 100% |  | Tue 6/13/23 |  | Mon 6/26/23
1129 | 4 | 1.2 | Building 4 Exterior Lighting and Controls Acceptance | 0% |  | Sat 7/1/23 |  | Sat 7/1/23
1130 | 4 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 7/8/24 |  | Fri 7/19/24
1131 | 4 | 8.2 | Building 4 Control Optimization MDMP/MRR Installation | 0% |  | Mon 7/8/24 |  | Fri 7/12/24
1132 | 4 | 8.2 | Building 4 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 7/19/24 |  | Fri 7/19/24
1133 | 4 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/11/23 |  | Wed 8/16/23
1134 | 4 | 2.1 | Building 4 Water Conservation Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
1135 | 4 | 2.1 | Building 4 Water Conservation Acceptance | 0% |  | Wed 8/16/23 |  | Wed 8/16/23
1136 | 4 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 10/24/23 |  | Thu 11/2/23
1137 | 4 | 3.1 | Building 4 Steam Trap Replacement Installation | 0% |  | Tue 10/24/23 |  | Thu 10/26/23
1138 | 4 | 3.1 | Building 4 Steam Trap Replacement Acceptance | 0% |  | Thu 11/2/23 |  | Thu 11/2/23
1139 | 38 |  | Building 38 Mcadams Hall Installation | 21% |  | Mon 6/19/23 |  | Fri 7/26/24
1140 | 38 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 9/25/23 |  | Mon 10/2/23
1141 | 38 | 6.1 | Building 38 Building Envelope Installation | 99% | 99% | Mon 9/25/23 | 2023-10-17 | Tue 9/26/23 | 2023-10-21
1142 | 38 | 6.1 | Building 38 Building Envelope Acceptance | 0% |  | Mon 10/2/23 |  | Mon 10/2/23
1143 | 38 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 6/19/23 |  | Thu 7/6/23
1144 | 38 | 1.1 | Building 38 Interior Lighting and Controls Installation | 100% |  | Mon 6/19/23 |  | Fri 6/30/23
1145 | 38 | 1.1 | Building 38 Interior Lighting and Controls Acceptance | 0% |  | Thu 7/6/23 |  | Thu 7/6/23
1146 | 38 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 6/21/23 |  | Mon 7/10/23
1147 | 38 | 1.2 | Building 38 Exterior Lighting and Controls Installation | 100% |  | Wed 6/21/23 |  | Mon 7/3/23
1148 | 38 | 1.2 | Building 38 Exterior Lighting and Controls Acceptance | 0% |  | Mon 7/10/23 |  | Mon 7/10/23
1149 | 38 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 7/15/24 |  | Fri 7/26/24
1150 | 38 | 8.2 | Building 38 Control Optimization MDMP/MRR Installation | 0% |  | Mon 7/15/24 |  | Fri 7/19/24
1151 | 38 | 8.2 | Building 38 Control Optimization MDMP/MRR Acceptance | 0% |  | Fri 7/26/24 |  | Fri 7/26/24
1152 | 38 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
1153 | 38 | 2.1 | Building 38 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
1154 | 38 | 2.1 | Building 38 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1155 | 38 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 9/21/23 |  | Thu 9/28/23
1156 | 38 | 3.2 | Building 38 Mechanical Insulation Installation | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
1157 | 38 | 3.2 | Building 38 Mechanical Insulation Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1158 | 38 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 10/27/23 |  | Tue 11/7/23
1159 | 38 | 3.1 | Building 38 Steam Trap Replacement Installation | 0% |  | Fri 10/27/23 |  | Tue 10/31/23
1160 | 38 | 3.1 | Building 38 Steam Trap Replacement Acceptance | 0% |  | Tue 11/7/23 |  | Tue 11/7/23
1161 | 38 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Tue 11/28/23 |  | Tue 12/12/23
1162 | 38 | 4.1 | Building 38 Seal HVAC Ductwork Installation | 0% |  | Tue 11/28/23 |  | Wed 12/6/23
1163 | 38 | 4.1 | Building 38 Seal HVAC Ductwork Acceptance | 0% |  | Tue 12/12/23 |  | Tue 12/12/23
1164 | 38 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Mon 5/13/24 |  | Fri 7/26/24
1165 | 38 | 10 | Building 38 HVAC Upgrades Installation | 0% |  | Mon 5/13/24 |  | Fri 7/19/24
1166 | 38 | 10 | Building 38 HVAC Upgrades Acceptance | 0% |  | Fri 7/26/24 |  | Fri 7/26/24
1167 | 38 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Wed 12/13/23 |  | Tue 1/16/24
1168 | 38 | 5.1 | Building 38 Retro Cx Installation | 0% |  | Wed 12/13/23 |  | Tue 1/9/24
1169 | 38 | 5.1 | Building 38 Retro Cx Acceptance | 0% |  | Tue 1/16/24 |  | Tue 1/16/24
1170 | 23 |  | Building 23 Earle Hall Installation | 69% |  | Mon 7/17/23 |  | Mon 7/29/24
1171 | 23 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Wed 8/30/23 |  | Sun 9/10/23
1172 | 23 | 6.1 | Building 23 Building Envelope Installation | 99% |  | Wed 8/30/23 |  | Mon 9/4/23
1173 | 23 | 6.1 | Building 23 Building Envelope Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
1174 | 23 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 7/17/23 |  | Thu 8/10/23
1175 | 23 | 1.1 | Building 23 Interior Lighting and Controls Installation | 100% |  | Mon 7/17/23 |  | Thu 8/3/23
1176 | 23 | 1.1 | Building 23 Interior Lighting and Controls Acceptance | 0% |  | Thu 8/10/23 |  | Thu 8/10/23
1177 | 23 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 50% |  | Mon 7/17/23 |  | Thu 8/10/23
1178 | 23 | 1.2 | Building 23 Exterior Lighting and Controls Installation | 50% |  | Mon 7/17/23 |  | Thu 8/3/23
1179 | 23 | 1.2 | Building 23 Exterior Lighting and Controls Acceptance | 0% |  | Thu 8/10/23 |  | Thu 8/10/23
1180 | 23 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Mon 7/22/24 |  | Mon 7/29/24
1181 | 23 | 8.2 | Building 23 Control Optimization MDMP/MRR Installation | 0% |  | Mon 7/22/24 |  | Mon 7/22/24
1182 | 23 | 8.2 | Building 23 Control Optimization MDMP/MRR Acceptance | 0% |  | Mon 7/29/24 |  | Mon 7/29/24
1183 | 23 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/11/23 |  | Wed 8/16/23
1184 | 23 | 2.1 | Building 23 Water Conservation Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
1185 | 23 | 2.1 | Building 23 Water Conservation Acceptance | 0% |  | Wed 8/16/23 |  | Wed 8/16/23
1186 | 23 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 9/22/23 |  | Fri 9/29/23
1187 | 23 | 3.2 | Building 23 Mechanical Insulation Installation | 0% |  | Fri 9/22/23 |  | Fri 9/22/23
1188 | 23 | 3.2 | Building 23 Mechanical Insulation Acceptance | 0% |  | Fri 9/29/23 |  | Fri 9/29/23
1189 | 23 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 11/1/23 |  | Fri 11/10/23
1190 | 23 | 3.1 | Building 23 Steam Trap Replacement Installation | 0% |  | Wed 11/1/23 |  | Fri 11/3/23
1191 | 23 | 3.1 | Building 23 Steam Trap Replacement Acceptance | 0% |  | Fri 11/10/23 |  | Fri 11/10/23
1192 | 1259 |  | Building 1259 Biosystems Research Complex (BRC) Installation | 21% |  | Wed 7/5/23 |  | Mon 11/11/24
1193 | 1259 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 8/28/23 |  | Sun 9/10/23
1194 | 1259 | 6.1 | Building 1259 Building Envelope Installation | 99% |  | Mon 8/28/23 |  | Mon 9/4/23
1195 | 1259 | 6.1 | Building 1259 Building Envelope Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
1196 | 1259 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 7/5/23 |  | Mon 8/14/23
1197 | 1259 | 1.1 | Building 1259 Interior Lighting and Controls Installation | 100% | 99% | Wed 7/5/23 | 2023-07-05 | Wed 8/9/23 | 2023-10-12
1198 | 1259 | 1.1 | Building 1259 Interior Lighting and Controls Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
1199 | 1259 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 7/5/23 |  | Mon 8/14/23
1200 | 1259 | 1.2 | Building 1259 Exterior Lighting and Controls Installation | 100% | 99% | Wed 7/5/23 | 2023-07-05 | Wed 8/9/23 | 2023-10-12
1201 | 1259 | 1.2 | Building 1259 Exterior Lighting and Controls Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
1202 | 1259 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 9/25/23 |  | Sun 10/1/23
1203 | 1259 | 3.2 | Building 1259 Mechanical Insulation Installation | 0% |  | Mon 9/25/23 |  | Mon 9/25/23
1204 | 1259 | 3.2 | Building 1259 Mechanical Insulation Acceptance | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
1205 | 1259 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 11/6/23 |  | Wed 11/15/23
1206 | 1259 | 3.1 | Building 1259 Steam Trap Replacement Installation | 0% |  | Mon 11/6/23 |  | Wed 11/8/23
1207 | 1259 | 3.1 | Building 1259 Steam Trap Replacement Acceptance | 0% |  | Wed 11/15/23 |  | Wed 11/15/23
1208 | 1259 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 7/24/23 |  | Wed 8/9/23
1209 | 1259 | 4.1 | Building 1259 Seal HVAC Ductwork Installation | 95% |  | Mon 7/24/23 |  | Wed 8/2/23
1210 | 1259 | 4.1 | Building 1259 Seal HVAC Ductwork Acceptance | 0% |  | Wed 8/9/23 |  | Wed 8/9/23
1211 | 1259 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Thu 9/7/23 |  | Thu 9/14/23
1212 | 1259 | 3.3 | Building 1259 Condensate Receiver Repair Installation | 0% |  | Thu 9/7/23 |  | Fri 9/8/23
1213 | 1259 | 3.3 | Building 1259 Condensate Receiver Repair Acceptance | 0% |  | Thu 9/14/23 |  | Thu 9/14/23
1214 | 1259 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Wed 1/10/24 |  | Tue 2/13/24
1215 | 1259 | 5.1 | Building 1259 Retro Cx Installation | 0% |  | Wed 1/10/24 |  | Tue 2/6/24
1216 | 1259 | 5.1 | Building 1259 Retro Cx Acceptance | 0% |  | Tue 2/13/24 |  | Tue 2/13/24
1217 | 1259 | 9 | FIM 9.0 Lab Controls | 0% |  | Sat 12/2/23 |  | Mon 11/11/24
1218 | 1259 | 9 | Building 1259 Lab Controls Installation | 0% |  | Sat 12/2/23 |  | Mon 11/4/24
1219 | 1259 | 9 | Building 1259 Lab Controls Acceptance | 0% |  | Mon 11/11/24 |  | Mon 11/11/24
1220 | 1264 |  | Building 1264 Advanced Materials Research Lab | 0% |  | Sat 8/26/23 |  | Fri 3/22/24
1221 | 1264 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 1/8/24 |  | Thu 2/1/24
1222 | 1264 | 6.1 | Building 1264 Building Envelope Installation | 0% | 99% | Mon 1/8/24 | 2023-09-01 | Thu 1/25/24 | 2023-10-11
1223 | 1264 | 6.1 | Building 1264 Building Envelope Acceptance | 0% |  | Thu 2/1/24 |  | Thu 2/1/24
1224 | 1264 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Thu 10/26/23 |  | Wed 11/22/23
1225 | 1264 | 1.1 | Building 1264 Interior Lighting and Controls Installation | 0% |  | Thu 10/26/23 |  | Wed 11/15/23
1226 | 1264 | 1.1 | Building 1264 Interior Lighting and Controls Acceptance | 0% |  | Wed 11/22/23 |  | Wed 11/22/23
1227 | 1264 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 10/26/23 |  | Thu 11/2/23
1228 | 1264 | 1.2 | Building 1264 Exterior Lighting and Controls Installation | 0% |  | Thu 10/26/23 |  | Thu 10/26/23
1229 | 1264 | 1.2 | Building 1264 Exterior Lighting and Controls Acceptance | 0% |  | Thu 11/2/23 |  | Thu 11/2/23
1230 | 1264 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Sat 8/26/23 |  | Thu 8/31/23
1231 | 1264 | 2.1 | Building 1264 Water Conservation Installation | 95% |  | Sat 8/26/23 |  | Sat 8/26/23
1232 | 1264 | 2.1 | Building 1264 Water Conservation Acceptance | 0% |  | Thu 8/31/23 |  | Thu 8/31/23
1233 | 1264 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Thu 10/26/23 |  | Mon 11/6/23
1234 | 1264 | 4.1 | Building 1264 Seal HVAC Ductwork Installation | 0% |  | Thu 10/26/23 |  | Mon 10/30/23
1235 | 1264 | 4.1 | Building 1264 Seal HVAC Ductwork Acceptance | 0% |  | Mon 11/6/23 |  | Mon 11/6/23
1236 | 1264 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Wed 2/7/24 |  | Tue 3/12/24
1237 | 1264 | 5.1 | Building 1264 Retro Cx Installation | 0% |  | Wed 2/7/24 |  | Tue 3/5/24
1238 | 1264 | 5.1 | Building 1264 Retro Cx Acceptance | 0% |  | Tue 3/12/24 |  | Tue 3/12/24
1239 | 1264 | 11 | FIM 11.0 Chiller Plant Improvements | 0% |  | Mon 10/16/23 |  | Fri 3/22/24
1240 | 1264 | 11 | Building 1264 Chiller Plant Improvements Installation | 0% |  | Mon 10/16/23 |  | Fri 3/15/24
1241 | 1264 | 11 | Building 1264 Chiller Plant Improvements Acceptance | 0% |  | Fri 3/22/24 |  | Fri 3/22/24
1242 | 1264 | 12 | FIM 12.0 Heating Plant Improvements | 0% |  | Mon 10/16/23 |  | Thu 11/23/23
1243 | 1264 | 12 | Building 1264 Heating Plant Improvements Installation | 0% |  | Mon 10/16/23 |  | Thu 11/16/23
1244 | 1264 | 12 | Building 1264 Heating Plant Improvements Acceptance | 0% |  | Thu 11/23/23 |  | Thu 11/23/23
1245 | 1264 | 9 | FIM 9.0 Lab Controls | 0% |  | Mon 10/23/23 |  | Thu 2/29/24
1246 | 1264 | 9 | Building 1264 Lab Controls Installation | 0% | 5% | Mon 10/23/23 | 2023-08-23 | Thu 2/22/24 | 2023-10-24
1247 | 1264 | 9 | Building 1264 Lab Controls Acceptance | 0% |  | Thu 2/29/24 |  | Thu 2/29/24
1248 | 1264 | 9.1 | FIM 9.1 Lab Exhaust System Modifications | 0% |  | Mon 11/6/23 |  | Fri 2/23/24
1249 | 1264 | 9.1 | Building 1264 Lab Exhaust System Modifications Installation | 0% |  | Mon 11/6/23 |  | Fri 2/16/24
1250 | 1264 | 9.1 | Building 1264 Lab Exhaust System Modifications Acceptance | 0% |  | Fri 2/23/24 |  | Fri 2/23/24
1251 | 2002 |  | Building 2002 Bowen Hall Installation | 59% |  | Tue 7/11/23 |  | Mon 11/20/23
1252 | 2002 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/7/23 |  | Sat 8/12/23
1253 | 2002 | 6.1 | Building 2002 Building Envelope Installation | 95% |  | Mon 8/7/23 |  | Mon 8/7/23
1254 | 2002 | 6.1 | Building 2002 Building Envelope Acceptance | 0% |  | Sat 8/12/23 |  | Sat 8/12/23
1255 | 2002 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Tue 7/11/23 |  | Tue 7/18/23
1256 | 2002 | 1.1 | Building 2002 Interior Lighting and Controls Installation | 100% |  | Tue 7/11/23 |  | Wed 7/12/23
1257 | 2002 | 1.1 | Building 2002 Interior Lighting and Controls Acceptance | 0% |  | Tue 7/18/23 |  | Tue 7/18/23
1258 | 2002 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 7/11/23 |  | Tue 7/18/23
1259 | 2002 | 1.2 | Building 2002 Exterior Lighting and Controls Installation | 100% |  | Tue 7/11/23 |  | Wed 7/12/23
1260 | 2002 | 1.2 | Building 2002 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/18/23 |  | Tue 7/18/23
1261 | 2002 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1262 | 2002 | 2.1 | Building 2002 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1263 | 2002 | 2.1 | Building 2002 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1264 | 2002 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 9/26/23 |  | Mon 10/2/23
1265 | 2002 | 3.2 | Building 2002 Mechanical Insulation Installation | 0% |  | Tue 9/26/23 |  | Tue 9/26/23
1266 | 2002 | 3.2 | Building 2002 Mechanical Insulation Acceptance | 0% |  | Mon 10/2/23 |  | Mon 10/2/23
1267 | 2002 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 11/9/23 |  | Mon 11/20/23
1268 | 2002 | 3.1 | Building 2002 Steam Trap Replacement Installation | 0% |  | Thu 11/9/23 |  | Mon 11/13/23
1269 | 2002 | 3.1 | Building 2002 Steam Trap Replacement Acceptance | 0% |  | Mon 11/20/23 |  | Mon 11/20/23
1270 | 2005 |  | Building 2005 Norris Hall Installation | 42% |  | Fri 7/21/23 |  | Thu 11/23/23
1271 | 2005 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 7/24/23 |  | Mon 8/14/23
1272 | 2005 | 6.1 | Building 2005 Building Envelope Installation | 95% |  | Mon 7/24/23 |  | Wed 8/9/23
1273 | 2005 | 6.1 | Building 2005 Building Envelope Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
1274 | 2005 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Fri 7/21/23 |  | Sun 7/30/23
1275 | 2005 | 1.1 | Building 2005 Interior Lighting and Controls Installation | 100% | 99% | Fri 7/21/23 | 2023-07-21 | Mon 7/24/23 | 2023-10-24
1276 | 2005 | 1.1 | Building 2005 Interior Lighting and Controls Acceptance | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
1277 | 2005 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 5% |  | Fri 7/21/23 |  | Sun 7/30/23
1278 | 2005 | 1.2 | Building 2005 Exterior Lighting and Controls Installation | 5% | 99% | Fri 7/21/23 | 2023-07-21 | Mon 7/24/23 | 2023-10-24
1279 | 2005 | 1.2 | Building 2005 Exterior Lighting and Controls Acceptance | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
1280 | 2005 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1281 | 2005 | 2.1 | Building 2005 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1282 | 2005 | 2.1 | Building 2005 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1283 | 2005 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 9/27/23 |  | Tue 10/3/23
1284 | 2005 | 3.2 | Building 2005 Mechanical Insulation Installation | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
1285 | 2005 | 3.2 | Building 2005 Mechanical Insulation Acceptance | 0% |  | Tue 10/3/23 |  | Tue 10/3/23
1286 | 2005 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 11/14/23 |  | Thu 11/23/23
1287 | 2005 | 3.1 | Building 2005 Steam Trap Replacement Installation | 0% |  | Tue 11/14/23 |  | Thu 11/16/23
1288 | 2005 | 3.1 | Building 2005 Steam Trap Replacement Acceptance | 0% |  | Thu 11/23/23 |  | Thu 11/23/23
1289 | 2005 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Sun 9/10/23 |  | Mon 9/18/23
1290 | 2005 | 3.3 | Building 2005 Condensate Receiver Repair Installation | 0% |  | Sun 9/10/23 |  | Mon 9/11/23
1291 | 2005 | 3.3 | Building 2005 Condensate Receiver Repair Acceptance | 0% |  | Mon 9/18/23 |  | Mon 9/18/23
1292 | 3 |  | Building 3 Godfrey Hall Installation | 13% |  | Wed 4/19/23 |  | Tue 11/28/23
1293 | 3 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Sun 7/30/23 |  | Mon 8/7/23
1294 | 3 | 6.1 | Building 3 Building Envelope Installation | 95% |  | Sun 7/30/23 |  | Mon 7/31/23
1295 | 3 | 6.1 | Building 3 Building Envelope Acceptance | 0% |  | Mon 8/7/23 |  | Mon 8/7/23
1296 | 3 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 7/25/23 |  | Thu 8/3/23
1297 | 3 | 1.1 | Building 3 Interior Lighting and Controls Installation | 0% |  | Tue 7/25/23 |  | Fri 7/28/23
1298 | 3 | 1.1 | Building 3 Interior Lighting and Controls Acceptance | 0% |  | Thu 8/3/23 |  | Thu 8/3/23
1299 | 3 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 7/27/23 |  | Wed 8/2/23
1300 | 3 | 1.2 | Building 3 Exterior Lighting and Controls Installation | 0% |  | Thu 7/27/23 |  | Thu 7/27/23
1301 | 3 | 1.2 | Building 3 Exterior Lighting and Controls Acceptance | 0% |  | Wed 8/2/23 |  | Wed 8/2/23
1302 | 3 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1303 | 3 | 2.1 | Building 3 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1304 | 3 | 2.1 | Building 3 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1305 | 3 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 9/28/23 |  | Wed 10/4/23
1306 | 3 | 3.2 | Building 3 Mechanical Insulation Installation | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1307 | 3 | 3.2 | Building 3 Mechanical Insulation Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
1308 | 3 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 11/17/23 |  | Tue 11/28/23
1309 | 3 | 3.1 | Building 3 Steam Trap Replacement Installation | 0% |  | Fri 11/17/23 |  | Tue 11/21/23
1310 | 3 | 3.1 | Building 3 Steam Trap Replacement Acceptance | 0% |  | Tue 11/28/23 |  | Tue 11/28/23
1311 | 3 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Wed 4/19/23 |  | Tue 5/9/23
1312 | 3 | 5.1 | Building 3 Retro Cx Installation | 0% |  | Wed 4/19/23 |  | Tue 5/2/23
1313 | 3 | 5.1 | Building 3 Retro Cx Acceptance | 0% |  | Tue 5/9/23 |  | Tue 5/9/23
1314 | 2024 |  | Building 2024 Simpson Hall North Installation | 96% |  | Mon 7/17/23 |  | Mon 8/14/23
1315 | 2024 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 7/17/23 |  | Mon 8/14/23
1316 | 2024 | 6.1 | Building 2024 Building Envelope Installation | 95% |  | Mon 7/17/23 |  | Wed 8/9/23
1317 | 2024 | 6.1 | Building 2024 Building Envelope Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
1318 | 2024 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 7/17/23 |  | Wed 7/26/23
1319 | 2024 | 1.1 | Building 2024 Interior Lighting and Controls Installation | 100% |  | Mon 7/17/23 |  | Wed 7/19/23
1320 | 2024 | 1.1 | Building 2024 Interior Lighting and Controls Acceptance | 0% |  | Wed 7/26/23 |  | Wed 7/26/23
1321 | 2024 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 7/17/23 |  | Wed 7/26/23
1322 | 2024 | 1.2 | Building 2024 Exterior Lighting and Controls Installation | 100% |  | Mon 7/17/23 |  | Wed 7/19/23
1323 | 2024 | 1.2 | Building 2024 Exterior Lighting and Controls Acceptance | 0% |  | Wed 7/26/23 |  | Wed 7/26/23
1324 | 2024 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1325 | 2024 | 2.1 | Building 2024 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1326 | 2024 | 2.1 | Building 2024 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1327 | 2025 |  | Building 2025 Simpson Hall South Installation | 95% |  | Tue 7/18/23 |  | Mon 8/14/23
1328 | 2025 | 6.1 | FIM 6.1 Building Envelope | 94% |  | Tue 7/18/23 |  | Mon 8/14/23
1329 | 2025 | 6.1 | Building 2025 Building Envelope Installation | 94% |  | Tue 7/18/23 |  | Wed 8/9/23
1330 | 2025 | 6.1 | Building 2025 Building Envelope Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
1331 | 2025 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Tue 7/18/23 |  | Tue 7/25/23
1332 | 2025 | 1.1 | Building 2025 Interior Lighting and Controls Installation | 100% |  | Tue 7/18/23 |  | Tue 7/18/23
1333 | 2025 | 1.1 | Building 2025 Interior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1334 | 2025 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 7/18/23 |  | Tue 7/25/23
1335 | 2025 | 1.2 | Building 2025 Exterior Lighting and Controls Installation | 100% |  | Tue 7/18/23 |  | Tue 7/18/23
1336 | 2025 | 1.2 | Building 2025 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1337 | 2025 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1338 | 2025 | 2.1 | Building 2025 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1339 | 2025 | 2.1 | Building 2025 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1340 | 2004 |  | Building 2004 Bradley Hall Installation | 62% |  | Wed 7/19/23 |  | Fri 12/1/23
1341 | 2004 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Thu 7/20/23 |  | Thu 7/27/23
1342 | 2004 | 6.1 | Building 2004 Building Envelope Installation | 95% |  | Thu 7/20/23 |  | Thu 7/20/23
1343 | 2004 | 6.1 | Building 2004 Building Envelope Acceptance | 0% |  | Thu 7/27/23 |  | Thu 7/27/23
1344 | 2004 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 7/19/23 |  | Sun 7/30/23
1345 | 2004 | 1.1 | Building 2004 Interior Lighting and Controls Installation | 100% | 50% | Wed 7/19/23 | 2023-10-24 | Mon 7/24/23
1346 | 2004 | 1.1 | Building 2004 Interior Lighting and Controls Acceptance | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
1347 | 2004 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 7/19/23 |  | Sun 7/30/23
1348 | 2004 | 1.2 | Building 2004 Exterior Lighting and Controls Installation | 100% | 50% | Wed 7/19/23 | 2023-10-24 | Mon 7/24/23
1349 | 2004 | 1.2 | Building 2004 Exterior Lighting and Controls Acceptance | 0% |  | Sun 7/30/23 |  | Sun 7/30/23
1350 | 2004 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/7/23 |  | Sat 8/12/23
1351 | 2004 | 2.1 | Building 2004 Water Conservation Installation | 95% |  | Mon 8/7/23 |  | Mon 8/7/23
1352 | 2004 | 2.1 | Building 2004 Water Conservation Acceptance | 0% |  | Sat 8/12/23 |  | Sat 8/12/23
1353 | 2004 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 9/29/23 |  | Thu 10/5/23
1354 | 2004 | 3.2 | Building 2004 Mechanical Insulation Installation | 0% |  | Fri 9/29/23 |  | Fri 9/29/23
1355 | 2004 | 3.2 | Building 2004 Mechanical Insulation Acceptance | 0% |  | Thu 10/5/23 |  | Thu 10/5/23
1356 | 2004 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 11/22/23 |  | Fri 12/1/23
1357 | 2004 | 3.1 | Building 2004 Steam Trap Replacement Installation | 0% |  | Wed 11/22/23 |  | Fri 11/24/23
1358 | 2004 | 3.1 | Building 2004 Steam Trap Replacement Acceptance | 0% |  | Fri 12/1/23 |  | Fri 12/1/23
1359 | 2004 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Tue 9/12/23 |  | Wed 9/20/23
1360 | 2004 | 3.3 | Building 2004 Condensate Receiver Repair Installation | 0% |  | Tue 9/12/23 |  | Wed 9/13/23
1361 | 2004 | 3.3 | Building 2004 Condensate Receiver Repair Acceptance | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
1362 | 1059 |  | Building 1059 Ravenel Research Center Installation | 5% |  | Sun 3/5/23 |  | Tue 5/7/24
1363 | 1059 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 9/25/23 |  | Tue 10/3/23
1364 | 1059 | 6.1 | Building 1059 Building Envelope Installation | 99% |  | Mon 9/25/23 |  | Wed 9/27/23
1365 | 1059 | 6.1 | Building 1059 Building Envelope Acceptance | 0% |  | Tue 10/3/23 |  | Tue 10/3/23
1366 | 1059 | 8 | FIM 8.0 Controls Improvement | 0% |  | Thu 10/5/23 |  | Tue 12/5/23
1367 | 1059 | 8 | Building 1059 Controls Improvement Installation | 0% |  | Thu 10/5/23 |  | Wed 11/29/23
1368 | 1059 | 8 | Building 1059 Controls Improvement Acceptance | 0% |  | Tue 12/5/23 |  | Tue 12/5/23
1369 | 1059 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 3/13/23 |  | Thu 3/23/23
1370 | 1059 | 1.1 | Building 1059 Interior Lighting and Controls Installation | 100% |  | Mon 3/13/23 |  | Thu 3/16/23
1371 | 1059 | 1.1 | Building 1059 Interior Lighting and Controls Acceptance | 0% |  | Thu 3/23/23 |  | Thu 3/23/23
1372 | 1059 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Sun 3/5/23 |  | Mon 3/13/23
1373 | 1059 | 1.2 | Building 1059 Exterior Lighting and Controls Installation | 100% |  | Sun 3/5/23 |  | Mon 3/6/23
1374 | 1059 | 1.2 | Building 1059 Exterior Lighting and Controls Acceptance | 0% |  | Mon 3/13/23 |  | Mon 3/13/23
1375 | 1059 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Mon 11/20/23 |  | Tue 5/7/24
1376 | 1059 | 10 | Building 1059 HVAC Upgrades Installation | 0% |  | Mon 11/20/23 |  | Tue 4/30/24
1377 | 1059 | 10 | Building 1059 HVAC Upgrades Acceptance | 0% |  | Tue 5/7/24 |  | Tue 5/7/24
1378 | 1059 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 12/14/23 |  | Wed 1/3/24
1379 | 1059 | 5.1 | Building 1059 Retro Cx Installation | 0% |  | Thu 12/14/23 |  | Wed 12/27/23
1380 | 1059 | 5.1 | Building 1059 Retro Cx Acceptance | 0% |  | Wed 1/3/24 |  | Wed 1/3/24
1381 | 2001 |  | Building 2001 Donaldson Hall Installation | 81% |  | Mon 7/31/23 |  | Fri 10/6/23
1382 | 2001 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/7/23 |  | Sat 8/12/23
1383 | 2001 | 6.1 | Building 2001 Building Envelope Installation | 95% |  | Mon 8/7/23 |  | Mon 8/7/23
1384 | 2001 | 6.1 | Building 2001 Building Envelope Acceptance | 0% |  | Sat 8/12/23 |  | Sat 8/12/23
1385 | 2001 | 1.1 | FIM 1.1 Interior Lighting and Controls | 95% |  | Mon 7/31/23 |  | Tue 8/8/23
1386 | 2001 | 1.1 | Building 2001 Interior Lighting and Controls Installation | 95% |  | Mon 7/31/23 |  | Tue 8/1/23
1387 | 2001 | 1.1 | Building 2001 Interior Lighting and Controls Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
1388 | 2001 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 95% |  | Mon 7/31/23 |  | Tue 8/8/23
1389 | 2001 | 1.2 | Building 2001 Exterior Lighting and Controls Installation | 95% |  | Mon 7/31/23 |  | Tue 8/1/23
1390 | 2001 | 1.2 | Building 2001 Exterior Lighting and Controls Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
1391 | 2001 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1392 | 2001 | 2.1 | Building 2001 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1393 | 2001 | 2.1 | Building 2001 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1394 | 2001 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Sun 10/1/23 |  | Fri 10/6/23
1395 | 2001 | 3.2 | Building 2001 Mechanical Insulation Installation | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
1396 | 2001 | 3.2 | Building 2001 Mechanical Insulation Acceptance | 0% |  | Fri 10/6/23 |  | Fri 10/6/23
1397 | 1309 |  | Building 1309 Cribb Hall Installation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1398 | 1309 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1399 | 1309 | 2.1 | Building 1309 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1400 | 1309 | 2.1 | Building 1309 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1401 | 2003 |  | Building 2003 Wannamaker Hall Installation | 71% |  | Fri 7/14/23 |  | Tue 12/5/23
1402 | 2003 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Fri 7/14/23 |  | Thu 7/20/23
1403 | 2003 | 6.1 | Building 2003 Building Envelope Installation | 95% |  | Fri 7/14/23 |  | Fri 7/14/23
1404 | 2003 | 6.1 | Building 2003 Building Envelope Acceptance | 0% |  | Thu 7/20/23 |  | Thu 7/20/23
1405 | 2003 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Fri 7/14/23 |  | Tue 7/25/23
1406 | 2003 | 1.1 | Building 2003 Interior Lighting and Controls Installation | 100% |  | Fri 7/14/23 |  | Tue 7/18/23
1407 | 2003 | 1.1 | Building 2003 Interior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1408 | 2003 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Fri 7/14/23 |  | Tue 7/25/23
1409 | 2003 | 1.2 | Building 2003 Exterior Lighting and Controls Installation | 100% |  | Fri 7/14/23 |  | Tue 7/18/23
1410 | 2003 | 1.2 | Building 2003 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1411 | 2003 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1412 | 2003 | 2.1 | Building 2003 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1413 | 2003 | 2.1 | Building 2003 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1414 | 2003 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 10/2/23 |  | Mon 10/9/23
1415 | 2003 | 3.2 | Building 2003 Mechanical Insulation Installation | 0% |  | Mon 10/2/23 |  | Mon 10/2/23
1416 | 2003 | 3.2 | Building 2003 Mechanical Insulation Acceptance | 0% |  | Mon 10/9/23 |  | Mon 10/9/23
1417 | 2003 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 11/27/23 |  | Tue 12/5/23
1418 | 2003 | 3.1 | Building 2003 Steam Trap Replacement Installation | 0% |  | Mon 11/27/23 |  | Wed 11/29/23
1419 | 2003 | 3.1 | Building 2003 Steam Trap Replacement Acceptance | 0% |  | Tue 12/5/23 |  | Tue 12/5/23
1420 | 388 |  | Building 388 Fluor Daniel (Engineering Innovation Center) EIB Installation | 5% |  | Thu 8/3/23 |  | Fri 8/9/24
1421 | 388 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Fri 8/18/23 |  | Wed 8/23/23
1422 | 388 | 6.1 | Building 388 Building Envelope Installation | 0% | 99% | Fri 8/18/23 | 2023-10-11 | Fri 8/18/23 | 2023-10-11
1423 | 388 | 6.1 | Building 388 Building Envelope Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
1424 | 388 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Wed 10/11/23 |  | Fri 11/24/23
1425 | 388 | 1.1 | Building 388 Interior Lighting and Controls Installation | 0% |  | Wed 10/11/23 |  | Fri 11/17/23
1426 | 388 | 1.1 | Building 388 Interior Lighting and Controls Acceptance | 0% |  | Fri 11/24/23 |  | Fri 11/24/23
1427 | 388 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Wed 10/11/23 |  | Fri 11/24/23
1428 | 388 | 1.2 | Building 388 Interior Lighting and Controls Installation | 0% |  | Wed 10/11/23 |  | Fri 11/17/23
1429 | 388 | 1.2 | Building 388 Exterior Lighting and Controls Acceptance | 0% |  | Fri 11/24/23 |  | Fri 11/24/23
1430 | 388 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/28/23 |  | Wed 9/6/23
1431 | 388 | 2.1 | Building 388 Water Conservation Installation | 95% |  | Mon 8/28/23 |  | Wed 8/30/23
1432 | 388 | 2.1 | Building 388 Water Conservation Acceptance | 0% |  | Wed 9/6/23 |  | Wed 9/6/23
1433 | 388 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 10/3/23 |  | Tue 10/10/23
1434 | 388 | 3.2 | Building 388 Mechanical Insulation Installation | 0% |  | Tue 10/3/23 |  | Tue 10/3/23
1435 | 388 | 3.2 | Building 388 Mechanical Insulation Acceptance | 0% |  | Tue 10/10/23 |  | Tue 10/10/23
1436 | 388 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 11/30/23 |  | Fri 12/8/23
1437 | 388 | 3.1 | Building 388 Steam Trap Replacement Installation | 0% |  | Thu 11/30/23 |  | Sat 12/2/23
1438 | 388 | 3.1 | Building 388 Steam Trap Replacement Acceptance | 0% |  | Fri 12/8/23 |  | Fri 12/8/23
1439 | 388 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Thu 8/3/23 |  | Sat 8/26/23
1440 | 388 | 4.1 | Building 388 Seal HVAC Ductwork Installation | 95% |  | Thu 8/3/23 |  | Mon 8/21/23
1441 | 388 | 4.1 | Building 388 Seal HVAC Ductwork Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
1442 | 388 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Fri 12/1/23 |  | Mon 6/17/24
1443 | 388 | 10 | Building 388 HVAC Upgrades Installation | 0% |  | Fri 12/1/23 |  | Mon 6/10/24
1444 | 388 | 10 | Building 388 HVAC Upgrades Acceptance | 0% |  | Mon 6/17/24 |  | Mon 6/17/24
1445 | 388 | 9 | FIM 9.0 Lab Controls | 0% |  | Fri 2/23/24 |  | Thu 5/9/24
1446 | 388 | 9 | Building 388 Lab Controls Installation | 0% |  | Fri 2/23/24 |  | Thu 5/2/24
1447 | 388 | 9 | Building 388 Lab Controls Acceptance | 0% |  | Thu 5/9/24 |  | Thu 5/9/24
1448 | 388 | 9.1 | FIM 9.1 Lab Exhaust System Modifications | 0% |  | Mon 2/19/24 |  | Fri 8/9/24
1449 | 388 | 9.1 | Building 388 Lab Exhaust System Modifications Installation | 0% |  | Mon 2/19/24 |  | Fri 8/2/24
1450 | 388 | 9.1 | Building 388 Lab Exhaust System Modifications Acceptance | 0% |  | Fri 8/9/24 |  | Fri 8/9/24
1451 | 265 |  | Building 265 Barre Hall Installation | 41% |  | Mon 7/17/23 |  | Wed 1/17/24
1452 | 265 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Tue 8/15/23 |  | Sun 8/20/23
1453 | 265 | 6.1 | Building 265 Building Envelope Installation | 95% |  | Tue 8/15/23 |  | Tue 8/15/23
1454 | 265 | 6.1 | Building 265 Building Envelope Acceptance | 0% |  | Sun 8/20/23 |  | Sun 8/20/23
1455 | 265 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 10/23/23 |  | Tue 11/21/23
1456 | 265 | 1.1 | Building 265 Interior Lighting and Controls Installation | 0% |  | Mon 10/23/23 |  | Tue 11/14/23
1457 | 265 | 1.1 | Building 265 Interior Lighting and Controls Acceptance | 0% |  | Tue 11/21/23 |  | Tue 11/21/23
1458 | 265 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Mon 10/23/23 |  | Tue 11/21/23
1459 | 265 | 1.2 | Building 265 Exterior Lighting and Controls Installation | 0% |  | Mon 10/23/23 |  | Tue 11/14/23
1460 | 265 | 1.2 | Building 265 Exterior Lighting and Controls Acceptance | 0% |  | Tue 11/21/23 |  | Tue 11/21/23
1461 | 265 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/23/23 |  | Mon 8/28/23
1462 | 265 | 2.1 | Building 265 Water Conservation Installation | 95% |  | Wed 8/23/23 |  | Wed 8/23/23
1463 | 265 | 2.1 | Building 265 Water Conservation Acceptance | 0% |  | Mon 8/28/23 |  | Mon 8/28/23
1464 | 265 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 10/4/23 |  | Wed 10/11/23
1465 | 265 | 3.2 | Building 265 Mechanical Insulation Installation | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
1466 | 265 | 3.2 | Building 1 Mechanical Insulation Acceptance | 0% |  | Wed 10/11/23 |  | Wed 10/11/23
1467 | 265 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 12/4/23 |  | Tue 12/12/23
1468 | 265 | 3.1 | Building 265 Steam Trap Replacement Installation | 0% |  | Mon 12/4/23 |  | Wed 12/6/23
1469 | 265 | 3.1 | Building 265 Steam Trap Replacement Acceptance | 0% |  | Tue 12/12/23 |  | Tue 12/12/23
1470 | 265 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 7/17/23 |  | Tue 8/29/23
1471 | 265 | 4.1 | Building 265 Seal HVAC Ductwork Installation | 95% |  | Mon 7/17/23 |  | Thu 8/24/23
1472 | 265 | 4.1 | Building 265 Seal HVAC Ductwork Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1473 | 265 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 12/28/23 |  | Wed 1/17/24
1474 | 265 | 5.1 | Building 265 Retro Cx Installation | 0% |  | Thu 12/28/23 |  | Wed 1/10/24
1475 | 265 | 5.1 | Building 265 Retro Cx Acceptance | 0% |  | Wed 1/17/24 |  | Wed 1/17/24
1476 | 1222 |  | Building 1222 Clemson Environmental Tech Lab CETL (RUST) Installation | 33% |  | Mon 8/21/23 |  | Wed 1/31/24
1477 | 1222 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Wed 8/23/23 |  | Fri 9/8/23
1478 | 1222 | 6.1 | Building 1222 Building Envelope Installation | 99% |  | Wed 8/23/23 |  | Fri 9/1/23
1479 | 1222 | 6.1 | Building 1222 Building Envelope Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
1480 | 1222 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Wed 11/15/23 |  | Tue 11/28/23
1481 | 1222 | 1.1 | Building 1222 Interior Lighting and Controls Installation | 0% |  | Wed 11/15/23 |  | Tue 11/21/23
1482 | 1222 | 1.1 | Building 1222 Interior Lighting and Controls Acceptance | 0% |  | Tue 11/28/23 |  | Tue 11/28/23
1483 | 1222 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Fri 11/17/23 |  | Fri 11/24/23
1484 | 1222 | 1.2 | Building 1222 Exterior Lighting and Controls Installation | 0% |  | Fri 11/17/23 |  | Fri 11/17/23
1485 | 1222 | 1.2 | Building 1222 Exterior Lighting and Controls Acceptance | 0% |  | Fri 11/24/23 |  | Fri 11/24/23
1486 | 1222 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
1487 | 1222 | 2.1 | Building 1222 Water Conservation Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
1488 | 1222 | 2.1 | Building 1222 Water Conservation Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
1489 | 1222 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Fri 8/25/23 |  | Wed 9/6/23
1490 | 1222 | 4.1 | Building 1222 Seal HVAC Ductwork Installation | 0% |  | Fri 8/25/23 |  | Wed 8/30/23
1491 | 1222 | 4.1 | Building 1222 Seal HVAC Ductwork Acceptance | 0% |  | Wed 9/6/23 |  | Wed 9/6/23
1492 | 1222 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 1/11/24 |  | Wed 1/31/24
1493 | 1222 | 5.1 | Building 1222 Retro Cx Installation | 0% |  | Thu 1/11/24 |  | Wed 1/24/24
1494 | 1222 | 5.1 | Building 1222 Retro Cx Acceptance | 0% |  | Wed 1/31/24 |  | Wed 1/31/24
1495 | 28 |  | Building 28 Lee Hall Installation | 64% |  | Mon 7/24/23 |  | Wed 2/28/24
1496 | 28 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Thu 8/10/23 |  | Sun 8/20/23
1497 | 28 | 6.1 | Building 28 Building Envelope Installation | 95% |  | Thu 8/10/23 |  | Tue 8/15/23
1498 | 28 | 6.1 | Building 28 Building Envelope Acceptance | 0% |  | Sun 8/20/23 |  | Sun 8/20/23
1499 | 28 | 1.1 | FIM 1.1 Interior Lighting and Controls | 95% |  | Mon 7/24/23 |  | Mon 8/21/23
1500 | 28 | 1.1 | Building 28 Interior Lighting and Controls Installation | 95% |  | Mon 7/24/23 |  | Wed 8/16/23
1501 | 28 | 1.1 | Building 28 Interior Lighting and Controls Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1502 | 28 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 95% |  | Mon 7/24/23 |  | Mon 8/21/23
1503 | 28 | 1.2 | Building 28 Exterior Lighting and Controls Installation | 95% |  | Mon 7/24/23 |  | Wed 8/16/23
1504 | 28 | 1.2 | Building 28 Exterior Lighting and Controls Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1505 | 28 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
1506 | 28 | 2.1 | Building 28 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
1507 | 28 | 2.1 | Building 28 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1508 | 28 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 10/5/23 |  | Thu 10/12/23
1509 | 28 | 3.2 | Building 28 Mechanical Insulation Installation | 0% |  | Thu 10/5/23 |  | Thu 10/5/23
1510 | 28 | 3.2 | Building 28 Mechanical Insulation Acceptance | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
1511 | 28 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 12/7/23 |  | Fri 12/15/23
1512 | 28 | 3.1 | Building 28 Steam Trap Replacement Installation | 0% |  | Thu 12/7/23 |  | Sat 12/9/23
1513 | 28 | 3.1 | Building 28 Steam Trap Replacement Acceptance | 0% |  | Fri 12/15/23 |  | Fri 12/15/23
1514 | 28 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 1/25/24 |  | Wed 2/28/24
1515 | 28 | 5.1 | Building 28 Retro Cx Installation | 0% |  | Thu 1/25/24 |  | Wed 2/21/24
1516 | 28 | 5.1 | Building 28 Retro Cx Acceptance | 0% |  | Wed 2/28/24 |  | Wed 2/28/24
1517 | 1143 |  | Building 1143 Brooks Center for the Performing Arts Installation | 28% |  | Thu 8/17/23 |  | Wed 4/24/24
1518 | 1143 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 4/15/24 |  | Wed 4/24/24
1519 | 1143 | 6.1 | Building 1143 Building Envelope Installation | 0% | 95% | Mon 4/15/24 | 2023-10-13 | Wed 4/17/24 | 2023-10-13
1520 | 1143 | 6.1 | Building 1143 Building Envelope Acceptance | 0% |  | Wed 4/24/24 |  | Wed 4/24/24
1521 | 1143 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Thu 8/17/23 |  | Tue 9/5/23
1522 | 1143 | 1.1 | Building 1143 Interior Lighting and Controls Installation | 0% |  | Thu 8/17/23 |  | Tue 8/29/23
1523 | 1143 | 1.1 | Building 1143 Interior Lighting and Controls Acceptance | 0% |  | Tue 9/5/23 |  | Tue 9/5/23
1524 | 1143 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Sat 8/19/23 |  | Thu 8/24/23
1525 | 1143 | 1.2 | Building 1143 Exterior Lighting and Controls Installation | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1526 | 1143 | 1.2 | Building 1143 Exterior Lighting and Controls Acceptance | 0% |  | Thu 8/24/23 |  | Thu 8/24/23
1527 | 1143 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/18/23 |  | Wed 8/23/23
1528 | 1143 | 2.1 | Building 1143 Water Conservation Installation | 95% |  | Fri 8/18/23 |  | Fri 8/18/23
1529 | 1143 | 2.1 | Building 1143 Water Conservation Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
1530 | 1143 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 10/6/23 |  | Fri 10/13/23
1531 | 1143 | 3.2 | Building 1143 Mechanical Insulation Installation | 0% |  | Fri 10/6/23 |  | Fri 10/6/23
1532 | 1143 | 3.2 | Building 1143 Mechanical Insulation Acceptance | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
1533 | 1143 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 12/11/23 |  | Wed 12/20/23
1534 | 1143 | 3.1 | Building 1143 Steam Trap Replacement Installation | 0% |  | Mon 12/11/23 |  | Wed 12/13/23
1535 | 1143 | 3.1 | Building 1143 Steam Trap Replacement Acceptance | 0% |  | Wed 12/20/23 |  | Wed 12/20/23
1536 | 1143 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 85% |  | Mon 8/28/23 |  | Wed 9/13/23
1537 | 1143 | 4.1 | Building 1143 Seal HVAC Ductwork Installation | 85% |  | Mon 8/28/23 |  | Thu 9/7/23
1538 | 1143 | 4.1 | Building 1143 Seal HVAC Ductwork Acceptance | 0% |  | Wed 9/13/23 |  | Wed 9/13/23
1539 | 1279 |  | Building 1279 Lee III Installation | 0% |  | Wed 8/30/23 |  | Mon 9/11/23
1540 | 1279 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Wed 8/30/23 |  | Mon 9/11/23
1541 | 1279 | 1.1 | Building 1279 Interior Lighting and Controls Installation | 0% |  | Wed 8/30/23 |  | Tue 9/5/23
1542 | 1279 | 1.1 | Building 1279 Interior Lighting and Controls Acceptance | 0% |  | Mon 9/11/23 |  | Mon 9/11/23
1543 | 1279 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Fri 9/1/23 |  | Sun 9/10/23
1544 | 1279 | 1.2 | Building 1279 Exterior Lighting and Controls Installation | 0% |  | Fri 9/1/23 |  | Mon 9/4/23
1545 | 1279 | 1.2 | Building 1279 Exterior Lighting and Controls Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
1546 | 266 |  | Building 266 Lehotsky Hall Installation | 92% |  | Tue 2/14/23 |  | Mon 12/25/23
1547 | 266 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Wed 8/16/23 |  | Mon 8/21/23
1548 | 266 | 6.1 | Building 266 Building Envelope Installation | 0% | 99% | Wed 8/16/23 | 2023-10-12 | Wed 8/16/23 | 2023-10-12
1549 | 266 | 6.1 | Building 266 Building Envelope Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1550 | 266 | 1.1 | FIM 1.1 Interior Lighting and Controls | 100% |  | Tue 2/14/23 |  | Fri 4/21/23
1551 | 266 | 1.1 | Building 266 Interior Lighting and Controls Installation | 100% |  | Tue 2/14/23 |  | Fri 3/17/23
1552 | 266 | 1.1 | Building 266 Interior Lighting and Controls Acceptance | 100% |  | Fri 4/21/23 |  | Fri 4/21/23
1553 | 266 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Tue 2/14/23 |  | Tue 7/25/23
1554 | 266 | 1.2 | Building 266 Exterior Lighting and Controls Installation | 100% |  | Tue 2/14/23 |  | Tue 7/18/23
1555 | 266 | 1.2 | Building 266 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1556 | 266 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/24/23 |  | Tue 8/29/23
1557 | 266 | 2.1 | Building 266 Water Conservation Installation | 95% |  | Thu 8/24/23 |  | Thu 8/24/23
1558 | 266 | 2.1 | Building 266 Water Conservation Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1559 | 266 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 10/9/23 |  | Mon 10/16/23
1560 | 266 | 3.2 | Building 266 Mechanical Insulation Installation | 0% |  | Mon 10/9/23 |  | Mon 10/9/23
1561 | 266 | 3.2 | Building 266 Mechanical Insulation Acceptance | 0% |  | Mon 10/16/23 |  | Mon 10/16/23
1562 | 266 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 12/14/23 |  | Mon 12/25/23
1563 | 266 | 3.1 | Building 266 Steam Trap Replacement Installation | 0% |  | Thu 12/14/23 |  | Mon 12/18/23
1564 | 266 | 3.1 | Building 266 Steam Trap Replacement Acceptance | 0% |  | Mon 12/25/23 |  | Mon 12/25/23
1565 | 266 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Mon 10/9/23 |  | Tue 10/24/23
1566 | 266 | 4.1 | Building 266 Seal HVAC Ductwork Installation | 0% | 99% | Mon 10/9/23 | 2023-10-09 | Tue 10/17/23 | 2023-10-11
1567 | 266 | 4.1 | Building 266 Seal HVAC Ductwork Acceptance | 0% |  | Tue 10/24/23 |  | Tue 10/24/23
1568 | 24 |  | Building 24 Lowry Hall Installation | 61% |  | Fri 8/4/23 |  | Mon 8/5/24
1569 | 24 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Thu 8/31/23 |  | Sun 9/10/23
1570 | 24 | 6.1 | Building 24 Building Envelope Installation | 99% |  | Thu 8/31/23 |  | Mon 9/4/23
1571 | 24 | 6.1 | Building 24 Building Envelope Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
1572 | 24 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 9/20/23 |  | Wed 10/4/23
1573 | 24 | 1.1 | Building 24 Interior Lighting and Controls Installation | 99% | 99% | Wed 9/20/23 | 2023-09-20 | Thu 9/28/23 | 2023-10-16
1574 | 24 | 1.1 | Building 24 Interior Lighting and Controls Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
1575 | 24 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 9/20/23 |  | Wed 10/4/23
1576 | 24 | 1.2 | Building 24 Exterior Lighting and Controls Installation | 99% | 99% | Wed 9/20/23 | 2023-09-20 | Thu 9/28/23 | 2023-10-16
1577 | 24 | 1.2 | Building 24 Exterior Lighting and Controls Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
1578 | 24 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Tue 7/23/24 |  | Mon 8/5/24
1579 | 24 | 8.2 | Building 24 Control Optimization MDMP/MRR Installation | 0% |  | Tue 7/23/24 |  | Mon 7/29/24
1580 | 24 | 8.2 | Building 24 Control Optimization MDMP/MRR Acceptance | 0% |  | Mon 8/5/24 |  | Mon 8/5/24
1581 | 24 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
1582 | 24 | 2.1 | Building 24 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
1583 | 24 | 2.1 | Building 24 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
1584 | 24 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 10/10/23 |  | Tue 10/17/23
1585 | 24 | 3.2 | Building 24 Mechanical Insulation Installation | 0% |  | Tue 10/10/23 |  | Tue 10/10/23
1586 | 24 | 3.2 | Building 24 Mechanical Insulation Acceptance | 0% |  | Tue 10/17/23 |  | Tue 10/17/23
1587 | 24 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 12/19/23 |  | Thu 12/28/23
1588 | 24 | 3.1 | Building 24 Steam Trap Replacement Installation | 0% |  | Tue 12/19/23 |  | Thu 12/21/23
1589 | 24 | 3.1 | Building 24 Steam Trap Replacement Acceptance | 0% |  | Thu 12/28/23 |  | Thu 12/28/23
1590 | 24 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Thu 9/14/23 |  | Fri 9/22/23
1591 | 24 | 3.3 | Building 24 Condensate Receiver Repair Installation | 0% |  | Thu 9/14/23 |  | Fri 9/15/23
1592 | 24 | 3.3 | Building 24 Condensate Receiver Repair Acceptance | 0% |  | Fri 9/22/23 |  | Fri 9/22/23
1593 | 39 |  | Building 39 Newman Hall Installation | 94% |  | Thu 2/23/23 |  | Tue 1/2/24
1594 | 39 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Tue 9/26/23 |  | Wed 10/4/23
1595 | 39 | 6.1 | Building 39 Building Envelope Installation | 99% | 99% | Tue 9/26/23 | 2023-10-17 | Thu 9/28/23 | 2023-10-17
1596 | 39 | 6.1 | Building 39 Building Envelope Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
1597 | 39 | 8 | FIM 8.0 Controls Improvement | 95% |  | Fri 6/16/23 |  | Tue 8/15/23
1598 | 39 | 8 | Building 39 Controls Improvement Installation | 95% | 99% | Fri 6/16/23 | 2023-06-16 | Thu 8/10/23 | 2023-10-13
1599 | 39 | 8 | Building 39 Controls Improvement Acceptance | 0% |  | Tue 8/15/23 |  | Tue 8/15/23
1600 | 39 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Thu 2/23/23 |  | Tue 3/21/23
1601 | 39 | 1.1 | Building 39 Interior Lighting and Controls Installation | 100% |  | Thu 2/23/23 |  | Tue 3/14/23
1602 | 39 | 1.1 | Building 39 Interior Lighting and Controls Acceptance | 0% |  | Tue 3/21/23 |  | Tue 3/21/23
1603 | 39 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 5/15/23 |  | Tue 7/25/23
1604 | 39 | 1.2 | Building 39 Exterior Lighting and Controls Installation | 100% |  | Mon 5/15/23 |  | Tue 7/18/23
1605 | 39 | 1.2 | Building 39 Exterior Lighting and Controls Acceptance | 0% |  | Tue 7/25/23 |  | Tue 7/25/23
1606 | 39 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
1607 | 39 | 2.1 | Building 39 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
1608 | 39 | 2.1 | Building 39 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1609 | 39 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 10/11/23 |  | Thu 10/19/23
1610 | 39 | 3.2 | Building 39 Mechanical Insulation Installation | 0% |  | Wed 10/11/23 |  | Thu 10/12/23
1611 | 39 | 3.2 | Building 39 Mechanical Insulation Acceptance | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
1612 | 39 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 12/22/23 |  | Tue 1/2/24
1613 | 39 | 3.1 | Building 39 Steam Trap Replacement Installation | 0% |  | Fri 12/22/23 |  | Tue 12/26/23
1614 | 39 | 3.1 | Building 39 Steam Trap Replacement Acceptance | 0% |  | Tue 1/2/24 |  | Tue 1/2/24
1615 | 40 |  | Building 40 Poole Agricultural Center Installation | 57% |  | Mon 4/10/23 |  | Wed 3/27/24
1616 | 40 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 10/23/23 |  | Mon 11/6/23
1617 | 40 | 6.1 | Building 40 Building Envelope Installation | 0% | 99% | Mon 10/23/23 | 2023-10-18 | Mon 10/30/23 | 2023-10-18
1618 | 40 | 6.1 | Building 40 Building Envelope Acceptance | 0% |  | Mon 11/6/23 |  | Mon 11/6/23
1619 | 40 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 8/23/23 |  | Wed 9/20/23
1620 | 40 | 1.1 | Building 40 Interior Lighting and Controls Installation | 99% |  | Wed 8/23/23 |  | Wed 9/13/23
1621 | 40 | 1.1 | Building 40 Interior Lighting and Controls Acceptance | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
1622 | 40 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 8/23/23 |  | Wed 9/20/23
1623 | 40 | 1.2 | Building 40 Exterior Lighting and Controls Installation | 99% |  | Wed 8/23/23 |  | Wed 9/13/23
1624 | 40 | 1.2 | Building 40 Exterior Lighting and Controls Acceptance | 0% |  | Wed 9/20/23 |  | Wed 9/20/23
1625 | 40 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/15/23 |  | Sun 8/20/23
1626 | 40 | 2.1 | Building 40 Water Conservation Installation | 95% |  | Tue 8/15/23 |  | Tue 8/15/23
1627 | 40 | 2.1 | Building 40 Water Conservation Acceptance | 0% |  | Sun 8/20/23 |  | Sun 8/20/23
1628 | 40 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 10/13/23 |  | Fri 10/20/23
1629 | 40 | 3.2 | Building 40 Mechanical Insulation Installation | 0% |  | Fri 10/13/23 |  | Fri 10/13/23
1630 | 40 | 3.2 | Building 40 Mechanical Insulation Acceptance | 0% |  | Fri 10/20/23 |  | Fri 10/20/23
1631 | 40 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 12/27/23 |  | Fri 1/5/24
1632 | 40 | 3.1 | Building 40 Steam Trap Replacement Installation | 0% |  | Wed 12/27/23 |  | Fri 12/29/23
1633 | 40 | 3.1 | Building 40 Steam Trap Replacement Acceptance | 0% |  | Fri 1/5/24 |  | Fri 1/5/24
1634 | 40 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 95% |  | Mon 4/10/23 |  | Mon 4/24/23
1635 | 40 | 4.1 | Building 40 Seal HVAC Ductwork Installation | 95% |  | Mon 4/10/23 |  | Mon 4/17/23
1636 | 40 | 4.1 | Building 40 Seal HVAC Ductwork Acceptance | 0% |  | Mon 4/24/23 |  | Mon 4/24/23
1637 | 40 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Mon 9/18/23 |  | Tue 9/26/23
1638 | 40 | 3.3 | Building 40 Condensate Receiver Repair Installation | 0% |  | Mon 9/18/23 |  | Tue 9/19/23
1639 | 40 | 3.3 | Building 40 Condensate Receiver Repair Acceptance | 0% |  | Tue 9/26/23 |  | Tue 9/26/23
1640 | 40 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 2/22/24 |  | Wed 3/27/24
1641 | 40 | 5.1 | Building 40 Retro Cx Installation | 0% |  | Thu 2/22/24 |  | Wed 3/20/24
1642 | 40 | 5.1 | Building 40 Retro Cx Acceptance | 0% |  | Wed 3/27/24 |  | Wed 3/27/24
1643 | 1277 |  | Building 1277 Life Sciences Building Installation | 51% |  | Tue 8/22/23 |  | Wed 4/24/24
1644 | 1277 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 8/28/23 |  | Fri 9/8/23
1645 | 1277 | 6.1 | Building 1277 Building Envelope Installation | 99% |  | Mon 8/28/23 |  | Fri 9/1/23
1646 | 1277 | 6.1 | Building 1277 Building Envelope Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
1647 | 1277 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 9/18/23 |  | Thu 9/28/23
1648 | 1277 | 1.1 | Building 1277 Interior Lighting and Controls Installation | 99% |  | Mon 9/18/23 |  | Thu 9/21/23
1649 | 1277 | 1.1 | Building 1277 Interior Lighting and Controls Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1650 | 1277 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 9/18/23 |  | Thu 9/28/23
1651 | 1277 | 1.2 | Building 1277 Exterior Lighting and Controls Installation | 99% |  | Mon 9/18/23 |  | Thu 9/21/23
1652 | 1277 | 1.2 | Building 1277 Exterior Lighting and Controls Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1653 | 1277 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 10/16/23 |  | Mon 10/23/23
1654 | 1277 | 3.2 | Building 1277 Mechanical Insulation Installation | 0% |  | Mon 10/16/23 |  | Mon 10/16/23
1655 | 1277 | 3.2 | Building 1277 Mechanical Insulation Acceptance | 0% |  | Mon 10/23/23 |  | Mon 10/23/23
1656 | 1277 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 1/1/24 |  | Wed 1/10/24
1657 | 1277 | 3.1 | Building 1277 Steam Trap Replacement Installation | 0% |  | Mon 1/1/24 |  | Wed 1/3/24
1658 | 1277 | 3.1 | Building 1277 Steam Trap Replacement Acceptance | 0% |  | Wed 1/10/24 |  | Wed 1/10/24
1659 | 1277 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Wed 10/18/23 |  | Thu 11/9/23
1660 | 1277 | 4.1 | Building 1277 Seal HVAC Ductwork Installation | 0% | 85% | Wed 10/18/23 | 2023-10-16 | Thu 11/2/23
1661 | 1277 | 4.1 | Building 1277 Seal HVAC Ductwork Acceptance | 0% |  | Thu 11/9/23 |  | Thu 11/9/23
1662 | 1277 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 3/21/24 |  | Wed 4/24/24
1663 | 1277 | 5.1 | Building 1277 Retro Cx Installation | 0% |  | Thu 3/21/24 |  | Wed 4/17/24
1664 | 1277 | 5.1 | Building 1277 Retro Cx Acceptance | 0% |  | Wed 4/24/24 |  | Wed 4/24/24
1665 | 1277 | 9 | FIM 9.0 Lab Controls | 99% |  | Tue 8/22/23 |  | Wed 9/27/23
1666 | 1277 | 9 | Building 1277 Lab Controls Installation | 99% |  | Tue 8/22/23 |  | Wed 9/20/23
1667 | 1277 | 9 | Building 1277 Lab Controls Acceptance | 0% |  | Wed 9/27/23 |  | Wed 9/27/23
1668 | 309 |  | Building 309 Edwards Hall Installation | 60% |  | Wed 8/16/23 |  | Mon 8/12/24
1669 | 309 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/17/23 |  | Tue 8/22/23
1670 | 309 | 6.1 | Building 309 Building Envelope Installation | 0% | 99% | Thu 8/17/23 | 2023-10-11 | Thu 8/17/23 | 2023-10-11
1671 | 309 | 6.1 | Building 309 Building Envelope Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
1672 | 309 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 8/30/23 |  | Thu 9/28/23
1673 | 309 | 1.1 | Building 309 Interior Lighting and Controls Installation | 99% |  | Wed 8/30/23 |  | Thu 9/21/23
1674 | 309 | 1.1 | Building 309 Interior Lighting and Controls Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1675 | 309 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 8/30/23 |  | Thu 9/28/23
1676 | 309 | 1.2 | Building 309 Exterior Lighting and Controls Installation | 99% |  | Wed 8/30/23 |  | Thu 9/21/23
1677 | 309 | 1.2 | Building 309 Exterior Lighting and Controls Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1678 | 309 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Tue 7/30/24 |  | Mon 8/12/24
1679 | 309 | 8.2 | Building 309 Control Optimization MDMP/MRR Installation | 0% |  | Tue 7/30/24 |  | Mon 8/5/24
1680 | 309 | 8.2 | Building 309 Control Optimization MDMP/MRR Acceptance | 0% |  | Mon 8/12/24 |  | Mon 8/12/24
1681 | 309 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
1682 | 309 | 2.1 | Building 309 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
1683 | 309 | 2.1 | Building 309 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1684 | 309 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 10/17/23 |  | Tue 10/24/23
1685 | 309 | 3.2 | Building 309 Mechanical Insulation Installation | 0% |  | Tue 10/17/23 |  | Tue 10/17/23
1686 | 309 | 3.2 | Building 309 Mechanical Insulation Acceptance | 0% |  | Tue 10/24/23 |  | Tue 10/24/23
1687 | 309 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 1/4/24 |  | Mon 1/15/24
1688 | 309 | 3.1 | Building 309 Steam Trap Replacement Installation | 0% |  | Thu 1/4/24 |  | Mon 1/8/24
1689 | 309 | 3.1 | Building 309 Steam Trap Replacement Acceptance | 0% |  | Mon 1/15/24 |  | Mon 1/15/24
1690 | 309 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Mon 11/6/23 |  | Tue 11/28/23
1691 | 309 | 4.1 | Building 309 Seal HVAC Ductwork Installation | 0% |  | Mon 11/6/23 |  | Tue 11/21/23
1692 | 309 | 4.1 | Building 309 Seal HVAC Ductwork Acceptance | 0% |  | Tue 11/28/23 |  | Tue 11/28/23
1693 | 309 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Wed 9/20/23 |  | Thu 9/28/23
1694 | 309 | 3.3 | Building 309 Condensate Receiver Repair Installation | 0% |  | Wed 9/20/23 |  | Thu 9/21/23
1695 | 309 | 3.3 | Building 309 Condensate Receiver Repair Acceptance | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
1696 | 272 |  | Building 272 Jordan Hall Installation | 1% |  | Fri 8/25/23 |  | Tue 8/27/24
1697 | 272 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Wed 11/15/23 |  | Thu 12/14/23
1698 | 272 | 6.1 | Building 272 Building Envelope Installation | 0% | 99% | Wed 11/15/23 | 2023-10-02 | Fri 12/8/23 | 2023-10-03
1699 | 272 | 6.1 | Building 272 Building Envelope Acceptance | 0% |  | Thu 12/14/23 |  | Thu 12/14/23
1700 | 272 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 9/11/23 |  | Mon 10/16/23
1701 | 272 | 1.1 | Building 272 Interior Lighting and Controls Installation | 0% | 99% | Mon 9/11/23 | 2023-10-04 | Mon 10/9/23 | 2023-10-23
1702 | 272 | 1.1 | Building 272 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/16/23 |  | Mon 10/16/23
1703 | 272 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Mon 9/11/23 |  | Mon 10/16/23
1704 | 272 | 1.2 | Building 272 Exterior Lighting and Controls Installation | 0% | 99% | Mon 9/11/23 | 2023-10-04 | Mon 10/9/23 | 2023-10-23
1705 | 272 | 1.2 | Building 272 Exterior Lighting and Controls Acceptance | 0% |  | Mon 10/16/23 |  | Mon 10/16/23
1706 | 272 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/25/23 |  | Wed 8/30/23
1707 | 272 | 2.1 | Building 272 Water Conservation Installation | 95% |  | Fri 8/25/23 |  | Fri 8/25/23
1708 | 272 | 2.1 | Building 272 Water Conservation Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1709 | 272 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 10/18/23 |  | Wed 10/25/23
1710 | 272 | 3.2 | Building 272 Mechanical Insulation Installation | 0% |  | Wed 10/18/23 |  | Wed 10/18/23
1711 | 272 | 3.2 | Building 272 Mechanical Insulation Acceptance | 0% |  | Wed 10/25/23 |  | Wed 10/25/23
1712 | 272 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 1/9/24 |  | Thu 1/18/24
1713 | 272 | 3.1 | Building 272 Steam Trap Replacement Installation | 0% |  | Tue 1/9/24 |  | Thu 1/11/24
1714 | 272 | 3.1 | Building 272 Steam Trap Replacement Acceptance | 0% |  | Thu 1/18/24 |  | Thu 1/18/24
1715 | 272 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Wed 11/22/23 |  | Sat 12/9/23
1716 | 272 | 4.1 | Building 272 Seal HVAC Ductwork Installation | 0% |  | Wed 11/22/23 |  | Mon 12/4/23
1717 | 272 | 4.1 | Building 272 Seal HVAC Ductwork Acceptance | 0% |  | Sat 12/9/23 |  | Sat 12/9/23
1718 | 272 | 9 | FIM 9.0 Lab Controls | 0% |  | Fri 5/3/24 |  | Tue 8/27/24
1719 | 272 | 9 | Building 272 Lab Controls Installation | 0% |  | Fri 5/3/24 |  | Tue 8/20/24
1720 | 272 | 9 | Building 272 Lab Controls Acceptance | 0% |  | Tue 8/27/24 |  | Tue 8/27/24
1721 | 35 |  | Building 35 Kinard Lab Installation | 22% |  | Mon 8/14/23 |  | Fri 9/27/24
1722 | 35 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Fri 9/29/23 |  | Tue 10/10/23
1723 | 35 | 6.1 | Building 35 Building Envelope Installation | 99% | 99% | Fri 9/29/23 | 2023-09-29 | Tue 10/3/23 | 2023-10-03
1724 | 35 | 6.1 | Building 35 Building Envelope Acceptance | 0% |  | Tue 10/10/23 |  | Tue 10/10/23
1725 | 35 | 8 | FIM 8.0 Controls Improvement | 99% |  | Fri 9/8/23 |  | Wed 10/11/23
1726 | 35 | 8 | Building 35 Controls Improvement Installation | 99% | 99% | Fri 9/8/23 | 2023-09-08 | Wed 10/4/23 | 2023-10-06
1727 | 35 | 8 | Building 35 Controls Improvement Acceptance | 0% |  | Wed 10/11/23 |  | Wed 10/11/23
1728 | 35 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 10/9/23 |  | Fri 11/10/23
1729 | 35 | 1.1 | Building 35 Interior Lighting and Controls Installation | 0% | 95% | Mon 10/9/23 | 2023-10-19 | Fri 11/3/23 | 2023-11-01
1730 | 35 | 1.1 | Building 35 Interior Lighting and Controls Acceptance | 0% |  | Fri 11/10/23 |  | Fri 11/10/23
1731 | 35 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Mon 10/9/23 |  | Fri 11/10/23
1732 | 35 | 1.2 | Building 35 Exterior Lighting and Controls Installation | 0% | 95% | Mon 10/9/23 | 2023-10-19 | Fri 11/3/23 | 2023-11-01
1733 | 35 | 1.2 | Building 35 Exterior Lighting and Controls Acceptance | 0% |  | Fri 11/10/23 |  | Fri 11/10/23
1734 | 35 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
1735 | 35 | 2.1 | Building 35 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
1736 | 35 | 2.1 | Building 35 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1737 | 35 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 10/19/23 |  | Thu 10/26/23
1738 | 35 | 3.2 | Building 35 Mechanical Insulation Installation | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
1739 | 35 | 3.2 | Building 35 Mechanical Insulation Acceptance | 0% |  | Thu 10/26/23 |  | Thu 10/26/23
1740 | 35 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 1/12/24 |  | Tue 1/23/24
1741 | 35 | 3.1 | Building 35 Steam Trap Replacement Installation | 0% |  | Fri 1/12/24 |  | Tue 1/16/24
1742 | 35 | 3.1 | Building 35 Steam Trap Replacement Acceptance | 0% |  | Tue 1/23/24 |  | Tue 1/23/24
1743 | 35 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Tue 12/5/23 |  | Fri 12/15/23
1744 | 35 | 4.1 | Building 35 Seal HVAC Ductwork Installation | 0% |  | Tue 12/5/23 |  | Sat 12/9/23
1745 | 35 | 4.1 | Building 35 Seal HVAC Ductwork Acceptance | 0% |  | Fri 12/15/23 |  | Fri 12/15/23
1746 | 35 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 4/18/24 |  | Wed 5/22/24
1747 | 35 | 5.1 | Building 35 Retro Cx Installation | 0% |  | Thu 4/18/24 |  | Wed 5/15/24
1748 | 35 | 5.1 | Building 35 Retro Cx Acceptance | 0% |  | Wed 5/22/24 |  | Wed 5/22/24
1749 | 35 | 9 | FIM 9.0 Lab Controls | 0% |  | Wed 8/21/24 |  | Fri 9/27/24
1750 | 35 | 9 | Building 35 Lab Controls Installation | 0% |  | Wed 8/21/24 |  | Fri 9/20/24
1751 | 35 | 9 | Building 35 Lab Controls Acceptance | 0% |  | Fri 9/27/24 |  | Fri 9/27/24
1752 | 382 |  | Building 382 Vickery Academic Learning Center Installation | 5% |  | Thu 8/17/23 |  | Mon 8/19/24
1753 | 382 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/17/23 |  | Tue 8/22/23
1754 | 382 | 6.1 | Building 382 Building Envelope Installation | 0% | 99% | Thu 8/17/23 | 2023-10-11 | Thu 8/17/23 | 2023-10-13
1755 | 382 | 6.1 | Building 382 Building Envelope Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
1756 | 382 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 11/6/23 |  | Wed 11/15/23
1757 | 382 | 1.1 | Building 382 Interior Lighting and Controls Installation | 0% |  | Mon 11/6/23 |  | Wed 11/8/23
1758 | 382 | 1.1 | Building 382 Interior Lighting and Controls Acceptance | 0% |  | Wed 11/15/23 |  | Wed 11/15/23
1759 | 382 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Wed 11/8/23 |  | Wed 11/15/23
1760 | 382 | 1.2 | Building 382 Exterior Lighting and Controls Installation | 0% |  | Wed 11/8/23 |  | Wed 11/8/23
1761 | 382 | 1.2 | Building 382 Exterior Lighting and Controls Acceptance | 0% |  | Wed 11/15/23 |  | Wed 11/15/23
1762 | 382 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Tue 8/6/24 |  | Mon 8/19/24
1763 | 382 | 8.2 | Building 382 Control Optimization MDMP/MRR Installation | 0% |  | Tue 8/6/24 |  | Mon 8/12/24
1764 | 382 | 8.2 | Building 382 Control Optimization MDMP/MRR Acceptance | 0% |  | Mon 8/19/24 |  | Mon 8/19/24
1765 | 382 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/18/23 |  | Wed 8/23/23
1766 | 382 | 2.1 | Building 382 Water Conservation Installation | 95% |  | Fri 8/18/23 |  | Fri 8/18/23
1767 | 382 | 2.1 | Building 382 Water Conservation Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
1768 | 382 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 10/20/23 |  | Fri 10/27/23
1769 | 382 | 3.2 | Building 382 Mechanical Insulation Installation | 0% |  | Fri 10/20/23 |  | Fri 10/20/23
1770 | 382 | 3.2 | Building 382 Mechanical Insulation Acceptance | 0% |  | Fri 10/27/23 |  | Fri 10/27/23
1771 | 382 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 1/17/24 |  | Fri 1/26/24
1772 | 382 | 3.1 | Building 382 Steam Trap Replacement Installation | 0% |  | Wed 1/17/24 |  | Fri 1/19/24
1773 | 382 | 3.1 | Building 382 Steam Trap Replacement Acceptance | 0% |  | Fri 1/26/24 |  | Fri 1/26/24
1774 | 382 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Mon 12/11/23 |  | Thu 12/21/23
1775 | 382 | 4.1 | Building 382 Seal HVAC Ductwork Installation | 0% |  | Mon 12/11/23 |  | Thu 12/14/23
1776 | 382 | 4.1 | Building 382 Seal HVAC Ductwork Acceptance | 0% |  | Thu 12/21/23 |  | Thu 12/21/23
1777 | 232A |  | Building 232A Rhodes Hall Annex Installation | 21% |  | Mon 6/12/23 |  | Fri 6/7/24
1778 | 232A | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
1779 | 232A | 6.1 | Building 232A Building Envelope Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
1780 | 232A | 6.1 | Building 232A Building Envelope Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1781 | 232A | 8 | FIM 8.0 Controls Improvement | 95% |  | Thu 6/15/23 |  | Mon 7/3/23
1782 | 232A | 8 | Building 232A Controls Improvement Installation | 95% |  | Thu 6/15/23 |  | Thu 9/14/23
1783 | 232A | 8 | Building 232A Controls Improvement Acceptance | 0% |  | Thu 9/21/23 |  | Thu 9/21/23
1784 | 232A | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 8/21/23 |  | Tue 8/29/23
1785 | 232A | 1.1 | Building 232A Interior Lighting and Controls Installation | 99% |  | Mon 8/21/23 |  | Thu 8/24/23
1786 | 232A | 1.1 | Building 232A Interior Lighting and Controls Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1787 | 232A | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 8/21/23 |  | Tue 8/29/23
1788 | 232A | 1.2 | Building 232A Exterior Lighting and Controls Installation | 99% |  | Mon 8/21/23 |  | Thu 8/24/23
1789 | 232A | 1.2 | Building 232A Exterior Lighting and Controls Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1790 | 232A | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 9/7/23 |  | Wed 9/13/23
1791 | 232A | 2.1 | Building 232A Water Conservation Installation | 95% |  | Thu 9/7/23 |  | Thu 9/7/23
1792 | 232A | 2.1 | Building 232A Water Conservation Acceptance | 0% |  | Wed 9/13/23 |  | Wed 9/13/23
1793 | 232A | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Fri 12/15/23 |  | Wed 12/27/23
1794 | 232A | 4.1 | Building 232A Seal HVAC Ductwork Installation | 0% |  | Fri 12/15/23 |  | Wed 12/20/23
1795 | 232A | 4.1 | Building 232A Seal HVAC Ductwork Acceptance | 0% |  | Wed 12/27/23 |  | Wed 12/27/23
1796 | 232A | 5.1 | FIM 5.1 Retro Cx | 0% |  | Thu 5/16/24 |  | Fri 6/7/24
1797 | 232A | 5.1 | Building 232A Retro Cx Installation | 0% |  | Thu 5/16/24 |  | Fri 5/31/24
1798 | 232A | 5.1 | Building 232A Retro Cx Acceptance | 0% |  | Fri 6/7/24 |  | Fri 6/7/24
1799 | 232A | 9 | FIM 9.0 Lab Controls | 0% |  | Mon 6/12/23 |  | Sat 8/12/23
1800 | 232A | 9 | Building 232A Lab Controls Installation | 0% |  | Mon 6/12/23 |  | Mon 8/7/23
1801 | 232A | 9 | Building 232A Lab Controls Acceptance | 0% |  | Sat 8/12/23 |  | Sat 8/12/23
1802 | 223 |  | Building 223 Schilletter Dining Hall Installation | 11% |  | Thu 7/6/23 |  | Fri 4/12/24
1803 | 223 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Thu 7/6/23 |  | Thu 7/13/23
1804 | 223 | 6.1 | Building 223 Building Envelope Installation | 95% |  | Thu 7/6/23 |  | Thu 7/6/23
1805 | 223 | 6.1 | Building 223 Building Envelope Acceptance | 0% |  | Thu 7/13/23 |  | Thu 7/13/23
1806 | 223 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Fri 8/25/23 |  | Wed 8/30/23
1807 | 223 | 1.1 | Building 223 Interior Lighting and Controls Installation | 0% |  | Fri 8/25/23 |  | Fri 8/25/23
1808 | 223 | 1.1 | Building 223 Interior Lighting and Controls Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1809 | 223 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Sun 8/27/23 |  | Fri 9/1/23
1810 | 223 | 1.2 | Building 223 Exterior Lighting and Controls Installation | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
1811 | 223 | 1.2 | Building 223 Exterior Lighting and Controls Acceptance | 0% |  | Fri 9/1/23 |  | Fri 9/1/23
1812 | 223 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/1/23 |  | Tue 8/8/23
1813 | 223 | 2.1 | Building 223 Water Conservation Installation | 95% |  | Tue 8/1/23 |  | Tue 8/1/23
1814 | 223 | 2.1 | Building 223 Water Conservation Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
1815 | 223 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 10/23/23 |  | Mon 10/30/23
1816 | 223 | 3.2 | Building 223 Mechanical Insulation Installation | 0% |  | Mon 10/23/23 |  | Mon 10/23/23
1817 | 223 | 3.2 | Building 223 Mechanical Insulation Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
1818 | 223 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 1/22/24 |  | Wed 1/31/24
1819 | 223 | 3.1 | Building 223 Steam Trap Replacement Installation | 0% |  | Mon 1/22/24 |  | Wed 1/24/24
1820 | 223 | 3.1 | Building 223 Steam Trap Replacement Acceptance | 0% |  | Wed 1/31/24 |  | Wed 1/31/24
1821 | 223 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Thu 12/21/23 |  | Wed 1/3/24
1822 | 223 | 4.1 | Building 223 Seal HVAC Ductwork Installation | 0% |  | Thu 12/21/23 |  | Wed 12/27/23
1823 | 223 | 4.1 | Building 223 Seal HVAC Ductwork Acceptance | 0% |  | Wed 1/3/24 |  | Wed 1/3/24
1824 | 223 | 8.1 | FIM 8.1 Kitchen Hood Controls or Upgrades | 0% |  | Mon 4/1/24 |  | Fri 4/12/24
1825 | 223 | 8.1 | Building 223 Kitchen Hood Controls or Upgrades | 0% |  | Mon 4/1/24 |  | Fri 4/5/24
1826 | 223 | 8.1 | Building 223 Kitchen Hood Controls or Upgrades | 0% |  | Fri 4/12/24 |  | Fri 4/12/24
1827 | 1227 |  | Building 1227 Hendrix Student Center Installation | 30% |  | Thu 7/13/23 |  | Fri 7/5/24
1828 | 1227 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 3/28/24 |  | Tue 4/9/24
1829 | 1227 | 6.1 | Building 1227 Building Envelope Installation | 0% | 99% | Thu 3/28/24 | 2023-10-04 | Tue 4/2/24 | 2023-10-04
1830 | 1227 | 6.1 | Building 1227 Building Envelope Acceptance | 0% |  | Tue 4/9/24 |  | Tue 4/9/24
1831 | 1227 | 8 | FIM 8.0 Controls Improvement | 95% |  | Thu 7/13/23 |  | Tue 8/29/23
1832 | 1227 | 8 | Building 1227 Controls Improvement Installation | 95% |  | Thu 7/13/23 |  | Thu 8/24/23
1833 | 1227 | 8 | Building 1227 Controls Improvement Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1834 | 1227 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 9/26/23 |  | Tue 10/31/23
1835 | 1227 | 1.1 | Building 1227 Interior Lighting and Controls Installation | 0% | 99% | Tue 9/26/23 | 2023-10-10 | Tue 10/24/23 | 2023-10-18
1836 | 1227 | 1.1 | Building 1227 Interior Lighting and Controls Acceptance | 0% |  | Tue 10/31/23 |  | Tue 10/31/23
1837 | 1227 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Tue 9/26/23 |  | Tue 10/31/23
1838 | 1227 | 1.2 | Building 1227 Exterior Lighting and Controls Installation | 0% | 99% | Tue 9/26/23 | 2023-10-10 | Tue 10/24/23 | 2023-10-18
1839 | 1227 | 1.2 | Building 1227 Exterior Lighting and Controls Acceptance | 0% |  | Tue 10/31/23 |  | Tue 10/31/23
1840 | 1227 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/22/23 |  | Sun 8/27/23
1841 | 1227 | 2.1 | Building 1227 Water Conservation Installation | 95% |  | Tue 8/22/23 |  | Tue 8/22/23
1842 | 1227 | 2.1 | Building 1227 Water Conservation Acceptance | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
1843 | 1227 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 10/24/23 |  | Tue 10/31/23
1844 | 1227 | 3.2 | Building 1227 Mechanical Insulation Installation | 0% |  | Tue 10/24/23 |  | Tue 10/24/23
1845 | 1227 | 3.2 | Building 1227 Mechanical Insulation Acceptance | 0% |  | Tue 10/31/23 |  | Tue 10/31/23
1846 | 1227 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 1/25/24 |  | Mon 2/5/24
1847 | 1227 | 3.1 | Building 1227 Steam Trap Replacement Installation | 0% |  | Thu 1/25/24 |  | Mon 1/29/24
1848 | 1227 | 3.1 | Building 1227 Steam Trap Replacement Acceptance | 0% |  | Mon 2/5/24 |  | Mon 2/5/24
1849 | 1227 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Thu 12/28/23 |  | Mon 1/15/24
1850 | 1227 | 4.1 | Building 1227 Seal HVAC Ductwork Installation | 0% |  | Thu 12/28/23 |  | Mon 1/8/24
1851 | 1227 | 4.1 | Building 1227 Seal HVAC Ductwork Acceptance | 0% |  | Mon 1/15/24 |  | Mon 1/15/24
1852 | 1227 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Mon 6/3/24 |  | Fri 7/5/24
1853 | 1227 | 5.1 | Building 1227 Retro Cx Installation | 0% |  | Mon 6/3/24 |  | Fri 6/28/24
1854 | 1227 | 5.1 | Building 1227 Retro Cx Acceptance | 0% |  | Fri 7/5/24 |  | Fri 7/5/24
1855 | 1168 |  | Building 1168 Lebanon Road Installation | 14% |  | Tue 8/15/23 |  | Fri 5/17/24
1856 | 1168 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Mon 3/25/24 |  | Wed 4/3/24
1857 | 1168 | 6.1 | Building 1168 Building Envelope Installation | 0% | 99% | Mon 3/25/24 | 2023-10-04 | Wed 3/27/24 | 2023-10-04
1858 | 1168 | 6.1 | Building 1168 Building Envelope Acceptance | 0% |  | Wed 4/3/24 |  | Wed 4/3/24
1859 | 1168 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 1/8/24 |  | Wed 1/17/24
1860 | 1168 | 1.1 | Building 1168 Interior Lighting and Controls Installation | 0% |  | Mon 1/8/24 |  | Wed 1/10/24
1861 | 1168 | 1.1 | Building 1168 Interior Lighting and Controls Acceptance | 0% |  | Wed 1/17/24 |  | Wed 1/17/24
1862 | 1168 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/15/23 |  | Wed 9/6/23
1863 | 1168 | 2.1 | Building 1168 Water Conservation Installation | 95% |  | Tue 8/15/23 |  | Wed 8/30/23
1864 | 1168 | 2.1 | Building 1168 Water Conservation Acceptance | 0% |  | Wed 9/6/23 |  | Wed 9/6/23
1865 | 1168 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Mon 1/8/24 |  | Fri 5/17/24
1866 | 1168 | 10 | Building 1168 HVAC Upgrades Installation | 0% |  | Mon 1/8/24 |  | Fri 5/10/24
1867 | 1168 | 10 | Building 1168 HVAC Upgrades Acceptance | 0% |  | Fri 5/17/24 |  | Fri 5/17/24
1868 | 1178 |  | Building 1178 Westinghouse Road, 509 Installation | 1% |  | Mon 8/28/23 |  | Fri 9/20/24
1869 | 1178 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 1/8/24 |  | Wed 1/17/24
1870 | 1178 | 1.1 | Building 1178 Interior Lighting and Controls Installation | 0% |  | Mon 1/8/24 |  | Wed 1/10/24
1871 | 1178 | 1.1 | Building 1178 Interior Lighting and Controls Acceptance | 0% |  | Wed 1/17/24 |  | Wed 1/17/24
1872 | 1178 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Mon 1/8/24 |  | Mon 1/15/24
1873 | 1178 | 1.2 | Building 1178 Exterior Lighting and Controls Installation | 0% |  | Mon 1/8/24 |  | Mon 1/8/24
1874 | 1178 | 1.2 | Building 1178 Exterior Lighting and Controls Acceptance | 0% |  | Mon 1/15/24 |  | Mon 1/15/24
1875 | 1178 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/28/23 |  | Mon 9/4/23
1876 | 1178 | 2.1 | Building 1178 Water Conservation Installation | 95% |  | Mon 8/28/23 |  | Mon 8/28/23
1877 | 1178 | 2.1 | Building 1178 Water Conservation Acceptance | 0% |  | Mon 9/4/23 |  | Mon 9/4/23
1878 | 1178 | 10 | FIM 10.0 HVAC Upgrades | 0% |  | Mon 5/13/24 |  | Fri 9/20/24
1879 | 1178 | 10 | Building 1178 HVAC Upgrades Installation | 0% |  | Mon 5/13/24 |  | Fri 9/13/24
1880 | 1178 | 10 | Building 1178 HVAC Upgrades Acceptance | 0% |  | Fri 9/20/24 |  | Fri 9/20/24
1881 | 10 |  | Building 10 Fike Recreation Center Installation | 53% |  | Tue 7/11/23 |  | Thu 2/8/24
1882 | 10 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 8/16/23 |  | Wed 9/13/23
1883 | 10 | 6.1 | Building 10 Building Envelope Installation | 95% |  | Wed 8/16/23 |  | Thu 9/7/23
1884 | 10 | 6.1 | Building 10 Building Envelope Acceptance | 0% |  | Wed 9/13/23 |  | Wed 9/13/23
1885 | 10 | 8 | FIM 8.0 Controls Improvement | 95% |  | Tue 7/11/23 |  | Tue 8/29/23
1886 | 10 | 8 | Building 10 Controls Improvement Installation | 95% |  | Tue 7/11/23 |  | Thu 8/24/23
1887 | 10 | 8 | Building 10 Controls Improvement Acceptance | 0% |  | Tue 8/29/23 |  | Tue 8/29/23
1888 | 10 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Thu 9/28/23 |  | Fri 10/27/23
1889 | 10 | 1.1 | Building 10 Interior Lighting and Controls Installation | 0% | 99% | Thu 9/28/23 | 2023-10-04 | Fri 10/20/23 | 2023-10-20
1890 | 10 | 1.1 | Building 10 Interior Lighting and Controls Acceptance | 0% |  | Fri 10/27/23 |  | Fri 10/27/23
1891 | 10 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 9/28/23 |  | Fri 10/27/23
1892 | 10 | 1.2 | Building 10 Exterior Lighting and Controls Installation | 0% | 99% | Thu 9/28/23 | 2023-10-04 | Fri 10/20/23 | 2023-10-20
1893 | 10 | 1.2 | Building 10 Exterior Lighting and Controls Acceptance | 0% |  | Fri 10/27/23 |  | Fri 10/27/23
1894 | 10 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
1895 | 10 | 2.1 | Building 10 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
1896 | 10 | 2.1 | Building 10 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
1897 | 10 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 10/25/23 |  | Wed 11/1/23
1898 | 10 | 3.2 | Building 10 Mechanical Insulation Installation | 0% |  | Wed 10/25/23 |  | Wed 10/25/23
1899 | 10 | 3.2 | Building 10 Mechanical Insulation Acceptance | 0% |  | Wed 11/1/23 |  | Wed 11/1/23
1900 | 10 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 1/30/24 |  | Thu 2/8/24
1901 | 10 | 3.1 | Building 10 Steam Trap Replacement Installation | 0% |  | Tue 1/30/24 |  | Thu 2/1/24
1902 | 10 | 3.1 | Building 10 Steam Trap Replacement Acceptance | 0% |  | Thu 2/8/24 |  | Thu 2/8/24
1903 | 10 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Tue 1/9/24 |  | Tue 1/23/24
1904 | 10 | 4.1 | Building 10 Seal HVAC Ductwork Installation | 0% |  | Tue 1/9/24 |  | Tue 1/16/24
1905 | 10 | 4.1 | Building 10 Seal HVAC Ductwork Acceptance | 0% |  | Tue 1/23/24 |  | Tue 1/23/24
1906 | 10 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Fri 9/22/23 |  | Sun 10/1/23
1907 | 10 | 3.3 | Building 10 Condensate Receiver Repair Installation | 0% |  | Fri 9/22/23 |  | Mon 9/25/23
1908 | 10 | 3.3 | Building 10 Condensate Receiver Repair Acceptance | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
1909 | 50 |  | Building 50 Barnes Student Activity Center Installation | 48% |  | Thu 8/17/23 |  | Mon 10/30/23
1910 | 50 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Mon 10/23/23 |  | Mon 10/30/23
1911 | 50 | 1.2 | Building 50 Exterior Lighting and Controls Installation | 0% |  | Mon 10/23/23 |  | Mon 10/23/23
1912 | 50 | 1.2 | Building 50 Exterior Lighting and Controls Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
1913 | 50 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/17/23 |  | Tue 8/22/23
1914 | 50 | 2.1 | Building 50 Water Conservation Installation | 95% |  | Thu 8/17/23 |  | Thu 8/17/23
1915 | 50 | 2.1 | Building 50 Water Conservation Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
1916 | 446 |  | Building 446 Child Development Center Installation | 95% |  | Wed 8/9/23 |  | Thu 9/14/23
1917 | 446 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Fri 9/8/23 |  | Thu 9/14/23
1918 | 446 | 6.1 | Building 446 Building Envelope Installation | 99% |  | Fri 9/8/23 |  | Fri 9/8/23
1919 | 446 | 6.1 | Building 446 Building Envelope Acceptance | 0% |  | Thu 9/14/23 |  | Thu 9/14/23
1920 | 446 | 8 | FIM 8.0 Controls Improvement | 95% |  | Wed 8/9/23 |  | Sun 8/20/23
1921 | 446 | 8 | Building 446 Controls Improvement Installation | 95% | 99% | Wed 8/9/23 | 2023-08-09 | Tue 8/15/23 | 2023-10-06
1922 | 446 | 8 | Building 446 Controls Improvement Acceptance | 0% |  | Sun 8/20/23 |  | Sun 8/20/23
1923 | 446 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
1924 | 446 | 2.1 | Building 446 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
1925 | 446 | 2.1 | Building 446 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1926 | 1263 |  | Building 1263 Clemson Textiles Installation | 0% |  | Tue 7/18/23 |  | Wed 11/1/23
1927 | 1263 | 8 | FIM 8.0 Controls Improvement | 0% |  | Tue 7/18/23 |  | Tue 8/1/23
1928 | 1263 | 8 | Building 1263 Controls Improvement Installation | 0% |  | Tue 7/18/23 |  | Wed 7/26/23
1929 | 1263 | 8 | Building 1263 Controls Improvement Acceptance | 0% |  | Tue 8/1/23 |  | Tue 8/1/23
1930 | 1263 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 10/23/23 |  | Mon 10/30/23
1931 | 1263 | 1.1 | Building 1263 Interior Lighting and Controls Installation | 0% |  | Mon 10/23/23 |  | Mon 10/23/23
1932 | 1263 | 1.1 | Building 1263 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
1933 | 1263 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Wed 10/25/23 |  | Wed 11/1/23
1934 | 1263 | 1.2 | Building 1263 Exterior Lighting and Controls Installation | 0% |  | Wed 10/25/23 |  | Wed 10/25/23
1935 | 1263 | 1.2 | Building 1263 Exterior Lighting and Controls Acceptance | 0% |  | Wed 11/1/23 |  | Wed 11/1/23
1936 | 318 |  | Building 318 Administrative Services Building (ASB) Installation | 96% |  | Wed 5/3/23 |  | Fri 9/8/23
1937 | 318 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Fri 9/1/23 |  | Fri 9/8/23
1938 | 318 | 6.1 | Building 318 Building Envelope Installation | 99% |  | Fri 9/1/23 |  | Fri 9/1/23
1939 | 318 | 6.1 | Building 318 Building Envelope Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
1940 | 318 | 8 | FIM 8.0 Controls Improvement | 95% |  | Tue 8/1/23 |  | Wed 8/23/23
1941 | 318 | 8 | Building 318 Controls Improvement Installation | 95% |  | Tue 8/1/23 |  | Fri 8/18/23
1942 | 318 | 8 | Building 318 Controls Improvement Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
1943 | 318 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 5/3/23 |  | Fri 5/12/23
1944 | 318 | 1.1 | Building 318 Interior Lighting and Controls Installation | 100% |  | Wed 5/3/23 |  | Fri 5/5/23
1945 | 318 | 1.1 | Building 318 Interior Lighting and Controls Acceptance | 0% |  | Fri 5/12/23 |  | Fri 5/12/23
1946 | 318 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 5/3/23 |  | Wed 5/10/23
1947 | 318 | 1.2 | Building 318 Exterior Lighting and Controls Installation | 100% |  | Wed 5/3/23 |  | Wed 5/3/23
1948 | 318 | 1.2 | Building 318 Exterior Lighting and Controls Acceptance | 0% |  | Wed 5/10/23 |  | Wed 5/10/23
1949 | 318 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Mon 8/21/23
1950 | 318 | 2.1 | Building 318 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/16/23
1951 | 318 | 2.1 | Building 318 Water Conservation Acceptance | 0% |  | Mon 8/21/23 |  | Mon 8/21/23
1952 | 212 |  | Building 212 Cooper Library Installation | 42% |  | Tue 8/1/23 |  | Fri 8/2/24
1953 | 212 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Fri 8/11/23 |  | Wed 8/16/23
1954 | 212 | 6.1 | Building 212 Building Envelope Installation | 95% |  | Fri 8/11/23 |  | Fri 8/11/23
1955 | 212 | 6.1 | Building 212 Building Envelope Acceptance | 0% |  | Wed 8/16/23 |  | Wed 8/16/23
1956 | 212 | 8 | FIM 8.0 Controls Improvement | 95% |  | Tue 8/1/23 |  | Wed 8/30/23
1957 | 212 | 8 | Building 212 Controls Improvement Installation | 95% |  | Tue 8/1/23 |  | Fri 8/25/23
1958 | 212 | 8 | Building 212 Controls Improvement Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
1959 | 212 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Sat 8/19/23 |  | Thu 8/24/23
1960 | 212 | 2.1 | Building 212 Water Conservation Installation | 95% |  | Sat 8/19/23 |  | Sat 8/19/23
1961 | 212 | 2.1 | Building 212 Water Conservation Acceptance | 0% |  | Thu 8/24/23 |  | Thu 8/24/23
1962 | 212 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 10/26/23 |  | Thu 11/2/23
1963 | 212 | 3.2 | Building 212 Mechanical Insulation Installation | 0% |  | Thu 10/26/23 |  | Thu 10/26/23
1964 | 212 | 3.2 | Building 212 Mechanical Insulation Acceptance | 0% |  | Thu 11/2/23 |  | Thu 11/2/23
1965 | 212 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 2/2/24 |  | Tue 2/13/24
1966 | 212 | 3.1 | Building 212 Steam Trap Replacement Installation | 0% |  | Fri 2/2/24 |  | Tue 2/6/24
1967 | 212 | 3.1 | Building 212 Steam Trap Replacement Acceptance | 0% |  | Tue 2/13/24 |  | Tue 2/13/24
1968 | 212 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Wed 1/17/24 |  | Thu 2/1/24
1969 | 212 | 4.1 | Building 212 Seal HVAC Ductwork Installation | 0% |  | Wed 1/17/24 |  | Thu 1/25/24
1970 | 212 | 4.1 | Building 212 Seal HVAC Ductwork Acceptance | 0% |  | Thu 2/1/24 |  | Thu 2/1/24
1971 | 212 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Mon 7/1/24 |  | Fri 8/2/24
1972 | 212 | 5.1 | Building 212 Retro Cx Installation | 0% |  | Mon 7/1/24 |  | Fri 7/26/24
1973 | 212 | 5.1 | Building 212 Retro Cx Acceptance | 0% |  | Fri 8/2/24 |  | Fri 8/2/24
1974 | 1283 |  | Building 1283 Watt Family Innovation Center Installation | 55% |  | Mon 8/28/23 |  | Fri 2/16/24
1975 | 1283 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Mon 8/28/23 |  | Fri 9/8/23
1976 | 1283 | 6.1 | Building 1283 Building Envelope Installation | 99% |  | Mon 8/28/23 |  | Fri 9/1/23
1977 | 1283 | 6.1 | Building 1283 Building Envelope Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
1978 | 1283 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 10/27/23 |  | Fri 11/3/23
1979 | 1283 | 3.2 | Building 1283 Mechanical Insulation Installation | 0% |  | Fri 10/27/23 |  | Fri 10/27/23
1980 | 1283 | 3.2 | Building 1283 Mechanical Insulation Acceptance | 0% |  | Fri 11/3/23 |  | Fri 11/3/23
1981 | 1283 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 2/7/24 |  | Fri 2/16/24
1982 | 1283 | 3.1 | Building 1283 Steam Trap Replacement Installation | 0% |  | Wed 2/7/24 |  | Fri 2/9/24
1983 | 1283 | 3.1 | Building 1283 Steam Trap Replacement Acceptance | 0% |  | Fri 2/16/24 |  | Fri 2/16/24
1984 | 1308 |  | Building 1308 Deschamps Hall Installation | 24% |  | Thu 8/3/23 |  | Wed 2/21/24
1985 | 1308 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/3/23 |  | Thu 8/10/23
1986 | 1308 | 2.1 | Building 1308 Water Conservation Installation | 95% |  | Thu 8/3/23 |  | Thu 8/3/23
1987 | 1308 | 2.1 | Building 1308 Water Conservation Acceptance | 0% |  | Thu 8/10/23 |  | Thu 8/10/23
1988 | 1308 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 2/12/24 |  | Wed 2/21/24
1989 | 1308 | 3.1 | Building 1308 Steam Trap Replacement Installation | 0% |  | Mon 2/12/24 |  | Wed 2/14/24
1990 | 1308 | 3.1 | Building 1308 Steam Trap Replacement Acceptance | 0% |  | Wed 2/21/24 |  | Wed 2/21/24
1991 | 1284 |  | Building 1284 Gressette Hall Installation | 19% |  | Thu 7/13/23 |  | Thu 4/18/24
1992 | 1284 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Thu 7/13/23 |  | Wed 7/19/23
1993 | 1284 | 6.1 | Building 1284 Building Envelope Installation | 95% |  | Thu 7/13/23 |  | Thu 7/13/23
1994 | 1284 | 6.1 | Building 1284 Building Envelope Acceptance | 0% |  | Wed 7/19/23 |  | Wed 7/19/23
1995 | 1284 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/1/23 |  | Tue 8/8/23
1996 | 1284 | 2.1 | Building 1284 Water Conservation Installation | 95% |  | Tue 8/1/23 |  | Tue 8/1/23
1997 | 1284 | 2.1 | Building 1284 Water Conservation Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
1998 | 1284 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 10/30/23 |  | Mon 11/6/23
1999 | 1284 | 3.2 | Building 1284 Mechanical Insulation Installation | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
2000 | 1284 | 3.2 | Building 1284 Mechanical Insulation Acceptance | 0% |  | Mon 11/6/23 |  | Mon 11/6/23
2001 | 1284 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 2/15/24 |  | Mon 2/26/24
2002 | 1284 | 3.1 | Building 1284 Steam Trap Replacement Installation | 0% |  | Thu 2/15/24 |  | Mon 2/19/24
2003 | 1284 | 3.1 | Building 1284 Steam Trap Replacement Acceptance | 0% |  | Mon 2/26/24 |  | Mon 2/26/24
2004 | 1284 | 8.1 | FIM 8.1 Kitchen Hood Controls or Upgrades | 0% |  | Mon 4/8/24 |  | Thu 4/18/24
2005 | 1284 | 8.1 | Building 1284 Kitchen Hood Controls or Upgrades Installation | 0% |  | Mon 4/8/24 |  | Thu 4/11/24
2006 | 1284 | 8.1 | Building 1284 Kitchen Hood Controls or Upgrades Acceptance | 0% |  | Thu 4/18/24 |  | Thu 4/18/24
2007 | 2023 |  | Building 2023 Holmes Hall Installation | 57% |  | Wed 7/26/23 |  | Thu 2/29/24
2008 | 2023 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Fri 7/28/23 |  | Sat 8/12/23
2009 | 2023 | 6.1 | Building 2023 Building Envelope Installation | 95% |  | Fri 7/28/23 |  | Mon 8/7/23
2010 | 2023 | 6.1 | Building 2023 Building Envelope Acceptance | 0% |  | Sat 8/12/23 |  | Sat 8/12/23
2011 | 2023 | 1.1 | FIM 1.1 Interior Lighting and Controls | 80% |  | Wed 7/26/23 |  | Mon 8/7/23
2012 | 2023 | 1.1 | Building 2023 Interior Lighting and Controls Installation | 80% |  | Wed 7/26/23 |  | Mon 7/31/23
2013 | 2023 | 1.1 | Building 2023 Interior Lighting and Controls Acceptance | 0% |  | Mon 8/7/23 |  | Mon 8/7/23
2014 | 2023 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 5% |  | Wed 7/26/23 |  | Mon 8/7/23
2015 | 2023 | 1.2 | Building 2023 Exterior Lighting and Controls Installation | 5% |  | Wed 7/26/23 |  | Mon 7/31/23
2016 | 2023 | 1.2 | Building 2023 Exterior Lighting and Controls Acceptance | 0% |  | Mon 8/7/23 |  | Mon 8/7/23
2017 | 2023 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/7/23 |  | Sun 8/13/23
2018 | 2023 | 2.1 | Building 2023 Water Conservation Installation | 95% |  | Mon 8/7/23 |  | Tue 8/8/23
2019 | 2023 | 2.1 | Building 2023 Water Conservation Acceptance | 0% |  | Sun 8/13/23 |  | Sun 8/13/23
2020 | 2023 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 10/31/23 |  | Tue 11/7/23
2021 | 2023 | 3.2 | Building 2023 Mechanical Insulation Installation | 0% |  | Tue 10/31/23 |  | Tue 10/31/23
2022 | 2023 | 3.2 | Building 2023 Mechanical Insulation Acceptance | 0% |  | Tue 11/7/23 |  | Tue 11/7/23
2023 | 2023 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 2/20/24 |  | Thu 2/29/24
2024 | 2023 | 3.1 | Building 2023 Steam Trap Replacement Installation | 0% |  | Tue 2/20/24 |  | Thu 2/22/24
2025 | 2023 | 3.1 | Building 2023 Steam Trap Replacement Acceptance | 0% |  | Thu 2/29/24 |  | Thu 2/29/24
2026 | 2022 |  | Building 2022 Mccabe Hall Installation | 74% |  | Wed 7/5/23 |  | Tue 3/5/24
2027 | 2022 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 7/5/23 |  | Fri 7/14/23
2028 | 2022 | 6.1 | Building 2022 Building Envelope Installation | 95% |  | Wed 7/5/23 |  | Sat 7/8/23
2029 | 2022 | 6.1 | Building 2022 Building Envelope Acceptance | 0% |  | Fri 7/14/23 |  | Fri 7/14/23
2030 | 2022 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Wed 7/5/23 |  | Sat 7/15/23
2031 | 2022 | 1.1 | Building 2022 Interior Lighting and Controls Installation | 100% |  | Wed 7/5/23 |  | Mon 7/10/23
2032 | 2022 | 1.1 | Building 2022 Interior Lighting and Controls Acceptance | 0% |  | Sat 7/15/23 |  | Sat 7/15/23
2033 | 2022 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Wed 7/5/23 |  | Sat 7/15/23
2034 | 2022 | 1.2 | Building 2022 Exterior Lighting and Controls Installation | 100% |  | Wed 7/5/23 |  | Mon 7/10/23
2035 | 2022 | 1.2 | Building 2022 Exterior Lighting and Controls Acceptance | 0% |  | Sat 7/15/23 |  | Sat 7/15/23
2036 | 2022 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
2037 | 2022 | 2.1 | Building 2022 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
2038 | 2022 | 2.1 | Building 2022 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
2039 | 2022 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 11/1/23 |  | Wed 11/8/23
2040 | 2022 | 3.2 | Building 2022 Mechanical Insulation Installation | 0% |  | Wed 11/1/23 |  | Wed 11/1/23
2041 | 2022 | 3.2 | Building 2022 Mechanical Insulation Acceptance | 0% |  | Wed 11/8/23 |  | Wed 11/8/23
2042 | 2022 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 2/23/24 |  | Tue 3/5/24
2043 | 2022 | 3.1 | Building 2022 Steam Trap Replacement Installation | 0% |  | Fri 2/23/24 |  | Tue 2/27/24
2044 | 2022 | 3.1 | Building 2022 Steam Trap Replacement Acceptance | 0% |  | Tue 3/5/24 |  | Tue 3/5/24
2045 | 1307 |  | Building 1307 Mcalister Hall Installation | 24% |  | Thu 7/13/23 |  | Tue 4/23/24
2046 | 1307 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Thu 7/13/23 |  | Wed 7/19/23
2047 | 1307 | 6.1 | Building 1307 Building Envelope Installation | 95% |  | Thu 7/13/23 |  | Thu 7/13/23
2048 | 1307 | 6.1 | Building 1307 Building Envelope Acceptance | 0% |  | Wed 7/19/23 |  | Wed 7/19/23
2049 | 1307 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/1/23 |  | Tue 8/8/23
2050 | 1307 | 2.1 | Building 1307 Water Conservation Installation | 95% |  | Tue 8/1/23 |  | Tue 8/1/23
2051 | 1307 | 2.1 | Building 1307 Water Conservation Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
2052 | 1307 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 2/28/24 |  | Fri 3/8/24
2053 | 1307 | 3.1 | Building 1307 Steam Trap Replacement Installation | 0% |  | Wed 2/28/24 |  | Fri 3/1/24
2054 | 1307 | 3.1 | Building 1307 Steam Trap Replacement Acceptance | 0% |  | Fri 3/8/24 |  | Fri 3/8/24
2055 | 1307 | 8.1 | FIM 8.1 Kitchen Hood Controls or Upgrades | 0% |  | Fri 4/12/24 |  | Tue 4/23/24
2056 | 1307 | 8.1 | Building 1307 Kitchen Hood Controls or Upgrades Installation | 0% |  | Fri 4/12/24 |  | Tue 4/16/24
2057 | 1307 | 8.1 | Building 1307 Kitchen Hood Controls or Upgrades Acceptance | 0% |  | Tue 4/23/24 |  | Tue 4/23/24
2058 | 6 |  | Building 6 Dillard Building Installation | 35% |  | Sun 7/30/23 |  | Fri 8/16/24
2059 | 6 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Sun 7/30/23 |  | Mon 8/7/23
2060 | 6 | 6.1 | Building 6 Building Envelope Installation | 95% |  | Sun 7/30/23 |  | Mon 7/31/23
2061 | 6 | 6.1 | Building 6 Building Envelope Acceptance | 0% |  | Mon 8/7/23 |  | Mon 8/7/23
2062 | 6 | 8 | FIM 8.0 Controls Improvement | 95% |  | Fri 8/18/23 |  | Wed 8/30/23
2063 | 6 | 8 | Building 6 Controls Improvement Installation | 95% |  | Fri 8/18/23 |  | Fri 8/25/23
2064 | 6 | 8 | Building 6 Controls Improvement Acceptance | 0% |  | Wed 8/30/23 |  | Wed 8/30/23
2065 | 6 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
2066 | 6 | 2.1 | Building 6 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
2067 | 6 | 2.1 | Building 6 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
2068 | 6 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 11/2/23 |  | Thu 11/9/23
2069 | 6 | 3.2 | Building 6 Mechanical Insulation Installation | 0% |  | Thu 11/2/23 |  | Thu 11/2/23
2070 | 6 | 3.2 | Building 6 Mechanical Insulation Acceptance | 0% |  | Thu 11/9/23 |  | Thu 11/9/23
2071 | 6 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 3/4/24 |  | Wed 3/13/24
2072 | 6 | 3.1 | Building 6 Steam Trap Replacement Installation | 0% |  | Mon 3/4/24 |  | Wed 3/6/24
2073 | 6 | 3.1 | Building 6 Steam Trap Replacement Acceptance | 0% |  | Wed 3/13/24 |  | Wed 3/13/24
2074 | 6 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Fri 1/26/24 |  | Thu 2/8/24
2075 | 6 | 4.1 | Building 6 Seal HVAC Ductwork Installation | 0% |  | Fri 1/26/24 |  | Thu 2/1/24
2076 | 6 | 4.1 | Building 6 Seal HVAC Ductwork Acceptance | 0% |  | Thu 2/8/24 |  | Thu 2/8/24
2077 | 6 | 5.1 | FIM 5.1 Retro Cx | 0% |  | Mon 7/29/24 |  | Fri 8/16/24
2078 | 6 | 5.1 | Building 6 Retro Cx Installation | 0% |  | Mon 7/29/24 |  | Fri 8/9/24
2079 | 6 | 5.1 | Building 6 Retro Cx Acceptance | 0% |  | Fri 8/16/24 |  | Fri 8/16/24
2080 | 411 |  | Building 411 Godley Snell Research Installation | 21% |  | Mon 8/21/23 |  | Mon 3/18/24
2081 | 411 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
2082 | 411 | 6.1 | Building 411 Building Envelope Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
2083 | 411 | 6.1 | Building 411 Building Envelope Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
2084 | 411 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/22/23 |  | Sun 8/27/23
2085 | 411 | 2.1 | Building 411 Water Conservation Installation | 95% |  | Tue 8/22/23 |  | Tue 8/22/23
2086 | 411 | 2.1 | Building 411 Water Conservation Acceptance | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
2087 | 411 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Fri 11/3/23 |  | Fri 11/10/23
2088 | 411 | 3.2 | Building 411 Mechanical Insulation Installation | 0% |  | Fri 11/3/23 |  | Fri 11/3/23
2089 | 411 | 3.2 | Building 411 Mechanical Insulation Acceptance | 0% |  | Fri 11/10/23 |  | Fri 11/10/23
2090 | 411 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Thu 3/7/24 |  | Mon 3/18/24
2091 | 411 | 3.1 | Building 411 Steam Trap Replacement Installation | 0% |  | Thu 3/7/24 |  | Mon 3/11/24
2092 | 411 | 3.1 | Building 411 Steam Trap Replacement Acceptance | 0% |  | Mon 3/18/24 |  | Mon 3/18/24
2093 | 411 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Fri 2/2/24 |  | Tue 2/13/24
2094 | 411 | 4.1 | Building 411 Seal HVAC Ductwork Installation | 0% |  | Fri 2/2/24 |  | Tue 2/6/24
2095 | 411 | 4.1 | Building 411 Seal HVAC Ductwork Acceptance | 0% |  | Tue 2/13/24 |  | Tue 2/13/24
2096 | 1252 |  | Building 1252 Mickel Hall Installation | 48% |  | Tue 8/1/23 |  | Thu 3/21/24
2097 | 1252 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Tue 8/1/23 |  | Wed 8/9/23
2098 | 1252 | 6.1 | Building 1252 Building Envelope Installation | 95% |  | Tue 8/1/23 |  | Wed 8/2/23
2099 | 1252 | 6.1 | Building 1252 Building Envelope Acceptance | 0% |  | Wed 8/9/23 |  | Wed 8/9/23
2100 | 1252 | 1.1 | FIM 1.1 Interior Lighting and Controls | 95% |  | Tue 8/1/23 |  | Fri 8/11/23
2101 | 1252 | 1.1 | Building 1252 Interior Lighting and Controls Installation | 95% |  | Tue 8/1/23 |  | Fri 8/4/23
2102 | 1252 | 1.1 | Building 1252 Interior Lighting and Controls Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
2103 | 1252 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 95% |  | Tue 8/1/23 |  | Fri 8/11/23
2104 | 1252 | 1.2 | Building 1252 Exterior Lighting and Controls Installation | 95% |  | Tue 8/1/23 |  | Fri 8/4/23
2105 | 1252 | 1.2 | Building 1252 Exterior Lighting and Controls Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
2106 | 1252 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/1/23 |  | Tue 8/8/23
2107 | 1252 | 2.1 | Building 1252 Water Conservation Installation | 95% |  | Tue 8/1/23 |  | Tue 8/1/23
2108 | 1252 | 2.1 | Building 1252 Water Conservation Acceptance | 0% |  | Tue 8/8/23 |  | Tue 8/8/23
2109 | 1252 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Mon 11/6/23 |  | Mon 11/13/23
2110 | 1252 | 3.2 | Building 1252 Mechanical Insulation Installation | 0% |  | Mon 11/6/23 |  | Mon 11/6/23
2111 | 1252 | 3.2 | Building 1252 Mechanical Insulation Acceptance | 0% |  | Mon 11/13/23 |  | Mon 11/13/23
2112 | 1252 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Tue 3/12/24 |  | Thu 3/21/24
2113 | 1252 | 3.1 | Building 1252 Steam Trap Replacement Installation | 0% |  | Tue 3/12/24 |  | Thu 3/14/24
2114 | 1252 | 3.1 | Building 1252 Steam Trap Replacement Acceptance | 0% |  | Thu 3/21/24 |  | Thu 3/21/24
2115 | 1252 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Wed 2/7/24 |  | Thu 2/22/24
2116 | 1252 | 4.1 | Building 1252 Seal HVAC Ductwork Installation | 0% |  | Wed 2/7/24 |  | Thu 2/15/24
2117 | 1252 | 4.1 | Building 1252 Seal HVAC Ductwork Acceptance | 0% |  | Thu 2/22/24 |  | Thu 2/22/24
2118 | 406 |  | Building 406 Linvil Rich Environmental Research Lab Installation | 70% |  | Mon 8/7/23 |  | Tue 2/27/24
2119 | 406 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Mon 8/21/23 |  | Sat 8/26/23
2120 | 406 | 6.1 | Building 406 Building Envelope Installation | 95% |  | Mon 8/21/23 |  | Mon 8/21/23
2121 | 406 | 6.1 | Building 406 Building Envelope Acceptance | 0% |  | Sat 8/26/23 |  | Sat 8/26/23
2122 | 406 | 8 | FIM 8.0 Controls Improvement | 99% |  | Fri 9/8/23 |  | Thu 10/12/23
2123 | 406 | 8 | Building 406 Controls Improvement Installation | 99% | 99% | Fri 9/8/23 | 2023-09-08 | Thu 10/5/23 | 2023-10-06
2124 | 406 | 8 | Building 406 Controls Improvement Acceptance | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
2125 | 406 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Mon 8/7/23 |  | Thu 8/17/23
2126 | 406 | 1.1 | Building 406 Interior Lighting and Controls Installation | 0% |  | Mon 8/7/23 |  | Sat 8/12/23
2127 | 406 | 1.1 | Building 406 Interior Lighting and Controls Acceptance | 0% |  | Thu 8/17/23 |  | Thu 8/17/23
2128 | 406 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Wed 8/9/23 |  | Mon 8/14/23
2129 | 406 | 1.2 | Building 406 Exterior Lighting and Controls Installation | 0% |  | Wed 8/9/23 |  | Wed 8/9/23
2130 | 406 | 1.2 | Building 406 Exterior Lighting and Controls Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
2131 | 406 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Sun 8/20/23 |  | Fri 8/25/23
2132 | 406 | 2.1 | Building 406 Water Conservation Installation | 95% |  | Sun 8/20/23 |  | Sun 8/20/23
2133 | 406 | 2.1 | Building 406 Water Conservation Acceptance | 0% |  | Fri 8/25/23 |  | Fri 8/25/23
2134 | 406 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Fri 2/16/24 |  | Tue 2/27/24
2135 | 406 | 4.1 | Building 406 Seal HVAC Ductwork Installation | 0% |  | Fri 2/16/24 |  | Tue 2/20/24
2136 | 406 | 4.1 | Building 406 Seal HVAC Ductwork Acceptance | 0% |  | Tue 2/27/24 |  | Tue 2/27/24
2137 | 232 |  | Building 232 Rhodes Engineering Research Center Installation | 89% |  | Wed 8/16/23 |  | Tue 3/26/24
2138 | 232 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 8/16/23 |  | Wed 8/23/23
2139 | 232 | 6.1 | Building 232 Building Envelope Installation | 95% |  | Wed 8/16/23 |  | Fri 8/18/23
2140 | 232 | 6.1 | Building 232 Building Envelope Acceptance | 0% |  | Wed 8/23/23 |  | Wed 8/23/23
2141 | 232 | 1.1 | FIM 1.1 Interior Lighting and Controls | 99% |  | Mon 8/21/23 |  | Sun 10/1/23
2142 | 232 | 1.1 | Building 232 Interior Lighting and Controls Installation | 99% |  | Mon 8/21/23 |  | Mon 9/25/23
2143 | 232 | 1.1 | Building 232 Interior Lighting and Controls Acceptance | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
2144 | 232 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 99% |  | Mon 8/21/23 |  | Sun 10/1/23
2145 | 232 | 1.2 | Building 232 Exterior Lighting and Controls Installation | 99% |  | Mon 8/21/23 |  | Mon 9/25/23
2146 | 232 | 1.2 | Building 232 Exterior Lighting and Controls Acceptance | 0% |  | Sun 10/1/23 |  | Sun 10/1/23
2147 | 232 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Tue 8/22/23 |  | Sun 8/27/23
2148 | 232 | 2.1 | Building 232 Water Conservation Installation | 95% |  | Tue 8/22/23 |  | Tue 8/22/23
2149 | 232 | 2.1 | Building 232 Water Conservation Acceptance | 0% |  | Sun 8/27/23 |  | Sun 8/27/23
2150 | 232 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Tue 11/7/23 |  | Tue 11/14/23
2151 | 232 | 3.2 | Building 232 Mechanical Insulation Installation | 0% |  | Tue 11/7/23 |  | Tue 11/7/23
2152 | 232 | 3.2 | Building 232 Mechanical Insulation Acceptance | 0% |  | Tue 11/14/23 |  | Tue 11/14/23
2153 | 232 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Fri 3/15/24 |  | Tue 3/26/24
2154 | 232 | 3.1 | Building 232 Steam Trap Replacement Installation | 0% |  | Fri 3/15/24 |  | Tue 3/19/24
2155 | 232 | 3.1 | Building 232 Steam Trap Replacement Acceptance | 0% |  | Tue 3/26/24 |  | Tue 3/26/24
2156 | 232 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Wed 2/21/24 |  | Fri 3/1/24
2157 | 232 | 4.1 | Building 232 Seal HVAC Ductwork Installation | 0% |  | Wed 2/21/24 |  | Fri 2/23/24
2158 | 232 | 4.1 | Building 232 Seal HVAC Ductwork Acceptance | 0% |  | Fri 3/1/24 |  | Fri 3/1/24
2159 | 31 |  | Building 31 Sikes Hall Installation | 8% |  | Wed 8/9/23 |  | Mon 8/26/24
2160 | 31 | 6.1 | FIM 6.1 Building Envelope | 95% |  | Wed 8/9/23 |  | Mon 8/14/23
2161 | 31 | 6.1 | Building 31 Building Envelope Installation | 95% |  | Wed 8/9/23 |  | Wed 8/9/23
2162 | 31 | 6.1 | Building 31 Building Envelope Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
2163 | 31 | 8 | FIM 8.0 Controls Improvement | 0% |  | Sat 8/26/23 |  | Tue 9/5/23
2164 | 31 | 8 | Building 31 Controls Improvement Installation | 0% |  | Sat 8/26/23 |  | Tue 8/29/23
2165 | 31 | 8 | Building 31 Controls Improvement Acceptance | 0% |  | Tue 9/5/23 |  | Tue 9/5/23
2166 | 31 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 9/26/23 |  | Mon 10/9/23
2167 | 31 | 1.1 | Building 31 Interior Lighting and Controls Installation | 0% |  | Tue 9/26/23 |  | Mon 10/2/23
2168 | 31 | 1.1 | Building 31 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/9/23 |  | Mon 10/9/23
2169 | 31 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 9/28/23 |  | Wed 10/4/23
2170 | 31 | 1.2 | Building 31 Exterior Lighting and Controls Installation | 0% |  | Thu 9/28/23 |  | Thu 9/28/23
2171 | 31 | 1.2 | Building 31 Exterior Lighting and Controls Acceptance | 0% |  | Wed 10/4/23 |  | Wed 10/4/23
2172 | 31 | 8.2 | FIM 8.2 Control Optimization MDMP/MRR | 0% |  | Tue 8/13/24 |  | Mon 8/26/24
2173 | 31 | 8.2 | Building 31 Control Optimization MDMP/MRR Installation | 0% |  | Tue 8/13/24 |  | Mon 8/19/24
2174 | 31 | 8.2 | Building 31 Control Optimization MDMP/MRR Acceptance | 0% |  | Mon 8/26/24 |  | Mon 8/26/24
2175 | 31 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Mon 8/14/23 |  | Sat 8/19/23
2176 | 31 | 2.1 | Building 31 Water Conservation Installation | 95% |  | Mon 8/14/23 |  | Mon 8/14/23
2177 | 31 | 2.1 | Building 31 Water Conservation Acceptance | 0% |  | Sat 8/19/23 |  | Sat 8/19/23
2178 | 31 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Wed 11/8/23 |  | Wed 11/15/23
2179 | 31 | 3.2 | Building 31 Mechanical Insulation Installation | 0% |  | Wed 11/8/23 |  | Wed 11/8/23
2180 | 31 | 3.2 | Building 31 Mechanical Insulation Acceptance | 0% |  | Wed 11/15/23 |  | Wed 11/15/23
2181 | 31 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Wed 3/20/24 |  | Fri 3/29/24
2182 | 31 | 3.1 | Building 31 Steam Trap Replacement Installation | 0% |  | Wed 3/20/24 |  | Fri 3/22/24
2183 | 31 | 3.1 | Building 31 Steam Trap Replacement Acceptance | 0% |  | Fri 3/29/24 |  | Fri 3/29/24
2184 | 31 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Tue 9/26/23 |  | Tue 10/3/23
2185 | 31 | 3.3 | Building 31 Condensate Receiver Repair Installation | 0% |  | Tue 9/26/23 |  | Wed 9/27/23
2186 | 31 | 3.3 | Building 31 Condensate Receiver Repair Acceptance | 0% |  | Tue 10/3/23 |  | Tue 10/3/23
2187 | 378 |  | Building 378 Computer Center (ITC) Installation | 37% |  | Wed 8/16/23 |  | Fri 1/12/24
2188 | 378 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Sat 12/9/23 |  | Fri 1/12/24
2189 | 378 | 6.1 | Building 378 Building Envelope Installation | 0% | 99% | Sat 12/9/23 | 2023-10-13 | Fri 1/5/24 | 2023-10-13
2190 | 378 | 6.1 | Building 378 Building Envelope Acceptance | 0% |  | Fri 1/12/24 |  | Fri 1/12/24
2191 | 378 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 10/3/23 |  | Thu 10/12/23
2192 | 378 | 1.1 | Building 378 Interior Lighting and Controls Installation | 0% |  | Tue 10/3/23 |  | Thu 10/5/23
2193 | 378 | 1.1 | Building 378 Interior Lighting and Controls Acceptance | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
2194 | 378 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/16/23 |  | Wed 9/6/23
2195 | 378 | 2.1 | Building 378 Water Conservation Installation | 95% |  | Wed 8/16/23 |  | Wed 8/30/23
2196 | 378 | 2.1 | Building 378 Water Conservation Acceptance | 0% |  | Wed 9/6/23 |  | Wed 9/6/23
2197 | 1271 |  | Building 1271 Emerging Technology Center (ETC) Installation | 76% |  | Tue 8/8/23 |  | Thu 11/2/23
2198 | 1271 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/31/23 |  | Thu 9/7/23
2199 | 1271 | 6.1 | Building 1271 Building Envelope Installation | 0% |  | Thu 8/31/23 |  | Thu 8/31/23
2200 | 1271 | 6.1 | Building 1271 Building Envelope Acceptance | 0% |  | Thu 9/7/23 |  | Thu 9/7/23
2201 | 1271 | 8 | FIM 8.0 Controls Improvement | 80% |  | Tue 8/8/23 |  | Thu 11/2/23
2202 | 1271 | 8 | Building 1271 Controls Improvement Installation | 80% | 90% | Tue 8/8/23 | 2023-08-08 | Thu 10/26/23 | 2023-10-24
2203 | 1271 | 8 | Building 1271 Controls Improvement Acceptance | 0% |  | Thu 11/2/23 |  | Thu 11/2/23
2204 | 1271 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Fri 10/6/23 |  | Mon 10/16/23
2205 | 1271 | 1.1 | Building 1271 Interior Lighting and Controls Installation | 0% |  | Fri 10/6/23 |  | Mon 10/9/23
2206 | 1271 | 1.1 | Building 1271 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/16/23 |  | Mon 10/16/23
2207 | 1271 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Tue 10/10/23 |  | Tue 10/17/23
2208 | 1271 | 1.2 | Building 1271 Exterior Lighting and Controls Installation | 0% |  | Tue 10/10/23 |  | Tue 10/10/23
2209 | 1271 | 1.2 | Building 1271 Exterior Lighting and Controls Acceptance | 0% |  | Tue 10/17/23 |  | Tue 10/17/23
2210 | 1271 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 9/6/23 |  | Tue 9/12/23
2211 | 1271 | 2.1 | Building 1271 Water Conservation Installation | 95% |  | Wed 9/6/23 |  | Wed 9/6/23
2212 | 1271 | 2.1 | Building 1271 Water Conservation Acceptance | 0% |  | Tue 9/12/23 |  | Tue 9/12/23
2213 | 379 |  | Building 379 Hunter Auditorium Installation | 12% |  | Thu 8/17/23 |  | Mon 10/23/23
2214 | 379 | 6.1 | FIM 6.1 Building Envelope | 0% |  | Thu 8/17/23 |  | Tue 8/22/23
2215 | 379 | 6.1 | Building 379 Building Envelope Installation | 0% | 99% | Thu 8/17/23 | 2023-10-16 | Thu 8/17/23 | 2023-10-16
2216 | 379 | 6.1 | Building 379 Building Envelope Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
2217 | 379 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 10/10/23 |  | Mon 10/23/23
2218 | 379 | 1.1 | Building 2023 Interior Lighting and Controls Installation | 0% |  | Tue 10/10/23 |  | Mon 10/16/23
2219 | 379 | 1.1 | Building 2023 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/23/23 |  | Mon 10/23/23
2220 | 379 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 10/12/23 |  | Thu 10/19/23
2221 | 379 | 1.2 | Building 2023 Exterior Lighting and Controls Installation | 0% |  | Thu 10/12/23 |  | Thu 10/12/23
2222 | 379 | 1.2 | Building 2023 Exterior Lighting and Controls Acceptance | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
2223 | 379 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Thu 8/17/23 |  | Tue 8/22/23
2224 | 379 | 2.1 | Building 379 Water Conservation Installation | 95% |  | Thu 8/17/23 |  | Thu 8/17/23
2225 | 379 | 2.1 | Building 379 Water Conservation Acceptance | 0% |  | Tue 8/22/23 |  | Tue 8/22/23
2226 | 22 |  | Building 22 Sirrine Hall Installation | 31% |  | Fri 8/4/23 |  | Wed 4/3/24
2227 | 22 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Wed 8/30/23 |  | Sun 9/10/23
2228 | 22 | 6.1 | Building 22 Building Envelope Installation | 99% |  | Wed 8/30/23 |  | Mon 9/4/23
2229 | 22 | 6.1 | Building 22 Building Envelope Acceptance | 0% |  | Sun 9/10/23 |  | Sun 9/10/23
2230 | 22 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 8/4/23 |  | Fri 8/11/23
2231 | 22 | 2.1 | Building 22 Water Conservation Installation | 95% |  | Fri 8/4/23 |  | Fri 8/4/23
2232 | 22 | 2.1 | Building 22 Water Conservation Acceptance | 0% |  | Fri 8/11/23 |  | Fri 8/11/23
2233 | 22 | 3.2 | FIM 3.2 Mechanical Insulation | 0% |  | Thu 11/9/23 |  | Thu 11/16/23
2234 | 22 | 3.2 | Building 22 Mechanical Insulation Installation | 0% |  | Thu 11/9/23 |  | Thu 11/9/23
2235 | 22 | 3.2 | Building 22 Mechanical Insulation Acceptance | 0% |  | Thu 11/16/23 |  | Thu 11/16/23
2236 | 22 | 3.1 | FIM 3.1 Steam Trap Replacement | 0% |  | Mon 3/25/24 |  | Wed 4/3/24
2237 | 22 | 3.1 | Building 22 Steam Trap Replacement Installation | 0% |  | Mon 3/25/24 |  | Wed 3/27/24
2238 | 22 | 3.1 | Building 22 Steam Trap Replacement Acceptance | 0% |  | Wed 4/3/24 |  | Wed 4/3/24
2239 | 22 | 4.1 | FIM 4.1 Seal HVAC Ductwork | 0% |  | Mon 2/26/24 |  | Fri 3/8/24
2240 | 22 | 4.1 | Building 22 Seal HVAC Ductwork Installation | 0% |  | Mon 2/26/24 |  | Fri 3/1/24
2241 | 22 | 4.1 | Building 22 Seal HVAC Ductwork Acceptance | 0% |  | Fri 3/8/24 |  | Fri 3/8/24
2242 | 22 | 3.3 | FIM 3.3 Condensate Receiver Repair | 0% |  | Thu 9/28/23 |  | Thu 10/5/23
2243 | 22 | 3.3 | Building 22 Condensate Receiver Repair Installation | 0% |  | Thu 9/28/23 |  | Fri 9/29/23
2244 | 22 | 3.3 | Building 22 Condensate Receiver Repair Acceptance | 0% |  | Thu 10/5/23 |  | Thu 10/5/23
2245 | 6207 |  | Building 6207 Snow Family Outdoor Fitness and Wellness Center Installation | 95% |  | Fri 9/1/23 |  | Fri 9/8/23
2246 | 6207 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Fri 9/1/23 |  | Fri 9/8/23
2247 | 6207 | 2.1 | Building 6207 Water Conservation Installation | 95% |  | Fri 9/1/23 |  | Fri 9/1/23
2248 | 6207 | 2.1 | Building 6207 Water Conservation Acceptance | 0% |  | Fri 9/8/23 |  | Fri 9/8/23
2249 | 6220 |  | Building 6220 University Facilities Complex Installation | 55% |  | Wed 8/2/23 |  | Mon 10/30/23
2250 | 6220 | 6.1 | FIM 6.1 Building Envelope | 99% |  | Tue 9/5/23 |  | Mon 9/11/23
2251 | 6220 | 6.1 | Building 6220 Building Envelope Installation | 99% |  | Tue 9/5/23 |  | Tue 9/5/23
2252 | 6220 | 6.1 | Building 6220 Building Envelope Acceptance | 0% |  | Mon 9/11/23 |  | Mon 9/11/23
2253 | 6220 | 8 | FIM 8.0 Controls Improvement | 95% |  | Wed 8/2/23 |  | Mon 8/14/23
2254 | 6220 | 8 | Building 6220 Controls Improvement Installation | 95% |  | Wed 8/2/23 |  | Wed 8/9/23
2255 | 6220 | 8 | Building 6220 Controls Improvement Acceptance | 0% |  | Mon 8/14/23 |  | Mon 8/14/23
2256 | 6220 | 1.1 | FIM 1.1 Interior Lighting and Controls | 0% |  | Tue 10/17/23 |  | Mon 10/30/23
2257 | 6220 | 1.1 | Building 6220 Interior Lighting and Controls Installation | 0% |  | Tue 10/17/23 |  | Mon 10/23/23
2258 | 6220 | 1.1 | Building 6220 Interior Lighting and Controls Acceptance | 0% |  | Mon 10/30/23 |  | Mon 10/30/23
2259 | 6220 | 1.2 | FIM 1.2 Exterior Lighting and Controls | 0% |  | Thu 10/19/23 |  | Thu 10/26/23
2260 | 6220 | 1.2 | Building 6220 Exterior Lighting and Controls Installation | 0% |  | Thu 10/19/23 |  | Thu 10/19/23
2261 | 6220 | 1.2 | Building 6220 Exterior Lighting and Controls Acceptance | 0% |  | Thu 10/26/23 |  | Thu 10/26/23
2262 | 6220 | 2.1 | FIM 2.1 Water Conservation | 95% |  | Wed 8/30/23 |  | Wed 9/6/23
2263 | 6220 | 2.1 | Building 6220 Water Conservation Installation | 95% |  | Wed 8/30/23 |  | Wed 8/30/23
2264 | 6220 | 2.1 | Building 6220 Water Conservation Acceptance | 0% |  | Wed 9/6/23 |  | Wed 9/6/23
2265 |  |  | Project Closeout | 0% |  | Tue 10/29/24 |  | Wed 3/26/25
2266 |  |  | O&M Manuals/Fnl As-Builts/Training Docs/Warrainties | 0% |  | Thu 3/13/25 |  | Wed 3/26/25
2267 |  |  | Fnl M&V Report | 0% |  | Tue 10/29/24 |  | Mon 11/11/24
2268 |  |  | Demobilize Site | 0% |  | Fri 2/14/25 |  | Wed 3/26/25
2269 |  |  | Final Customer Acceptance | 0% |  | Wed 3/26/25 |  | Wed 3/26/25